REQUEST FOR PROPOSAL: Stakeholder Education, Advocacy, and Outreach

RFP STAKEHOLDER PARENTS AND CAREGIVERS_002

Parents and Caregivers
2019

www.mhsoac.ca.gov

State of California

Mental Health Services Oversight and Accountability Commission

Contents

I.	INTRODUCTION	5

A.	PURPOSE AND BRIEF OVERVIEW OF CONTRACT OPPORTUNITY	6

B.	KEY ACTION DATES	8

C.	CONTRACT TERM AND AVAILABLE FUNDING	9

D.	WRITTEN QUESTIONS	9

E.	CONTACT INFORMATION	9

II.	BACKGROUND	10

A.	THE MENTAL HEALTH SERVICES ACT	10

B.	MHSA VALUES	10

C.	MHSA FUNDING	11

D.	MHSOAC ROLES AND RESPONSIBILITIES	11

E.	REGIONS	12

III.	PROPOSER QUALIFICATIONS	12

A.	MINIMUM QUALIFICATIONS	12

B.	DESIRED QUALIFICATIONS	13

C.	PROPOSER BACKGROUND	13

D.	PROPOSER CAPACITY	14

IV.	SCOPE OF WORK	14

A.	CONTRACTOR RESPONSIBILITIES	14

B.	DELIVERABLES	20

C.	SUBCONTRACTOR REPLACEMENT	21

D.	FUNDING	21

V.	WORKPLAN AND COST WORKSHEET	22

A.	WORKPLAN	22

B.	COST WORKSHEET	26

VI.	REFERENCES	26

VII.	PROPOSAL SUBMISSION INSTRUCTIONS	27

A.	REQUIRED DOCUMENTS	27

B.	REQUIRED FORMAT FOR A PROPOSAL	28

C.	NUMBER OF COPIES	28

D.	PACKAGING AND LABELING	28

VIII.	LATE SUBMISSIONS	29

IX.	SCORING PROCESS	29

A.	PROPOSAL SCORING	29

B.	COMMERCIALLY USEFUL FUNCTION	40

C.	AWARD PROCEDURES	41

X.	ADMINISTRATION	42

A.	COST OF DEVELOPING PROPOSAL	42

B.	CONFIDENTIAL INFORMATION	42

C.	DARFUR CONTRACTING ACT OF 2008	42

D.	RFP CANCELLATION AND AMENDMENTS	42

E.	ERRORS IN THE RFP	43

F.	MODIFYING OR WITHDRAWAL OF PROPOSAL	43

G.	IMMATERIAL DEFECT	43

H.	DISPOSITION OF PROPOSALS	43

I.	PROPOSER’S ADMONISHMENT	43

J.	REJECTION OF PROPOSAL	43

K.	PROTEST PROCEDURES	44

L.	AGREEMENT EXECUTION AND PERFORMANCE	45

M.	OTHER ATTACHMENTS	45

ATTACHMENT 1: Required Attachments Checklist	47

ATTACHMENT 2: Proposal/Proposer Certification Sheet	48

ATTACHMENT 3: Secretary of State Registration	49

ATTACHMENT 4: Minimum Qualifications	50

ATTACHMENT 5: Proposer Background	51

ATTACHMENT 6: LOCAL COMMUNITY ENGAGEMENT PLAN	53

ATTACHMENT 7: LOCAL COMMUNITY ENGAGEMENT TASKS AND ACTIVITIES	56

ATTACHMENT 8: STATE LEVEL ENGAGEMENT PLAN	63

ATTACHMENT 9: STATE LEVEL ENGAGEMENT TASKS AND ACTIVITIES	65

ATTACHMENT 10: Cost Worksheet	71

ATTACHMENT 11: References (Organization)	73

ATTACHMENT 12: References (Parents AND Caregivers)	75

ATTACHMENT 13: Bidder Declaration (GSPD-05-105)	77

ATTACHMENT 14: Contract Certification Clauses (CCC-307)	78

ATTACHMENT 15: Darfur Contracting Act Certification (if applicable)	82

ATTACHMENT 16: Payee Data Record (STD 204)	83

ATTACHMENT 17: Sample Contract	84

EXHIBIT A – Scope of Work	84

Exhibit B - Budget Detail and Payment Provisions	86

EXHIBIT C – GENERAL TERMS AND CONDITIONS (GTC 610)	89

EXHIBIT D – SPECIAL TERMS AND CONDITIONS (SAC 1216)	93

ATTACHMENT 18: Questions Template	99

## INTRODUCTION

The Mental Health Services Oversight and Accountability Commission (MHSOAC or Commission) is seeking an experienced Contractor to work with Parents and Caregivers of Children and Youth to enhance local participation, voice, and empowerment through advocacy, education, and outreach efforts. A goal of this RFP is to ensure that parents and caregivers of children and youth have a major role in the development and implementation of local level mental health policies and programs, as well as access to quality services and supports.

The Commission’s budget includes funding for competitive bid contracts to support mental health advocacy on behalf of specific communities.  The intent is to ensure that there be meaningful stakeholder involvement at both the state and local level and that funds are provided to ensure advocacy, outreach, and education and training. Funds are available to support advocacy efforts on behalf of clients/consumers, parents and caregivers of children and youth, transition age youth (TAY), veterans, family members of clients/consumers, LGTBQ communities, immigrant and refugee communities, and diverse racial and ethnic communities. This RFP is designed to support advocacy, outreach, and education and training to address the mental health needs of children and youth as well as the needs of the parents and caregivers (hereafter “Parents and Caregivers”).

The contract awarded pursuant to this Request for Proposal (RFP) is to support the advocacy, education, and outreach needs of parents and caregivers. These activities include informing, educating, and advocating before local administrative bodies regarding issue-based policies consistent with the Mental Health Services Act.

Parents and caregivers include the parents, foster parents, grandparents, caregivers and those who are raising or caring for a child and/or youth, including transition age youth that have received or are currently receiving services for a mental health diagnosis, including crisis care.

The 2019-2020 Governor’s Budget summary states highlights the need to “to continue to seek new, innovative approaches to intervene as early as possible when mental illness is detected, especially in young people.” Parents and caregivers play a critical role in supporting children’s and youth’s physical and mental health and well-being. Parents, however, often face immense challenges in navigating California’s mental health system and accessing quality treatment and supports for kids in their care. The mental health needs of children affect every family member and often result in the needs of others being unmet, including those of parents and caregivers.

Parents and caregivers of children and youth with mental health needs face additional challenges when trying to identify individuals who can provide safe temporary care to their family member. Respite care has been identified by parents and caregivers as one of the top three needs for themselves and those they care for.  Respite has been shown to help sustain family caregiver health, enhance the mental wellness of both parents and caregivers and the children and youth under their care, and avoid or delay out-of-home placements, and reduce the likelihood of abuse and neglect, yet respite care is only available in a few communities throughout the state.

Through a response to this RFP, the successful Proposer will demonstrate that they have the personnel and organizational capacity to effectively carry out a contract of this scope and magnitude. The successful Proposer will describe how they meet minimum and desired qualifications, including their breadth of experience working statewide with Parents and Caregivers of children and youth with special emphasis on unserved, underserved, and hard to reach populations. While collaborative Proposals including subcontractors are acceptable and even encouraged to provide the relevant range of expertise and/or capacity, the Proposal must be submitted by a lead or prime contractor, hereinafter called “Proposer.”

All agreements entered into with the State will include by reference General Terms and Conditions (GTC) (see ATTACHMENT 17, EXHIBIT C) and Contractor Certification Clauses (CCC-307) (see ATTACHMENT 14). Subcontractors are permitted by the MHSOAC for this contract. The Contractor shall manage and coordinate subcontractor activities. Proposers are encouraged to carefully read the entire RFP. The need to verify all documentation and responses prior to the submission of Proposals cannot be overemphasized. Please note that no verbal information given will be binding upon the State unless such information is issued in writing as an official addendum. In the opinion of MHSOAC, this RFP is complete and without need of explanation. All questions must be submitted directly to the MHSOAC via email to: mhsoac@mhsoac.ca.gov.  Include the RFP name and number in the subject line.

### PURPOSE AND BRIEF OVERVIEW OF CONTRACT OPPORTUNITY

The passage of the Mental Health Services Act (MHSA or Act) initiated, at the state and local levels, the concept of transparent and collaborative processes being implemented to determine the mental health needs, priorities, and services for California mental health consumers and their families.

Welfare and Institutions (W&I) Code Section 5892(d) requires the Mental Health Services administrative fund to “include funds to assist consumers and family members to ensure the appropriate state and county agencies give full consideration to concerns about quality, structure of service delivery, or access to services.”

Through the MHSA, California has encouraged the transformation of its mental health system by supporting the need for and development of a partnership between state and local level planning and program implementation. The MHSA was designed to change not only the way people accessed mental health services and participated in policy planning, but to change public perception and stigma associated with mental illness. Through support of stakeholder advocacy efforts, MHSA funding encourages dialogue to address not just the local needs of a community and region but to align with state level needs and priorities in a way that acknowledges and adheres to the diverse cultural values among California’s Parents and Caregivers.

One contract will be awarded to a state-level advocacy organization to provide advocacy, training and education, and outreach and engagement on behalf of Parents and Caregivers populations throughout California.

This contract opportunity supports the goals of the MHSA and proposes to support the goal of system transformation through the engagement and participation of Parents and Caregivers that is client and family driven, culturally competent, and collaborative in design. This contract will provide the opportunity to conduct local Parents and Caregivers-led events which highlight local mental health services available to Parents and Caregivers, provide an opportunity to learn from Parents and Caregivers what needs exist in their local communities, reduce stigma, and inform local county leadership on the specific needs of the population.

##### Community Engagement Efforts

To support the development of this contract opportunity, the MHSOAC engaged in an extensive community consultation process to learn more about Parents and Caregivers communities and to collect input from individuals and those working with and on behalf of these populations.

An information survey was administered to learn more about the types of county and community-based organizations located across the state that are serving Parents and Caregivers communities in California. Surveys asked respondents to provide their input regarding what services they provide, the most critical needs of the populations they serve, how they determined the most critical needs, how success is determined in meeting those needs, and the most effective tools in working with Parents and Caregivers. They were also asked about collaboration efforts and current organization funding.

Parent and Caregiver surveys indicated that the most critical need of the population is training and education for parents on how to effectively address the mental health needs of their children. The need for materials and resource guides was indicated as a helpful tool for parents and caregivers who are seeking information on available services and supports. Surveys indicate that parents and caregivers without appropriate transportation and housing face significant barriers in accessing care. Service organization representatives who responded to the survey indicated that the most effective method to determine the needs of the population are community advocacy events, parent and caregiver organization meetings and focus groups. Respondents listed several state and local organizations with whom parents and caregivers are working with including county mental health departments, local service providers, faith-based organizations, and school districts. Surveys indicated that time constraints and the demanding role of parents and caregivers requires support to be provided through social media and websites which direct parents to services and event announcements.

In addition, public listening sessions were conducted to hear from individuals within the community about the barriers to seeking and receiving mental health services and to better understand how those needs could be addressed through advocacy, training, and outreach efforts. Through these open discussion forums, participants identified a number of individual and systemic challenges to accessing and receiving care.

More than 50 stakeholders attended listening sessions that were held for each of the six stakeholder populations to gather information about how funds should be spent, consistent with the needs of the six populations. Though each group expressed issues unique to their community, the feedback provided expressed in the listening sessions were consistent with the survey findings.

Listening Session findings indicated the need for:

•	Increased access to relevant, culturally competent mental health services

•	Stakeholder inclusion in local level decision making processes

•	Stakeholder representation and engagement in the local mental health planning process

•	Stigma and discrimination reduction

•	Expansion of peer, parent, and family support

•	Work force training and education

##### Goals and Objectives

The goals and objectives of the contract are to bring awareness of the challenges and issues facing the Parents and Caregivers populations through advocacy, training and education, and outreach and engagement at the local levels, with the expectation that service providers increase services and access to the services that are needed and that government or private entities provide funding to address these unmet needs.

### KEY ACTION DATES

Key actions including dates and times for this RFP are presented below.

| Action | Action Date & Time |
| --- | --- |
| RFP Release | December 5, 2019 |
| Deadline for Written Questions | December 12, 2019 |
| Distribute Questions/Answers and Addenda (if any) to RFP | December 18, 2019 |
| Deadline to Submit Proposals | January 31, 2020 by 4:00 p.m. |
| Notice of Intent to Award* | February 27, 2020 |
| Anticipated Contract Start Date* | April/May 2020 |

* Dates after Deadline to Submit Proposals are estimates and may be changed by the Commission without the issuance of an addendum.

### CONTRACT TERM AND AVAILABLE FUNDING

The available funding for this RFP is a total of $2,010,000, with funds available as follows: $550,000 year 1, $670,000 year 2, and $790,000 Year 3. It is anticipated that the work on this contract will begin in July 2020, and continue for a period of 39 months, or three (3) years, three (3) months. Payment to the Contractor shall be based on the satisfactory completion and delivery of each project deliverable for the total fixed price of $2,010,000.

Organizations submitting proposals on more than one Stakeholder RFP (e.g. Clients and Consumers, Diverse Racial and Ethnic Communities, Families of Clients and Consumers, LGBTQ, Parents and Caregivers of Children and Youth, Transitional Age Youth (TAY), and Veterans) during this round, must demonstrate the capability and capacity to successfully complete the scope of work for multiple target populations.  Proposed locations and dates for event activities cannot be the same in the multiple proposals.

The MHSOAC may withhold funds from the Contractor if the Contractor fails to meet the reporting requirements, perform the activities, submits the deliverables by the due date, falls behind schedule, or modifies the scope of the work performed.

### WRITTEN QUESTIONS

During the RFP process, questions about this RFP must be directed to the Procurement Official listed in the Contact Information section below. Inquires shall be put in writing and communicated via email to: mhsoac@mhsoac.ca.gov by 4:00 p.m. Pacific Standard Time (PST) on December 12, 2019. Use Attachment 18, Questions Template, to submit your questions. At its discretion, MHSOAC reserves the right to contact a Proposer to seek clarification of any inquiry received.

All questions will be answered in writing. The questions and answers will be posted on the MHSOAC’s website at: www.mhsoac.ca.gov.

Any changes to the RFP will be made in the form of an addendum. Please note that no verbal information given will be binding upon the MHSOAC unless such information is confirmed in writing as an official addendum.

### CONTACT INFORMATION

Michele Nottingham, Procurement Official

Mental Health Services Oversight and Accountability Commission

1325 J Street, Suite 1700

Sacramento, CA 95814

E-mail: mhsoac@mhsoac.ca.gov

## BACKGROUND

### THE MENTAL HEALTH SERVICES ACT

In 2004, the MHSA was approved through a voter initiative (Proposition 63). The MHSA was designed to support and encourage system-wide change in California’s public community mental health system that would foster a positive impact on the state’s prevention of and response to mental illness. The MHSA was crafted to finance culturally and linguistically competent, new-generation, promising approaches to delivery of mental health services for Californians of all ages using approaches that incorporate the critical elements of hope, recovery, personal empowerment, respect, social connection, self-responsibility, and self-determination. The MHSA is intended to encourage early identification of and response to indicators of mental health needs, treat mental illness, promote recovery, reduce the duration of untreated mental illness, prevent the negative impact of untreated mental illness, and reduce stigma and discrimination associated with mental illness.

The Act emphasizes an expectation for participatory planning that engages a broad range of stakeholders, including diverse individuals with mental health needs and their families, representatives of communities that are unserved and underserved by the community mental health system, as well as service providers and mental health policy makers. The engagement and participation of these stakeholders should be meaningful and play a partnership role in all mental health decisions.

The Act and subsequent legislation intends that there be a meaningful stakeholder involvement at both the state and local level and that funds are provided to ensure advocacy, outreach, and education and training on behalf of clients and consumers, parents and caregivers of children and youth, transition age youth (TAY), veterans, families of clients and consumers, LGTBQ communities, immigrant and refugee communities, and organizations working to reduce racial and ethnic disparities. This RFP is designed to support advocacy and outreach on behalf of Parents and Caregivers in the mental health system.

### MHSA VALUES

The MHSA articulates values that are expected to be embedded throughout planning, policy development, implementation, and evaluation of the MHSA. These values are codified in Title 9, California Code of Regulations, Section 3320 and/or by actions of the MHSOAC and include:

- Community Collaboration: Diverse clients and/or families receiving services, other community members, agencies, organizations, and businesses work together to share information and resources to create and fulfill a shared vision and goals.

- Cultural Competence: All aspects of policy-making, program design, administration, and service delivery in the public mental health system incorporate and include work to achieve equal access to services, equal quality of services, and equal outcomes of services, without disparities among racial/ethnic, cultural, linguistic, and other diverse populations or communities.

- Client- and Family-Driven: The client, parent/caregiver of children and youth has the primary decision-making role in identifying needs, preferences, and strengths, and a shared decision-making role in determining the services and supports that are most effective and helpful.

- Wellness-, Recovery-, Resilience-Focused Service Delivery: Public mental health services promote and increase resilience, recovery, and wellness.

- Integrated Service Experiences: Clients, and when appropriate a client’s parent/caregiver and family, access a full range of services in a comprehensive and coordinated manner, even when these services are provided by multiple agencies, programs, and funding sources.

- Co-occurring Disorder Services Competency: Services incorporate appropriate methods to ensure that co-occurring disorders are treated efficiently and in a cost-effective manner.

### MHSA FUNDING

The Act establishes a one percent (1%) tax on personal income in excess of one (1) million dollars. These funds are dedicated in specified proportions for the following components:  Community Services and Supports (CSS); Prevention and Early Intervention (PEI); Workforce, Education, and Training (WET); Capital Facilities and Technological Needs (CF/TN); and Innovation (INN). In addition, up to five percent (5%) of funding received is provided for state administrative activities, including stakeholder contract funding, and local incentive funding for specific grant programs.

The statutory requirement in W&I Code Section 5892(d) states that the Mental Health Services fund shall “include funds to assist consumers and family members to ensure the appropriate state and county agencies give full consideration to concerns about quality, structure of service delivery, or access to services.”

Further, W&I Code Section 5846(d) states that the MHSOAC shall “ensure that the perspective and participation of diverse community members reflective of California populations and others suffering from severe mental illness and their family members is a significant factor in all of [the Commission’s] decisions and recommendations.”

### MHSOAC ROLES AND RESPONSIBILITIES

The MHSA established the MHSOAC to provide oversight and accountability for California’s mental health system. The Commission is committed to:

- Effective oversight and accountability that may be achieved via evaluation of MHSA processes, values, and outcomes;

- An approach of continuous quality improvement including tracking and evaluating processes and outcomes in a manner that supports critical system-wide improvements; and

- Increasing meaningful stakeholder involvement in all aspects of California’s mental health system including the local planning and decision-making process as it relates to Parents and Caregivers mental health services which promote wellness, recovery, and resilience.

### REGIONS

For the purposes of this procurement, regions are defined as follows:

- Bay Area: Alameda, Contra Costa, Marin, Monterey, Napa, San Benito, San Francisco, San Mateo, Santa Clara, Santa Cruz, Solano, and Sonoma counties, and City of Berkeley.

- Central: Alpine, Amador, Calaveras, El Dorado, Fresno, Inyo, Kings, Madera, Mariposa, Merced, Mono, Placer, Sacramento, San Joaquin, Stanislaus, Sutter-Yuba (Joint Powers), Tulare, Tuolumne, and Yolo counties.

- Los Angeles: County of Los Angeles.

- Southern: Imperial, Kern, Orange, Riverside, San Bernardino, San Diego, San Luis Obispo, Santa Barbara, and Ventura counties, and Tri-City (Pomona, Claremont, La Verne).

- Superior: Butte, Colusa, Del Norte, Glenn, Humboldt, Lake, Lassen, Mendocino, Modoc, Nevada, Plumas, Shasta, Sierra, Siskiyou, Tehama and Trinity counties.

## PROPOSER QUALIFICATIONS

An individual who is authorized to bind the proposing firm contractually shall sign ATTACHMENT 2 (Proposal/Proposer Certification Sheet). The original signature must indicate the title or position that the individual holds in the firm. An unsigned or signature stamped Proposal may be rejected.

Evidence that Proposer is registered and has a current active status with the California Secretary of State (SOS) to do business in California is required as detailed in ATTACHMENT 3. The registration can be pending at the time of bid submission but must be complete by the time at which a contract is awarded.

### MINIMUM QUALIFICATIONS

Each of the minimum qualifications below must be met by the Proposer. The Proposer shall include documentation and reference the documentation within the Proposal that verifies each qualification (see ATTACHMENT 4).

- Be an established state-level organization which has been in operation for 2 years and has experience with programs and services related to the unique mental health issues of California’s Parents and Caregivers populations;

- Have experience and capacity to partner with local community-based organizations working on mental health issues of Parents and Caregivers;

- Be a non-profit organization, registered to do business in California;

- Have more than 50% of staff or board members who are Parents and Caregivers.

### DESIRED QUALIFICATIONS

The following are desired qualifications of the Proposer:

- Have comparable experience in advocacy, outreach, and training activities related to the mental health needs of children and youth and their Parents and Caregivers;

- Have experience that demonstrates capability to manage a project of similar duration and funding;

- Have experience in designing culturally competent approaches to engagement and outreach targeting Parents and Caregivers;

- Have experience with incorporating concepts of client and family resilience and recovery into programs, projects, training, and technical assistance;

- Have experience and capacity to coordinate a State Level Advocacy event with legislative visits.

Desired qualifications will be validated based on References.

### PROPOSER BACKGROUND

Provide responses to the following on ATTACHMENT 5, Proposer Background:

- Describe what your organization does to advocate for the mental health and wellness needs of children and youth and their Parents and Caregivers.

- What counties, regions, or areas of the State do you serve?

- What counties do you have a branch/physical presence located?

  - Provide support

- How do you determine where service gaps may exist for the Parents and Caregivers populations that you serve?

- What are the specific outcomes you are working toward?

- What do you measure to determine the success of your approach?

- How long has your organization been in existence?

  - Provide support

- How many staff/employees do you have?  This does not include volunteers or contractors.

  - Provide support.

- How many staff/employees are Parents and Caregivers? This does not include volunteers or contractors.

  - Provide support.

### PROPOSER CAPACITY

Proposers must demonstrate in their plan their capacity to successfully conduct all duties included in this RFP.  Therefore, Proposers may perform all the duties independently, or with other individuals, groups, organizations through an informal agreement or through a contract (subcontractor), or contract (subcontractor) with a Local Level Entity (LLE).  Subcontractors are to be paid directly by the Contractor.  Payment amounts to an LLE are listed on ATTACHMENT 10 – Cost Worksheet, lines 16 – 30. In addition, the LLE must meet the requirements listed in V.A.2.e.2.  The definition of a LLE is a group of people organized at a local level (e.g. county) for a common lawful purpose, whether formally organized (e.g. Non-profit organization) or informally organized (e.g. Unincorporated Associations).

## SCOPE OF WORK

### CONTRACTOR RESPONSIBILITIES

##### PARENTS AND CAREGIVERS POPULATION

The Contractor will be responsible to represent the needs of children and youth and their parents and caregivers through state-level advocacy and policy engagement.  In addition, the Contractor will provide technical assistance and support to conduct training, outreach activities and advocacy meetings at the local/county level. The Contractor will be responsible for the following:

- Provide state-level, statewide advocacy for mental health policies which support the mental health and wellness of children and youth and their parents and caregivers.

- Conduct advocacy with local/county decision makers and outreach events to the Parents and Caregivers community.

- Provide training and technical assistance to individuals and local organizations to grow their capacity for ongoing advocacy efforts.

- Write a State of the Community report each year.

- Plan and implement a Parents and Caregivers-led statewide event each year.

- Attend MHSOAC Collaboration meetings

- Track legislation that impacts Parents and Caregivers mental health services

Effective implementation of this contract will require ongoing reporting, meetings, and updates between the Contractor and the MHSOAC.

The Contractor shall determine whether it has the capacity and capability to perform all duties by themselves or with the assistance of a Local Level Entity (subcontractor).

##### LOCAL COMMUNITY ENGAGEMENT

Contractor shall conduct 15 local Parents and Caregivers-led events to provide outreach, engagement, education, and advocacy opportunities for Parents and Caregivers and local decision-making bodies at the local/county level.  Five (5) events will be conducted per year, for a total of fifteen (15) events during the contract period. No less than two (2) events shall occur in each of the five (5) regions of the State (Bay Area, Central, Los Angeles, Southern, and Superior) over the contract period, without duplicating the event location in any of the regions.

The MHSOAC is seeking from the Proposers creative ways to hold an event that is tailored to the target population.

- Engagement events shall include:

      - Local Advocacy Activity:

        - An informational presentation to local level decision makers, which may include the County Board of Supervisors, City Council, Mental Health Department Administrators, Educational entities, and/or other local leaders who provide support, direction, or funding for behavioral/mental health services and activities.

          - Informational Presentations shall be held prior to the local Parents and Caregivers engagement event to encourage local leaders to attend.

        - The presentation shall focus on education, advocacy, and awareness of the mental health needs of children and youth and their parents and caregivers.  In addition, the following shall be presented:

          - An overview of the unique mental health needs of the children and youth and their parents and caregivers including advocacy needs and challenges they face at the local level;

          - An overview of the Parents and Caregivers Engagement event planned in their county and the outreach strategy used to promote the event and support Parents and Caregivers participation;

          - The importance of the Parents and Caregivers perspective in the local mental health Community Program Planning (CPP) Process;

          - The local individuals and/or organizations involved in planning, hosting, and supporting the Parents and Caregivers Engagement event, and

          - Invitation to the local leaders to attend the Parents and Caregivers engagement event which follows the presentation.

        - Contractor will promote the event to maximize awareness and attendance.  All marketing materials created, that are non-advocacy in nature, need to include the MHSOAC logo.  As such, all materials with the MHSOAC logo need to be approved by the MHSOAC prior to being used and disseminated for public release.

      - Parents and Caregivers Engagement Event:

        - A community-based, Parents and Caregivers led event for local Parents and Caregivers focused on engagement, education, and awareness. Events shall occur in areas where Parents and Caregivers are likely to spend time in their communities, i.e., schools and community centers, with an emphasis on unserved/underserved communities and neighborhoods.

        - Contractor shall incorporate the following activities, goals and objectives into the events:

          - Promote awareness of and linkage to local services and supports;

          - Provide information regarding local employment, volunteer opportunities and job skills training for Parents and Caregivers;

          - Encourage and promote principles of wellness, recovery, and resiliency activities;

          - Provide awareness of and strategies for reducing stigma and discrimination associated with mental health needs;

          - Conduct a listening session with event participants to elicit feedback and comments from the community regarding Parents and Caregivers issues with mental health services, including what is needed to address the issues.  Information heard at the listening sessions shall be documented and presented to the MHSOAC and local level decision makers, including, but not limited to county behavioral health departments; and

          - The Contractor shall prominently display the MHSOAC logo at the 15 local-level events and the 3 state-level events.

        - Contractor will promote the event to maximize awareness and attendance.  All marketing materials created, that are non-advocacy in nature, need to include the MHSOAC logo.  As such, all materials with the MHSOAC logo need to be approved by the MHSOAC prior to being used and disseminated for public release.

##### STATE LEVEL ADVOCACY EVENT

##### The Contractor shall host annually a State Level Advocacy event (e.g. Day at the Capitol).  The event shall include State level leaders and administrators to learn about the specific mental health issues of Parents and Caregivers and to show the Statewide support.  Contractor shall plan the event, host the event and follow-up with after-event activities as described below.

The intent is to grow this event through attendance and participation each year of the contract term.

- Contractor shall be responsible for planning the event, including securing facilities/grounds, arranging legislative visits, booking speakers (State legislators, State Department executives/administrators, public-figures, etc.) mental health organization participation (booths, speakers, etc.) arranging for LLEs, local level support groups and/or individuals connected to the Parents and Caregivers community  to attend.  Budgeted funds of $10,000 per local/county area in which there has been a Local Community Engagement event are available to assist these groups to attend.

- Contractor is required to achieve Parents and Caregivers participation/attendance goals of 75, year 1; 150, year 2; and 225, year 3.

- Contractor shall host the event including coordinating the event activities and Master of Ceremony duties.

- Contractor shall be responsible for after-event activities including following up with all the speakers and participants and creating an Event Summary Report.

- In addition, and in conjunction with this event, Contractor shall conduct Technical Assistance training on advocacy for all of the LLEs, local level support groups or individuals connected to the Parents and Caregivers community that are attending.

- Contractor shall be responsible for Post-Event activities, including but not limited to:

  - Follow up with State and Local decision-makers who attended to continue advocacy

  - Follow up with other attendees to obtain feedback and continue advocacy and outreach

  - Completion of all summaries and/or reports

##### MEETINGS

##### Kickoff Meeting

  - The Contractor shall attend a kickoff meeting with the MHSOAC Contract Manager (CM). The Contractor’s Project Manager (PM) and other key staff shall attend this meeting to discuss the administrative (e.g. finalizing dates), fiscal (e.g. payment milestones), and technical aspects (e.g. reports) of this contract. MHSOAC will designate the date and location of this meeting.

##### Collaboration

  - The Contractor shall attend periodic in-person collaboration meetings with other Contractors to be held at a time and place as determined by the MHSOAC. The purpose of these meetings will be to bring together stakeholder contractors to report out on current activities, discuss upcoming projects and plans, and to identify areas for potential collaboration. The Contractor must plan to send a minimum of two people (including the Project Manager) to these meetings.

##### Other Interactions with MHSOAC

  - The Contractor shall engage in ongoing communication with the MHSOAC and relevant constituents regarding progress within all facets of this project. Specifically, the Contractor shall be prepared to, at the request of the Commission:

    - Provide an annual update of Workplan and deliverables;

    - Maintain ongoing interaction with MHSOAC staff and other MHSOAC constituents;

    - Participate in briefing calls with MHSOAC staff to discuss project progress and the status of Deliverables;

    - Provide periodic updates and presentations to MHSOAC Committees and Commissioners;

    - Present the final results/conclusions of this work to Commissioners and the public at a Commission meeting; and

    - Develop and provide a plan for dissemination of Deliverables to MHSOAC stakeholders.

##### REPORTS

The contractor shall provide the following reports:

  - State of the Community Report

      - Demographic information on the population served;

      - Barriers to accessing mental health care;

      - Programs and services needed to address mental health needs of children and youth and their parents and caregivers;

      - Innovative approaches to meeting the mental health needs of Parents and Caregivers;

      - Statistical overview of the number of children and youth and their parents and caregivers in need of mental health services versus those who are utilizing services;

      - Legislation and policy agenda annual summary;

      - Survey and post event results;

      - Recommendations for action by specific state and local agencies; and

      - Summary of all the listening event information captured from participants

  - Quarterly Reports

These reports shall outline the planning efforts underway for the 15 local Parents and Caregivers-led events, planning efforts for the annual State Level Advocacy event, as well as an Event Summary detailing the activities and outcomes of each completed local event. The quarterly report shall include the following:

        - Status of local training, outreach, and advocacy events including:

            - Who the Contractor is contracting with at the local level;

            - Where are they planning to hold the events;

            - Who they plan to meet with for local outreach to decision-makers;

            - Dates of meetings or events which have been scheduled;

            - Communication plan to highlight the event; and

            - Outreach plan to drive attendance.

        - Status of State Level Advocacy event planning

            - Outreach plan to drive attendance;

            - Date, time, location;

            - Specific goals;

            - Speakers being arranged;

            - Travel logistics for local level advocacy organizations;

            - Legislator visit planning; and

            - Communication plan to highlight the event.

        - Event Summary

Summary of Parents and Caregivers Engagement Events held during the quarter, detailing the activities and outcomes of each completed local event.  The Contractor shall report the relevant information to MHSOAC including but not limited to:

      - The county name and specific location of the outreach and engagement event;

      - The number of Parents and Caregivers attending each event;

      - Local individuals and/or organizations that assisted with the event;

      - Lessons learned regarding the needs of Parents and Caregivers in the target community;

      - Response from the local level decision-making body to the Informational Presentation (Attach a copy of the presentation);

      - Planned follow up activities with local level decision-making body; and

      - Recommendations to the MHSOAC regarding the mental health needs of children and youth and their parents and caregivers and the involvement of Parents and Caregivers in local planning efforts.

      - Listening session reporting template completed, detailing the information captured at the listening sessions

        - Legislative Tracking Summary

Contractor shall report on legislation that is being tracked, including:

              - Bill number;

              - Bill Summary;

              - Relationship to the mental health of children and youth and their parents and caregivers;

              - Impact to the MHSOAC, MHSA, and Mental Health Services Fund;

              - Who supports and opposes;

              - Planned activities for the next reporting period; and

              - Any other information that is relevant to the Parents and Caregivers population.

  - Payment Milestone Status Report

- The contractor agrees to provide a Payment Milestone Status Report with each invoice that will need to be reviewed and approved by the MHSOAC prior to invoice payment.  The MHSOAC reserves the right to contact the contractor to discuss the report as part of the review and approval process.

- The report shall contain the following information:

  - Summary of activities that occurred within the reporting period

  - A statement on whether or not the event and all the planning activities are on schedule; and

  - If not on schedule, provide the reason(s) for not being on schedule and the corrective action to address reason(s).

  - Based on this information, the MHSOAC may choose one of the following options:

    - Approve the report and payment

    - Approve the report, request additional information (including meetings) to assist the correction, and approve the payment

    - Request additional information before the report and payment are approved

  - Record Keeping

    - The Contractor shall ensure that all funds provided under this contract to the Contractor and LLEs can be accounted for separately during the contract term. At a minimum, upon request of the MHSOAC, the Contractor shall provide a monthly fund reconciliation for the funds allocated to the Contractor and the funds allocated to the LLEs, as follows:

- Beginning Fund balance

- Monthly expenditures

- Ending Fund balance

### DELIVERABLES

This is a deliverable based contract and the contractor agrees to provide the following deliverables:

                - Payment Milestone Status Report

- An activity summary report based on the detailed list of activities and tasks identified for each proposed event (see Section IV.A. Contractor Responsibilities for detail) as described above in Section 5. Reports

- This report is due prior to the invoice being approved for payment.

                - State of the Community Report

- Annual report (see Section IV.A. Contractor Responsibilities for detail) as described above in Section 5. Reports.

- Report is due within 30 days after each 12-month contract term for years 1 and 2.  Year 3 report is due within 90 days of the last 12-month contract term.

                - Quarterly Report

- Quarterly Report (see Section IV.A. Contractor Responsibilities for detail) as described above in Section 5. Reports.

- Report is due within 30 days after each quarter

### SUBCONTRACTOR REPLACEMENT

The Contractor is required to use all subcontractors listed in their proposal.  If, during the contract term, there is a need to replace a subcontractor, the Contractor must obtain approval from the Commission before such change is made.  The Commission may require that the Contractor present to the Commission the reason for the change and the plan to ensure all contractual obligations are met and in accordance with the contract schedule and no change will occur unless the Commission agrees to the change.

### FUNDING

The Contractor agrees to the budgeted funding listed on the Cost Worksheet (ATTACHMENT 10), including the amounts listed on lines 16 – 30, to be paid directly to the LLE, if applicable. The Contractor further agrees to commit spending at least half of the money designated as “Event” (Lines 1 – 15) and “Additional Local Community Engagement” (Lines 16 – 30) directly on the Local Community Event.  The remaining monies may be spent on administration (up to 15% each, of lines 16 – 30 budgeted funding), continued local level advocacy, outreach, and training.

The Contractor also agrees to the budgeted funding listed on the Cost Worksheet (ATTACHMENT 10), including the amounts listed on line 31, “State Level Advocacy Event”. The Contractor further agrees to commit spending at least half of the money designated as “State Level Advocacy Event” directly on the State Level Advocacy Event, less amounts budgeted for assistance for local level groups and individuals to attend (Section IV.A.3.a.).  The remaining monies may be spent on administration (up to 15% of line 31 budgeted funding), continued state level advocacy, outreach, and training.

Budgeted funds included in this section as are as follows (References are to ATTACHMENT 10 – Cost Worksheet):

- Event

  - Lines 1 – 15, $34,000 each

  - Commit spending $17,000 directly on each event

- Additional Local Community Engagement

  - Lines 16 – 20, First Year, $30,000 each

    - Commit spending $15,000 directly on each event

  - Line 21 – 25, Second Year, $30,000 each

    - Commit spending $15,000 directly on each event

  - Line 26 – 30, Third Year, $30,000 each

    - Commit spending $15,000 directly on each event

- State Level Advocacy Event

  - Line 31, First Year, $170,000, attendance assistance budget $50,000

    - $170,000 - $50,000 = $120,000 / 2 = $60,000 spend directly on the event

  - Line 31, Second Year, $220,000, attendance assistance budget $100,000

    - $220,000 - $100,000 = $120,000 / 2 = $60,000 spend directly on the event

  - Line 31, Third Year, $270,000, attendance assistance budget $150,000

    - $270,000 - $150,000 = $120,000 / 2 = $60,000 spend directly on the event.

## WORKPLAN AND COST WORKSHEET

### WORKPLAN

The Proposer shall respond to the requirement by completing the following worksheets:

      - ATTACHMENT 6 – Local Community Engagement Plan

      - ATTACHMENT 7 – Local Community Engagement Tasks and Activities

      - ATTACHMENT 8 – State Level Engagement Plan

      - ATTACHMENT 9 – State Level Engagement Tasks and Activities

The Attachments represent the Proposer’s detailed plan as to how the Proposer plans to complete all work required by the RFP.

LOCAL COMMUNITY ENGAGEMENT PLAN (ATTACHMENT 8)

- Describe, in detail, the plan for successfully completing all the tasks identified in Section IV.A.2., Local Community Engagement. (There is no restriction on the proposal as to how you plan to accomplish the tasks ).

  - In addition, provide a response to the following:

    - Will your organization be providing all of the services by yourself or with others (e.g. individuals, associations, LLEs, etc.)?

      - If using other people outside of your staff, identify them, if known at this time (individuals do not need to be identified by name), describe their role, the number of staff they will be providing, the amount they will be paid.

    - How does your plan target traditionally unserved, underserved, and hard to reach Parents and Caregivers populations?

      - Identify the specific Parents and Caregivers population being targeted.

    - How does your plan address the local Parents and Caregivers needs?

      - Identify the Parents and Caregivers needs that are addressed.

    - What are the expected outcomes/measurements of success from your plan?

    - What is your plan to promote the Local Engagement Events in order to maximize attendance in the local/county area?

The intent is for MHSOAC to fully understand that you have the experience, capability and capacity to perform all required tasks under this contract.

LOCAL COMMUNITY ENGAGEMENT TASKS AND ACTIVITIES (ATTACHMENT 8)

- For each event required under this RFP (15 Parents and Caregivers Engagement Events), the Proposer shall provide the following information:

        - Event Name

- Enter the unique name of the Event.

        - Event Location

          - Enter the proposed location of the event.  The location can be specific to an actual physical location (e.g. school name) or a geographic location (e.g. city or county.)

          - Provide enough information in order for the Commission to identify the California region

        - Event Date

          - Enter date (Month and Year)

          - Five (5) events must be held in each contract year

        - Event Description

          - Provide a narrative describing the proposed event

        - Staffing

          - Identify who will participate in conducting the Local Community Engagement, if more than the Proposer’s staff (e.g. individuals, groups, organizations, contracted LLE, etc.) and provide the following for each participant.  Do not include Local Level Entities on this line.

            - Name (Organization or state “Individual”)

            - Location/Address

            - Number of staff participating

            - Role/Tasks assigned

          - If contracting with a Local Level Entity, provide the following information:

            - Organization Name

            - Organization Address (must be in the area where the local engagement event will be held)

            - Organization Contact (Name, Title, Email)

            - Documented Relationship. (e.g. MOU, Letter between the organizations verifying the commitment to use this organization, etc.).  Documentation must be signed by both parties and cannot be signed by a fiscal agent of the Local Level Entity.

            - Number of staff

            - Role/Task assigned

- PRE-EVENT ACTIVITIES

  - List all the activities/tasks that are needed to plan and conduct the proposed event

    - Activities/Tasks should be in alignment and support your proposed Workplan

    - Add additional lines to the template, as needed.

    - The intent here is for the MHSOAC to have a full understanding of the Proposer’s understanding of the requirements and ability to plan and host these events

  - Enter the dates when each activity/task needs to be completed.

    - Dates provided should be a reasonable amount of time prior to the event to give assurance in the Proposer’s ability to successfully conduct an event

- EVENT ACTIVITIES

- List all the activities that will be provided at this event

- Provide a detailed list of the activities that will be available at the event.  Add additional lines or pages to the template, if needed.

- POST-EVENT ACTIVITIES

- List all the activities/tasks that are planned as part of your post-event follow up.

      - Add additional lines to the template, as needed.

      - Activities/tasks provided should cover the length of time still remaining on the contract.

        - For events held in the first year of the contract, activities/tasks should address the remaining time available in the first year of the contract from the date of the event and the two (2) subsequent contract years.

        - For events held in the second year of the contract, activities/tasks should address the remaining time available in the second year of the contract from the date of the event and the one (1) subsequent contract year.

        - For events held in the third year of the contract, activities/tasks should address the remaining time available in the third year of the contract from the date of the event.

      - The intent here is for the MHSOAC to have a full understanding of the Proposer’s ability to plan and host these events with appropriate after-event follow-up through the end of the contract.

- Enter the dates when each activity/task is planned to be completed.

- Dates provided should correspond to the length of time still remaining on the contract.

        - For events held in the first year of the contract, dates should address the remaining time available in the first year of the contract from the date of the event and the two (2) subsequent contract years

        - For events held in the second year of the contract, dates should address the remaining time available in the second year of the contract from the date of the event and the one (1) subsequent contract year.

        - For events held in the third year of the contract, dates should address the remaining time available in the third year of the contract from the date of the event.

STATE LEVEL ENGAGEMENT PLAN (ATTACHMENT 8)

- Describe, in detail, the plan for successfully completing all the tasks identified in SectionIV.A.3. State Level Advocacy Event. (There is no restriction on the type of plan that can be proposed).

  - In addition, provide a response to the following:

    - Will your organization be providing all of the services by yourself or with others (e.g. individuals, associations, LLEs, etc.)?

      - If using other staff, identify the groups (if known; individuals do not need to be identified by name), describe their role, the number of staff they will be providing, the amount they will be paid.

    - What are the expected outcomes/measurements of success from your plan?

    - What is your plan to promote the State Level Engagement Events in order to meet participation and attendance goals?

STATE LEVEL ENGAGEMENT TASKS AND ACTIVITIES (ATTACHMENT 9)

- For each event required under this RFP (3 State Level Advocacy events), the Proposer shall provide the following information:

  - Event Name

    - Enter the unique name of the Event.

  - Event Location

    - Enter the proposed location of the event.  The location can be specific to an actual physical location (e.g. school name) or a geographic location (e.g. city or county.)

  - Event Date

    - Enter date (Month and Year)

  - Event Description

    - Provide a narrative describing the proposed event

- PRE-EVENT ACTIVITIES

  - List all the activities/tasks that are needed to plan and conduct the proposed event

- Activities/Tasks should be in alignment and support your proposed Workplan

- Add additional lines to the template, as needed.

- The intent here is for the MHSOAC to have a full understanding of the Proposer’s ability to plan and host these events

- Enter the dates when each activity/task needs to be completed.

  - Dates provided should be a reasonable amount of time prior to the event to give assurance in the Proposer’s ability to successfully conduct an event.

- EVENT ACTIVITIES

  - List the activities that will be provided at this event

    - Provide a detailed list of the activities that will be available at the event.  Add additional lines or pages to the template, if needed

- POST-EVENT ACTIVITIES

  - List all the activities/tasks that are planned as part of your post-event wrap up.

    - Add additional lines to the template, as needed

    - Activities/tasks provided should cover the length of time still remaining on the contract.

      - For events held in the first year of the contract, activities/tasks should address the remaining time available in the first year of the contract from the date of the event and the two (2) subsequent contract years

      - For events held in the second year of the contract, activities/tasks should address the remaining time available in the second year of the contract from the date of the event and the one (1) subsequent contract year.

      - For events held in the third year of the contract, activities/tasks should address the remaining time available in the third year of the contract from the date of the event

    - The intent here is for the MHSOAC to have a full understanding of the Proposer’s ability to plan and host these events with appropriate after-event follow-up

    - Enter the dates when each activity/task is planned to be completed

### COST WORKSHEET

Costs are fixed for each activity/event/deliverable.  The line item costs are listed in the Cost Worksheet (ATTACHMENT 10).  Cost is not a factor in the evaluation of the proposal as the full $2,010,000 for 3 years 3 months will be awarded.  Therefore, the cost worksheet shall not be updated by the Proposer.

## REFERENCES

The Proposer shall provide four (4) references as follows:  two (2) references shall be from organizations for which the Proposer has worked with in providing state and/or local advocacy for the identified population (ATTACHMENT 11, References (Organization)); and two (2) references will be from individuals from the identified population, who have received training and education, and/or outreach and engagement from the proposer related to mental health needs and are not a family member of a board member and/or employee of the Proposer, or employed by the Proposer (ATTACHMENT 12, References (Parents and Caregivers)).  All references shall be from activities performed within the last two (2) years.

The references provided must be able to attest to the Proposer’s ability in meeting the desirable qualifications.  The references will fill out Attachment 11 or 12, sign the document and return to the Proposer to be submitted as part of the proposal.

## PROPOSAL SUBMISSION INSTRUCTIONS

This section contains the format requirements and instructions on how to submit a Proposal. The format is prescribed to assist the Proposer in meeting State bidding requirements and to enable the Commission to evaluate each Proposal uniformly and fairly. Proposers must follow all Proposal format instructions, answer all questions, and supply all required documents.

### REQUIRED DOCUMENTS

Proposals shall include all required attachments and be organized in the following order:

- Attachment 1: Required Attachment Checklist

- Attachment 2: Proposal/Proposer Certification Sheet

- Attachment 3: Secretary of State Registration

- Attachment 4: Minimum Qualifications

- Attachment 5: Proposer Background

- Attachment 6: Local Community Engagement Plan

- Attachment 7: Local Community Engagement Tasks and Activities

- Attachment 8: State Level Engagement Workplan

- Attachment 9: State Level Engagement Tasks and Activities

- Attachment 10: Cost Worksheet

- Attachment 11: References (Organization)

- Attachment 12: References (Parents and Caregivers)

- Attachment 13: Bidder Declaration (GSPD-05-105)

- Attachment 14: Contractor Certification Clauses (CCC-307)

- Attachment 15: Darfur Contracting Act Certification (if applicable)

- Attachment 16: Payee Data Record (STD 204)

Proposals not including all of the above listed items, with proper signatures when required, shall be deemed non-compliant. A non-compliant Proposal is one that does not meet the basic Proposal requirements and may be rejected.

### REQUIRED FORMAT FOR A PROPOSAL

Proposals shall be submitted in three-ring binders with tabs between each section. A Table of Contents shall be included and all pages shall be numbered.  An electronic copy of the Proposal on a USB drive must be submitted to MHSOAC with the physical copies.  Proposals must comply with all RFP requirements. Before submitting a response to this RFP, Proposers should review the Proposal, correct all errors, and confirm compliance with the RFP requirements. Not complying with all of the RFP requirements is cause for a Proposal to be rejected.

### NUMBER OF COPIES

Proposers must submit one (1) original Proposal plus four (4) paper copies of the Proposal. All hard copy submittals should use clearly marked tabs, page numbers and table of contents for effective access to the Respondent’s material. The original Proposal must be marked “MASTER.” All documents contained in the original Proposal package must have wet signatures and must be signed by a person who is authorized to bind the proposing firm. All additional Proposal sets may contain photocopies of the original package. If discrepancies exist between two (2) or more copies of the response, the response may be rejected. However, if not rejected, the Master Copy will provide the basis for resolving such discrepancies

The original Proposal package, all required copies, and the electronic copy of the Proposal must be submitted together by the due date. If they are not submitted together by the due date the Proposal will be considered non-compliant

### PACKAGING AND LABELING

Proposals must be received by January 31, 2020 no later than 4:00 p.m. Pacific Time by the MHSOAC. Proposals must be in a sealed package and must be delivered in person, by a postal service (United States Post Office, Federal Express, etc.), or by overnight delivery. Faxed and emailed Proposals will not be accepted. It is not sufficient to postmark Proposals by this date or to leave the Proposals at the MHSOAC without a MHSOAC staff member confirming delivery. This office is open 8:00 a.m. to 5:00 p.m., Monday-Friday except state holidays.

Please mail or deliver the Proposal to the address listed below. Include the following label information and deliver your Proposal in a sealed package:

Proposer’s Name

Street Address

City, State, Zip Code

DO NOT OPEN

RFP STAKEHOLDER Families and Caregivers_002

Families and Caregivers Stakeholder Contract

Michele Nottingham, Procurement Official

Mental Health Services Oversight and Accountability Commission

1325 J Street, Suite 1700, Sacramento, California 95814

Note: All Proposals must be submitted under sealed cover and received by MHSOAC Contracts Unit by the date and time shown above. Proposals received after this date and time will not be considered.

## LATE SUBMISSIONS

Late proposals will not be accepted regardless of the method sent. Proposer assumes all risk of late delivery by any method. Proposals received after the deadline will be rejected without review. Incomplete submissions may be rejected without review.

## SCORING PROCESS

This section explains how the Proposals will be scored.

### PROPOSAL SCORING

Proposals will be evaluated and scored based on their response to the information requested in this RFP. Evaluation will be conducted based on consensus scoring of the Evaluation Panel. The entire procurement process from issuance of the RFP, to the receipt of proposals, and scoring of the proposals until completion of the competitive process, with the issuance of the Intent to Award is confidential. All Proposals and the final evaluation and scoring sheet will be considered public documents upon completion of the competitive process and issuance of the Notice of Intent to Award.

Proposals will be evaluated as follows:

#### Administrative Review

Each Proposal will first be checked by the MHSOAC for the presence of all required documents as listed in Section VII.A. This review will be scored on a pass/fail basis. Those Proposals that pass the Administrative Review move on to the Technical Review. Those Proposals that do not meet the requirements of Administrative Review will be deemed non-compliant and will not be eligible to receive an award.

#### Technical Review

Each Proposal will be evaluated and scored based on the Proposer’s ability to successfully manage a program that meets the Scope of Work and requirements stated in the RFP.  The Evaluation will be based on meeting the aspects of the following requirements:

- Attachment 5: Proposer Background

- Attachment 6: Local Community Engagement Plan

- Attachment 7: Local Community Engagement Tasks and Activities

- Attachment 8: State Level Engagement Plan

- Attachment 9: State Level Engagement Tasks and Activities

- Attachment 10: Cost Worksheet

- Attachment 11: References (Organization)

- Attachment 12: References (Parents and Caregivers)

Total Points Available:

| No. | Requirement | Points Available |
| --- | --- | --- |
| 1 | Administrative Review | Pass/Fail |
| 2 | Background Review* | Pass/Fail 600 |
| 3 | Workplan Review | 9,460 |
| 4 | References | 2,000 |
| 5 | Total Evaluation Points | 12,060 |

* Background Review includes Pass/Fail and Scored requirements.

Evaluation Criteria

The following criteria will be used, where applicable:

| No. | Criteria | Definition |
| --- | --- | --- |
| 1 | Clarity | The ease at which the information presented is understood. |
| 2 | Reasonableness | The reasonableness of the information presented being accomplished successfully and is in alignment with the requirement. |
| 3 | Alignment with current functions being performed and proposed by Proposer. | Focus is on activities that have proven successful in the past for the organization. |
| 4 | Alignment with the goal, objectives, and requirements of this RFP and MHSA values. | Focus is on activities that support the stated goal, objectives, and requirements of this RFP and MHSA values |

Scoring

| Minimally addresses the requirement | Partially meets the requirement | Fully meets the requirement |
| --- | --- | --- |
| 1 | 3 | 5 |

Each Evaluation Criteria used will be given a score of 1, 3, or 5.  Multiple Evaluation Criteria may be used for each requirement.  See Evaluation Scoring Detail.

Evaluation Scoring Detail

| No. | Requirement | Points Available |
| --- | --- | --- |
| III.C. BACKGROUND |  |  |
| C.1. | Describe what your organization does to advocate for the mental health and wellness needs of children and youth and their parents and caregivers | Pass / Fail |
| C.2. | What counties, regions, or areas of the State do you serve? | Pass / Fail |
| C.3. | What counties do you have a branch/physical presence located? | Pass/Fail |
| C.3.a. | Provide Support. Scoring Criteria: 100 Points = 1 Unique Region 150 Points = 2 Unique Regions 200 Points = 3 Unique Regions 250 Points = 4 Unique Regions 300 Points = 5 Unique Regions | 300 |
| C.4. | How do you determine where service gaps may exist for the Parents and Caregivers populations that you serve? | Pass / Fail |
| C.5. | What are the specific outcomes you are working toward? | Pass / Fail |
| C.6. | What do you measure to determine the success of your approach? | Pass / Fail |
| C.7. | How long has your organization been in existence? | Pass / Fail |
| C.7.a. | Provide Support. Scoring Criteria: Clarity, Reasonableness (Max 100 points available. Calculated: Clarity and Reasonableness are worth 5 points each. Score will be multiplied by 10 to award max points) | 100 |
| C.8. | How many staff do you have? This does not include volunteers or contractors. | Pass / Fail |
| C.8.a. | Provide support Scoring Criteria: Clarity, Reasonableness (Max 100 points available. Calculated: Clarity and Reasonableness are worth 5 points each. Score will be multiplied by 10 to award max points) | 100 |
| C.9 | How many staff are Parents and Caregivers? This does not include volunteers or contractors. | Pass / Fail |
| C.9.a. | Provide Support. Scoring Criteria: Clarity, Reasonableness (Max 100 points available. Calculated: Clarity and Reasonableness are worth 5 points each. Score will be multiplied by 10 to award max points) | 100 |
| TOTAL BACKGROUND POINTS |  | 600 |
| V. WORKPLAN |  |  |
| A.1. | LOCAL COMMUNITY ENGAGEMENT PLAN |  |
| A.1. | Describe, in detail, the plan for successfully completing all the tasks identified in Section IV.A.2., Local Community Engagement. Scoring Criteria: Clarity, Reasonableness, Alignment with current functions being performed and proposed, Alignment with the goal and objectives of this RFP and MHSA values. Each criteria is worth 5 points each. Score will be multiplied by 50 to award max points. Maximum points available is 1000 points (4 criteria x 5 points each x 50) | 1000 |  |
| A.1.a.1. | Will your organization be providing all of the services by yourself or with others (e.g. individuals, associations, LLEs, etc.)? Scoring Criteria: Clarity. Each criteria is worth 5 points each. Score will be multiplied by 2 to award max points. Maximum points available is 10 points ( 5 points each x 2 ) | 10 |
| A.1.a.1. (a) | If using other people outside of your staff, identify them, if known at this time (individuals do not need to be identified by name), describe their role, the number of staff they will be providing, and the amount they will be paid. Scoring Criteria: Clarity, Reasonableness, Alignment with current functions being performed and proposed, Alignment with the goal and objectives of this RFP and MHSA values. Each criteria is worth 5 points each. Score will be multiplied by 20 to award max points. Maximum points available is 400 points (4 criteria x 5 points each x 20) | 400 |
| A.1.a.2. | How does your plan target traditionally unserved, underserved, and hard to reach Parents and Caregivers populations? Scoring Criteria: Clarity, Reasonableness, Alignment with current functions being performed and proposed, and Alignment with the goals, objectives, and requirements of the RFP and MHSA Values. Each criteria is worth 5 points each. Score will be multiplied by 5. Maximum points available is 100 points (4 criteria x 5 points each x 5) | 100 |
| A.1.a.2. (a) | Identify the specific Parents and Caregivers population being targeted. Scoring Criteria: Clarity, Reasonableness, and Alignment with the goals, objectives, and requirements of the RFP and MHSA Values. Each criteria is worth 5 points each. Score will be multiplied by 3. Maximum points available is 45 points (3 criteria x 5 points each x 3) | 45 |
| A.1.a.3. | How does your plan address the local Parents and Caregivers needs? Scoring Criteria: Clarity, Reasonableness, Alignment with current functions being performed and proposed, and Alignment with the goals, objectives, and requirements of the RFP and MHSA Values. Each criteria is worth 5 points each. Score will be multiplied by 5. Maximum points available is 100 points (4 criteria x 5 points each x 5) | 100 |
| A.1.a.3. (a) | Identify the Parents and Caregivers needs that are addressed Scoring Criteria: Clarity, Reasonableness, and Alignment with the goals, objectives, and requirements of the RFP and MHSA Values. Each criteria is worth 5 points each. Score will be multiplied by 3. Maximum points available is 45 points (3 criteria x 5 points each x 3) | 45 |
| A.1.a.4. | What are the expected outcomes/measurements of success from your plan? Scoring Criteria: Clarity, Reasonableness, Alignment with current functions being performed and proposed, and Alignment with the goals, objectives, and requirements of the RFP and MHSA Values. Each criteria is worth 5 points each. Score will be multiplied by 5. Maximum points available is 100 points (4 criteria x 5 points each x 5) | 100 |
| A.1.a.5. | What is your plan to promote the Local Engagement Events in order to maximize attendance in the local/county area? Scoring Criteria: Clarity, Reasonableness, Alignment with current functions being performed and proposed, and Alignment with the goals, objectives, and requirements of the RFP and MHSA Values. Each criteria is worth 5 points each. Score will be multiplied by 5. Maximum points available is 100 points (4 criteria x 5 points each x 5) | 100 |
| A.2. | LOCAL COMMUNITY ENGAGEMENT TASKS AND ACTIVITIES |  |
| A.2.a. | Event Name Scoring Criteria: Clarity. Each criteria is worth 5 points each, per event. Score will be multiplied by 0.20 to award max points. Maximum points available is 15 points (15 events x 5 point each x 0.20 ) | 15 |
| A.2.b.. | Event Location Scoring Criteria: Clarity and Reasonableness. Each criteria is worth 5 points each, per event. Score will be multiplied by 0.20 to award max points Maximum points available is 30 points (15 events x 2 criteria x 5 points each x 0.20) | 30 |
| A.2.b. | Event Location Confirm the Event Location meets the requirement of No less than two (2) events shall occur in each of the five (5) regions of the State over the contract period, without duplicating the event location in any of the regions (Meets requirement = 500 points, Does not meet = 0 points) | 500 |
| A.2.c. | Event Date (Month and Year) Scoring Criteria: Clarity and Reasonableness. Confirm the Event Date meets the requirement of 5 events per year. If not, proposal does not Pass the requirement. Each criteria is worth 5 points each, per event. Score will be multiplied by 0.20 to award max points. Maximum points available is 30 points (15 events x 2 criteria x 5 points each x 0.20) | 30 |
| A.2.c. | Event Date Confirm the Event Date meets the requirement of five (5) events must be held in each contract year (Meets requirement = 100 points, Does not meet = 0 points) | 100 |
| A.2.d. | Event Description Scoring Criteria: Clarity, Reasonableness, Alignment with current functions being performed and proposed, and Alignment with the goals, objectives, and requirements of the RFP and MHSA Values. Each criteria is worth 5 points each. Score will be multiplied by 2. Maximum points available is 600 points (15 events x 4 criteria x 5 points each x 2) | 600 |
| A.2.e.1. | Staffing Scoring Criteria: Clarity and Reasonableness. Each criteria is worth 5 points each. Score will be multiplied by 3. Maximum points available is 450 points (15 events x 2 criteria x 5 points each x 3) | 450 |
| A.2.e.2. | Staffing (Local Level Entity) Scoring Criteria: Clarity and Reasonableness. Each criteria is worth 5 points each. Score will be multiplied by 6. Maximum points available is 900 points (15 events x 2 criteria x 5 points each x 6) | 900 |
| A.3. | PRE-EVENT ACTIVITIES |  |
| A.3.a. | List all the activities/tasks that are needed to plan and conduct the proposed event. Scoring Criteria: Clarity, Reasonableness, Alignment with current functions being performed and proposed, and Alignment with the goals, objectives, and requirements of the RFP and MHSA Values. Each criteria is worth 5 points each, per event. Maximum points available is 300 points (15 events x 4 criteria x 5 points each) | 300 |
| A.3.b. | Enter the dates when each activity/task needs to be completed. Scoring Criteria: Reasonableness. Each criteria is worth 5 points each, per event. Score will be multiplied by 10 to award max points. Maximum points available is 150 (3 events x 5 points each x 10) | 150 |
| A.4. | EVENT ACTIVITIES |  |
| A.4.a. | List all the activities that will be provided at this event. Scoring Criteria: Clarity, Reasonableness, Alignment with current functions being performed and proposed, and Alignment with the goals, objectives, and requirements of the RFP and MHSA Values. Each criteria is worth 5 points each, per event. Maximum points available is 300 points (15 events x 4 criteria x 5 points each) | 300 |
| A.5. | POST-EVENT ACTIVITIES |  |
| A.5.a. | List all the activities/tasks that are planned as part of your post-event wrap up Scoring Criteria: Clarity, Reasonableness, Alignment with current functions being performed and proposed, and Alignment with the goals, objectives, and requirements of the RFP and MHSA Values. Each criteria is worth 5 points each, per event. Maximum points available is 300 points (15 events x 4 criteria x 5 points each) | 300 |
| A.5.b. | Enter the dates when each activity/task is planned to be completed. Scoring Criteria: Scoring Criteria: Reasonableness. Each criteria is worth 5 points each. Score will be multiplied by 4 to award max points. Maximum points available is 300 (15 events x 5 points each x 4) | 300 |
| A.6. | STATE LEVEL ENGAGEMENT PLAN |  |
| A.6. | Describe, in detail, the plan for successfully completing all the tasks identified in Section IV.A.3., State Level Advocacy Event. Scoring Criteria: Clarity, Reasonableness, Alignment with current functions being performed and proposed, Alignment with the goal and objectives of this RFP and MHSA values. Each criteria is worth 5 points each. Score will be multiplied by 50 to award max points. Maximum points available is 600 points (4 criteria x 5 points each x 30) | 1000 |  |
| A.6.a.1 | Will your organization be providing all of the services by yourself or with others (e.g. individuals, associations, LLEs, etc.)? Scoring Criteria: Clarity. Each criteria is worth 5 points each. Score will be multiplied by 2 to award max points. Maximum points available is 10 points (5 points each x 2) | 10 |  |
| A.6.a.1. (a) | If using other staff, identify the groups (if known; individuals do not need to be identified by name), describe their role, the number of staff they will be providing, the amount they will be paid. Scoring Criteria: Clarity, Reasonableness, Alignment with current functions being performed and proposed, Alignment with the goal and objectives of this RFP and MHSA values. Each criteria is worth 5 points each. Score will be multiplied by 20 to award max points. Maximum points available is 400 points (4 criteria x 5 points each x 20) | 400 |  |
| A.6.a.2. | What are the expected outcomes/measurements of success from your plan? Scoring Criteria: Clarity, Reasonableness, Alignment with current functions being performed and proposed, and Alignment with the goals, objectives, and requirements of the RFP and MHSA Values. Each criteria is worth 5 points each. Score will be multiplied by 5. Maximum points available is 100 points (4 criteria x 5 points each x 5) | 100 |  |
| A.6.a.3. | What is your plan to promote the State Level Engagement Events in order to meet participation and attendance goals? Scoring Criteria: Clarity, Reasonableness, Alignment with current functions being performed and proposed, and Alignment with the goals, objectives, and requirements of the RFP and MHSA Values. Each criteria is worth 5 points each. Score will be multiplied by 10. Maximum points available is 100 points (4 criteria x 5 points each x 10) | 200 |  |
| A.7. | STATE LEVEL ENGAGEMENT TASKS AND ACTIVITIES |  |  |
| A.7.a. | Event Name Scoring Criteria: Clarity. Each criteria is worth 5 points each, per event. Maximum points available is 15 points (3 events x 5 points each) | 15 |
| A.7.b. | Event Location Scoring Criteria: Clarity and Reasonableness. Each criteria is worth 5 points each, per event. Maximum points available is 30 points (3 events x 2 criteria x 5 points each) | 30 |
| A.7.c. | Event Date (Month and Year) Scoring Criteria: Clarity and Reasonableness. Each criteria is worth 5 points each, per event. Maximum points available is 30 points (3 events x 2 criteria x 5 points each) | 30 |
| A.7.d. | Event Description: Scoring Criteria: Clarity, Reasonableness, Alignment with current functions being performed and proposed, and Alignment with the goal, objectives, and requirements of this RFP and MHSA values. Each criteria is worth 5 points each, per event. Score will be multiplied by 5 to award max points. Maximum points available is 300 points (3 events x 4 criteria x 5 points each x 5) | 300 |
| A.8. | PRE-EVENT ACTIVITIES |  |
| A.8.a. | List all the activities/tasks that are needed to plan and conduct the proposed event. Scoring Criteria: 5 points will be given for each activity that is reasonable and in alignment with the goals, objectives, and requirements of the RFP and MHSA Values. A maximum of 100 points is available per event. Maximum points available is 300 (3 events x 100 points per event) | 300 |
| A.8.b. | Enter the dates when each activity/task needs to be completed. Scoring Criteria: Reasonableness. Each criteria is worth 5 points each. Score will be multiplied by 10 to award max points. Maximum points available is 150 (3 events x 5 points each x 10) | 150 |
| A.9. | EVENT ACTIVITIES |  |
| A.9.a. | List ALL the activities that will be provided at this event. Scoring Criteria: 5 points will be given for each activity that is reasonable and in alignment with the goals, objectives, and requirements of the RFP and MHSA Values. A maximum of 100 points is available per event. Maximum points available is 300 (3 events x 100 points per event) | 300 |
| A.9.b. | List the expected outcomes from these events. Scoring Criteria: Clarity, Reasonableness, Alignment with current functions being performed and proposed, and Alignment with the goal and objectives of this RFP and MHSA values. Each criteria is worth 5 points each, per event. Score will be multiplied by 5 to award max points. Maximum points available is 300 points (3 events x 4 criteria x 5 points each x 5) | 300 |
| A.10. | POST-EVENT ACTIVITIES |  |
| A.10.a. | List all the activities/tasks that are planned as part of your post-event wrap-up. Scoring Criteria: Clarity, Reasonableness, Alignment with current functions being performed and proposed, and Alignment with the goal and objectives of this RFP and MHSA values. Each criteria is worth 5 points each, per event. Score will be multiplied by 5 to award max points. Maximum points available is 300 points (3 events x 4 criteria x 5 points each x 5) | 300 |
| A.10.a.4. | Enter the dates when each activity/task is planned to be completed. Scoring Criteria: Reasonableness. Each criteria is worth 5 points each, per event. Score will be multiplied by 10 to award max points. Maximum points available is 150 points (3 events x 5 points each x 10) | 150 |
| TOTAL WORKPLAN POINTS |  | 9,460 |
| VI. REFERENCES |  |  |
| 1 | Reference 1 (Organization) (Max 500 points available. Calculated: Reference may score up to 25 points (5 categories at 5 points max for each). Reference score will be multiplied by 20 to award max points) | 500 |
| 2 | Reference 2 (Organization) (Max 500 points available. Calculated: Reference may score up to 25 points (5 categories at 5 points max for each). Reference score will be multiplied by 20 to award max points) | 500 |
| 3 | Reference 3 (Parents and Caregivers) (Max 500 points available. Calculated: Reference may score up to 25 points (5 categories at 5 points max for each). Reference score will be multiplied by 20 to award max points) | 500 |
| 4 | Reference 4 (Parents and Caregivers) (Max 500 points available. Calculated: Reference may score up to 25 points (5 categories at 5 points max for each). Reference score will be multiplied by 20 to award max points) | 500 |
| TOTAL REFERENCE POINTS |  | 2,000 |
| TOTAL EVALUATION POINTS |  | 12,060 |

NOTE – cost is not a factor in the evaluation of these proposals as the full amount of funds available will be awarded to the winning proposal.

### COMMERCIALLY USEFUL FUNCTION

##### Commercially Useful Function (Government code 14837)

A certified small business, micro-business Contractor, subcontractor or supplier, must meet commercially useful function requirements under Government Code Section 14837(d) (4). Selected firms must perform a "commercially useful function" relevant to this Contract.

The term "small business Contractor, subcontractor supplier" means any person or entity that satisfies the ownership (or management) and control requirements in accordance with Government Code Section 14847 (d) (4) and provides services or goods that contribute to the fulfillment of the Contract requirements by performing a commercially useful function. A person or an entity is deemed to perform a "commercially useful function' if that person or entity does all of the following:

- Is responsible for the execution of a distinct element of the work of the Contract;

- Carries out the obligation by actually performing, managing, or supervising the work involved;

- Performs work that is normal for its business services and functions; and

- Is not further subcontracting a portion of the work that is greater than that expected to be subcontracted by normal industry practices.

A Contractor, subcontractor, or supplier will not be considered to perform a commercially useful function if the Contractor’s, subcontractors, or supplier’s role is limited to that of an extra participant in order to obtain the appearance of disabled veteran business participation.

##### Bidder CUF Requirements

In responding to this solicitation, you are confirming that, under California Code of Regulations 1896.1, your business provides goods and or services that meet the definition of "commercially useful function." All Bidders are required to provide CUF documentation using the attached State's Bidder Declaration Form GSPD-05-105 (see ATTACHMENT 13). When completing the declaration, Bidders must identify all subcontractors proposed for participation in the Contract.

Any Bidder awarded a Contract is contractually obligated to use the subcontractor for the corresponding work defined unless the Commission agree to a substitution.  If, during the contract term, there is a need to replace a subcontractor, the Contractor must obtain approval from the Commission before such change is made.  Contractor will present to the Commission the reason for the change and the plan to ensure all contractual obligations are met and in accordance with the contract schedule.  No change will occur unless the Commission agree to the change.

### AWARD PROCEDURES

An award, if made, will be made to the highest scoring Proposal. A maximum of one (1) award may be made. If there are two or more Proposals with the same total score, the tie will be broken by a coin toss administered by the MHSOAC.

Prior to awarding the contract, a Notice of Intent to Award will be posted in the lobby of the MHSOAC office building located at 1325 J Street, 1st Floor, Sacramento, CA 95814 and on MHSOAC’s website (www.mhsoac.ca.gov) for a period of no less than five (5) working days.

## ADMINISTRATION

### COST OF DEVELOPING PROPOSAL

The Proposer is responsible for the cost of developing a Proposal, and this cost cannot be charged to the State.

### CONFIDENTIAL INFORMATION

The Commission will not accept any Proposals that are marked confidential in their entirety. Proposals marked confidential in their entirety will be deemed non-compliant and will not be scored.

### DARFUR CONTRACTING ACT OF 2008

Effective January 1, 2009, Public Contract Code sections 10475, et. seq.; Stats. 2008, Ch. 272, requires that all solicitations must address the requirements of the Darfur Contracting Act of 2008 (Act). (Public Contract Code sections 10475, et seq.; Stats. 2008, Ch. 272). The Act was passed by the California Legislature and signed into law by the Governor to preclude State agencies generally from contracting with “scrutinized” companies that do business in the African nation of Sudan (of which the Darfur region is a part), for the reasons described in Public Contract Code section 10475.

A scrutinized company is a company doing business in Sudan as defined in Public Contract Code section 10476. Scrutinized companies are ineligible to, and cannot, bid on or submit a Proposal for a contract with a State agency for goods or services. (Public Contract Code section 10477(a)).

Therefore, Public Contract Code section 10478 (a) requires a company that currently has (or within the previous three years has had) business activities or other operations outside of the United States to certify that it is not a “scrutinized” company when it submits a bid or Proposal to a State agency. (See option #1 on ATTACHMENT 15).

A scrutinized company may still, however, submit a bid or Proposal for a contract with a State agency for goods or services if the company first obtains permission from the Department of General Services according to the criteria set forth in Public Contract Code section 10477(b). (See option #2 on ATTACHMENT 15).

### RFP CANCELLATION AND AMENDMENTS

If it is in the State’s best interest, the MHSOAC reserves the right to do any of the following:

- Cancel this RFP;

- Amend this RFP as needed; or

- Reject any or all Proposals received in response to this RFP.

If the RFP is amended, the MHSOAC will send an addendum to all parties who requested the RFP and will post it on the MHSOAC’s website at www.mhsoac.ca.gov.

### ERRORS IN THE RFP

If a Proposer discovers any ambiguity, conflict, omission, or other error in the RFP, the Proposer shall immediately notify the MHSOAC of such error in writing and request modification or clarification of the document. Modifications or clarifications will be given by written notice to all parties who requested the RFP, without divulging the source of the request for clarification. If a Proposer fails to report a known or suspected problem with this RFP or fails to seek clarification and/or correction of the RFP, the Proposer submits a Proposal at his/her own risk.

### MODIFYING OR WITHDRAWAL OF PROPOSAL

A Proposer may, by letter to the Procurement Official, withdraw or modify a submitted Proposal before the deadline to submit Proposals. Proposals cannot be changed after the deadline to submit.

### IMMATERIAL DEFECT

The MHSOAC may waive any immaterial defect or deviation contained in a Proposer’s Proposal. The MHSOAC’s waiver shall in no way modify the Proposal or excuse the successful Proposer from full compliance.

### DISPOSITION OF PROPOSALS

Upon Proposal opening, all documents submitted in response to this RFP will become the property of the State of California.

### PROPOSER’S ADMONISHMENT

The RFP contains the instructions governing the requirements for a proposal to be submitted by interested Proposers, the format in which the technical information is to be submitted, the material to be included, the requirements which must be met to be eligible for consideration, and Proposer responsibilities. Proposers must take the responsibility to carefully read the entire RFP, ask appropriate questions in a timely manner, submit all required responses in a complete manner by the required date and time, make sure that all procedures and requirements of the RFP are followed and appropriately addressed, and carefully reread the entire RFP before submitting Proposal.

### REJECTION OF PROPOSAL

Deviation, whether or not intentional, may cause a Proposal to be non-compliant and not considered for award. The MHSOAC may reject any or all Proposals. Final Proposals not received by the date and time specified in the Key Action Dates or not sealed will be rejected.

### PROTEST PROCEDURES

This RFP is solicited in accordance with the Welfare and Institutions Code Section 5897(f) which exempts the MHSOAC from the Public Contract Code and the State Administrative Manual and the Department of General Services approval. Therefore, the provisions to protest the award of a contract under this RFP shall be as stated below:

There is no basis for protest if the MHSOAC rejects all proposals based on the best interest of the State or if the MHSOAC cancels the RFP. Only a Proposer who submitted a proposal to this RFP may protest the award of a contract under this RFP.

An Intent to Protest letter from a Proposer must be received at the following address no later than 5:00pm (Pacific Time) five (5) working days from the date of the posting of Notice of Intent to Award. The only acceptable delivery method for Intent to Protest letter is by a postal service (United States Post Office, Federal Express, etc.). The Intent to Protest letter cannot be hand delivered by the Proposer, faxed, or sent by electronic mail. Any Intent to Protest letter received without an original signature and/or by a delivery method other than a postal service will not be considered.

Include the following label information and deliver your Intent to Protest, in a sealed envelope:

Proposer Name

Street Address

City, State, Zip Code

INTENT TO PROTEST

RFP STAKEHOLDER Families and Caregivers_002

Families and Caregivers Stakeholder Contract

Michele Nottingham, Procurement Official

Mental Health Services Oversight and Accountability Commission

1325 J Street, Suite 1700, Sacramento, California 95814

Within five (5) working days from the date the MHSOAC receives the Intent to Protest letter, the protesting Proposer must file with the MHSOAC at the above address a Letter of Protest detailing the grounds for the protest. The only acceptable delivery method for the Letter of Protest is by a postal service (United States Post Office, Federal Express, etc.). The Letter of Protest cannot be hand delivered by the Proposer, faxed or sent by electronic mail. Any Letter of Protest received without an original signature and/or by a delivery method other than a postal service will not be considered.

The Letter of Protest must describe the factors that support the protesting Proposer’s claim that the protesting Proposer would have been awarded the contract had the MHSOAC correctly applied the prescribed evaluation rating standards in the RFP or if the MHSOAC had followed the evaluation and scoring methods in the RFP. The Letter of Protest must identify specific information in the Proposal that the Proposer believes was overlooked or misinterpreted. The Letter of Protest may not provide any additional information that was not included in the original Proposal.

If a Letter of Protest is filed, the contract shall not be awarded until the MHSOAC has reviewed and resolved the protest.

The Executive Director of the MHSOAC will render a decision in writing to the Protest and the decision will be considered final. The written decision will be sent to the protesting Proposer via a postal service.

### AGREEMENT EXECUTION AND PERFORMANCE

Performance shall start on the date set by MHSOAC and the Contractor after all approvals have been obtained and the agreement is fully executed. Should the Contractor fail to commence work at the agreed upon time, upon five (5) days written notice to the Contractor, the MHSOAC reserves the right to terminate the agreement. All performance under agreement shall be completed on or before the termination date of the agreement. The current term of the agreement is 39 months. The MHSOAC reserves the right to negotiate to finalize the contract. The Proposer who is awarded a contract will be required to sign a Standard Agreement and related documents.

### OTHER ATTACHMENTS

There are many attachments included in this RFP.  Many of them are described within the body of this RFP in their appropriate sections.  The remaining attachments will be explained here.

ATTACHMENT 16, Payee Data Record (Std 204), is required to receive a payment from the State of California and is completed in lieu of an IRS W-9 or W-7.  The information provided is used to populate the check (warrant) when payments are made.  In addition, the information is used for California state agencies to prepare Information Returns (Form1099).

ATTACHMENT 17, Sample Contract, provides an example of the resulting contract that will be awarded. Nothing is required to be done at this time in responding to the RFP:

EXHIBIT A – Scope of Work, includes the scope of work to be performed under this contact, contact information for the duration of the contract, contract term, deliverables, termination and amendment clauses. The Proposal will be included by reference in this Exhibit. This is only a sample of Exhibit A and does not represent the actual exhibit to be included in the contract.

EXHIBIT B – Budget Detail and Payment Provisions include the invoicing and payment process and budget contingency clause, which states that the contract is in force as long as the budget is appropriated to cover this contract.  Since the contract covers multiple fiscal years, funds need to be approved as part of the Governor’s annual budget at the start of each fiscal year. This is only a sample of Exhibit B and the actual exhibit may differ.

EXHIBIT C – General Terms and Conditions are the rules covering this contract and are standard language on all non-information technology contracts. This document is the actual document to be included in the contract.

EXHIBIT D – Special Terms and Conditions are the rules specific to the MHSOAC for this contract and covers areas not addressed in the General Terms and Conditions. This document is the actual document to be included in the contract.

## ATTACHMENT 1: Required Attachments Checklist

A responsive Proposal shall consist of all the required items identified below. Complete this checklist by marking the box with an “X” for each item you are submitting to the MHSOAC.

|  | Form | Form Name/Description |
| --- | --- | --- |
|  | Attachment 1 | Required Attachments Checklist |
|  | Attachment 2 | Proposal/Proposer Certification Sheet |
|  | Attachment 3 | Secretary of State Registration |
|  | Attachment 4 | Minimum Qualifications |
|  | Attachment 5 | Proposer Background |
|  | Attachment 6 | Local Community Engagement Plan |
|  | Attachment 7 | Local Community Engagement Tasks and Activities |
|  | Attachment 8 | State Level Engagement Plan |
|  | Attachment 9 | State Level Engagement Tasks and Activities |
|  | Attachment 10 | Cost Worksheet |
|  | Attachment 11 | References (Organization) |
|  | Attachment 12 | References (Parents and Caregivers) |
|  | Attachment 13 | Bidder Declaration (GSPD-05-105) |
|  | Attachment 14 | Contractor Certification Clauses (CCC-307) |
|  | Attachment 15 | Darfur Contracting Act Certification (if applicable) |
|  | Attachment 16 | Payee Data Record (STD 204) |

## ATTACHMENT 2: Proposal/Proposer Certification Sheet

This Proposal/Proposer Certification Sheet must be signed and return along with all the "required attachments" as an entire package with wet signatures by a representative authorized to bind the organization. Facsimiles and signature stamps will be deemed non-compliant.

Place all required attachments with this certification sheet.

The signature affixed hereon and dated certifies acceptance and compliance with all the requirements of this Proposal document.  Submission of any false information is grounds for your proposal to be rejected.  If there is any false information that comes to light after contract award, this is grounds for the contract to be terminated immediately.  In addition, your organization may be precluded from participating in future procurements.

| Company Name | Telephone Number |
| --- | --- |
| Address | Fax Number |
| Contact Name | Title |
| Authorized Signature | Date |

## ATTACHMENT 3: Secretary of State Registration

Proposer must provide evidence of registration with the Secretary of State to do business in California. If the Proposer is a partnership or corporation, the Proposer shall submit a copy of its current active status with the Secretary of State Business Certification program.

Go to https://businesssearch.sos.ca.gov/, Business Search.  Select your company’s entity type under Search Type and enter you company’s name under Search Criteria.  Select Search. On the search results page, select your company’s name under Entity Name.  Screen print the Business Search – Entity Detail page and attach to your proposal.  The Status on the page must equal Active.

## ATTACHMENT 4: Minimum Qualifications

| Qualification | Yes/No | Documentation Provided: |
| --- | --- | --- |
| - Be an established state-level organization which has been in operation for 2 years and has experience with programs and services related to the unique mental health issues of California’s Parents and Caregivers populations; | Yes No |  |
| - Have experience and capacity to partner with local community-based organizations working on mental health issues of Parents and Caregivers; | Yes No |  |
| - Be a non-profit organization, registered to do business in California; | Yes No |  |
| - Have more than 50% of staff or board members who are Parents and Caregivers. | Yes No |  |

## ATTACHMENT 5: Proposer Background

Provide responses to the following

| III.C.1. | Describe what your organization does to advocate for the mental health and wellness needs of children and youth and their Parents and Caregivers: |  |
| --- | --- | --- |
| III.C.2. | What counties, regions, or areas of the State do you serve? |  |
| III.C.3. | What counties do you have a branch/physical presence located? |  |
| III.C.3.a. |  | Provide Support: |
| III.C.4. | How do you determine where service gaps may exist for the Parents and Caregivers populations that you serve? |  |
| III.C.5. | What are the specific outcomes you are working toward? |  |
| III.C.6. | What do you measure to determine the success of your approach? |  |
| III.C.7. | How long has your organization been in existence? |  |
| III.C.7.a. |  | Provide Support: |
| III.C.8. | How many staff do you have? This does not include volunteers or contractors. |  |
| III.C.8.a. |  | Provide Support: |
| III.C.9. | How many staff are Parents and Caregivers? This does not include volunteers or contractors. |  |
| III.C.9.a. |  | Provide Support: |

## ATTACHMENT 6: LOCAL COMMUNITY ENGAGEMENT PLAN

Provide responses to the following

| V.A.1. | LOCAL COMMUNITY ENGAGEMENT PLAN |  |  |
| --- | --- | --- | --- |
| V.A.1. | Describe, in detail, the plan for successfully completing all the tasks identified in Section IV.A.2., Local Community Engagement: |  |  |
| V.A.1.a. | 1. | Will your organization be providing all of the services by yourself or with others (e.g. individuals, associations, LLEs, etc.?: |  |
| V.A.1.a. | 1. | (a) | If using other staff, identify the groups (if known; individuals do not need to be identified by name), describe their role, the number of staff they will be providing, the amount they will be paid: |
| V.A.1.a. | 2. | How does your plan target traditionally unserved, underserved, and hard to reach Parents and Caregivers populations?: |  |
|  | 2. | (a) | Identify the specific Parents and Caregivers population being targeted: |
|  | 3. | How does your plan address the local Parents and Caregivers needs?: |  |
|  | 3. | (a) | Identify the Parents and Caregivers needs that are addressed: |
|  | 4. | What are the expected outcomes/measurements of success from your plan? |  |
|  | 5. | What is you plan to promote the Local Engagement Events in order to maximize attendance in the local/county area?: |  |

## ATTACHMENT 7: LOCAL COMMUNITY ENGAGEMENT TASKS AND ACTIVITIES

For each Local Community Event, provide responses to the following

| V.A.2. | LOCAL COMMUNITY ENGAGEMENT TASKS AND ACTIVITIES |  |  |  |
| --- | --- | --- | --- | --- |
| V.A.2.a. | Event Name (Enter the unique name of the Event): |  |  |  |
| V.A.2.b. | Event Location (The location can be specific to an actual physical location (e.g. school name) or a geographic location (e.g. city or county.): |  |  |  |
| V.A.2.c. | Event Date (Month and Year): |  |  |  |
| V.A.2.d. | Event Description (Provide a narrative describing the proposed event): |  |  |  |
| V.A.2.e.1. | Identify who will be participate in conducting the Local Community Engagement, if more than the Proposer’s staff (e.g. individuals, groups, organizations, contracted LLE, etc.) and provide the following for each participant. Do not include Local Level Entities on this line (Add lines as needed) |  |  |  |
|  | (1) | (a) | Name (Organization or state “Individual”): |  |
|  |  | (b) | Location/Address: |  |
|  |  | (c) | Number of staff participating: |  |
|  |  | (d) | Role/Tasks assigned: |  |
|  |  | (e) | Proposed Payment: |  |
|  | (2) | (a) | Name (Organization or state “Individual”): |  |
|  |  | (b) | Location/Address: |  |
|  |  | (c) | Number of staff participating: |  |
|  |  | (d) | Role/Tasks assigned: |  |
|  |  | (e) | Proposed Payment: |  |
| V.A.2.e.2. | If contracting with a Local Level Entity, provide the following information: |  |  |  |
|  | (a) | Organization Name: |  |  |
|  | (b) | Organization Address (must be in the area where the local engagement event will be held): |  |  |
|  | (c) | Organization Contact (Name, Title, Email): |  |  |
|  | (d) | Documented Relationship. (e.g. MOU, Letter between the organizations verifying the commitment to use this organization, etc.). Documentation must be signed by both parties and cannot be signed by a fiscal agent of the Local Level Entity. |  |  |
|  | (e) | Number of Staff: |  |  |
|  | (f) | Role/Task assigned: |  |  |
| V.A.3. | PRE-EVENT ACTIVITIES |  |  |  |
| V.A.3.a. | List all the activities/tasks that are needed to plan and conduct the proposed event (Add additional lines to the template as, needed) |  |  | Date |
|  | (1) |  |  |  |
|  | (2) |  |  |  |
|  | (3) |  |  |  |
|  | (4) |  |  |  |
|  | (5) |  |  |  |
|  | (6) |  |  |  |
|  | (7) |  |  |  |
|  | (8) |  |  |  |
|  | (9) |  |  |  |
|  | (10) |  |  |  |
|  | (11) |  |  |  |
|  | (12) |  |  |  |
|  | (13) |  |  |  |
|  | (14) |  |  |  |
|  | (15) |  |  |  |
|  | (16) |  |  |  |
|  | (17) |  |  |  |
|  | (18) |  |  |  |
|  | (19) |  |  |  |
|  | (20) |  |  |  |
| V.A.4. | EVENT ACTIVITIES |  |  |  |
| V.A.4.a. | List ALL the activities that will be provided at this event (Provide a detailed list of the activities that will be available at the event. Add additional lines or pages to the template, if needed) |  |  |  |
|  | (1) |  |  |  |
|  | (2) |  |  |  |
|  | (3) |  |  |  |
|  | (4) |  |  |  |
|  | (5) |  |  |  |
|  | (6) |  |  |  |
|  | (7) |  |  |  |
|  | (8) |  |  |  |
|  | (9) |  |  |  |
|  | (10) |  |  |  |
|  | (11) |  |  |  |
|  | (12) |  |  |  |
|  | (13) |  |  |  |
|  | (14) |  |  |  |
|  | (15) |  |  |  |
|  | (16) |  |  |  |
|  | (17) |  |  |  |
|  | (18) |  |  |  |
|  | (19) |  |  |  |
|  | (20) |  |  |  |
| V.A.5. | POST EVENT ACTIVITIES |  |  |  |
| V.A.5.a. | List all the activities/tasks that are planned as part of your post-event wrap-up. (Add additional lines to the template as needed) |  |  | Date |
|  | Contract Year 1 |  |  | Date |
|  | (1) |  |  |  |
|  | (2) |  |  |  |
|  | (3) |  |  |  |
|  | (4) |  |  |  |
|  | (5) |  |  |  |
|  | (6) |  |  |  |
|  | (7) |  |  |  |
|  | (8) |  |  |  |
|  | (9) |  |  |  |
|  | (10) |  |  |  |
|  | (11) |  |  |  |
|  | (12) |  |  |  |
|  | (13) |  |  |  |
|  | (14) |  |  |  |
|  | (15) |  |  |  |
|  | (16) |  |  |  |
|  | (17) |  |  |  |
|  | (18) |  |  |  |
|  | (19) |  |  |  |
|  | (20) |  |  |  |
|  | Contract Year 2 (If Applicable) |  |  | Date |
|  | (1) |  |  |  |
|  | (2) |  |  |  |
|  | (3) |  |  |  |
|  | (4) |  |  |  |
|  | (5) |  |  |  |
|  | (6) |  |  |  |
|  | (7) |  |  |  |
|  | (8) |  |  |  |
|  | (9) |  |  |  |
|  | (10) |  |  |  |
|  | (11) |  |  |  |
|  | (12) |  |  |  |
|  | (13) |  |  |  |
|  | (14) |  |  |  |
|  | (15) |  |  |  |
|  | (16) |  |  |  |
|  | (17) |  |  |  |
|  | (18) |  |  |  |
|  | (19) |  |  |  |
|  | (20) |  |  |  |
|  | Contract Year 3 (If Applicable) |  |  | Date |
|  | (1) |  |  |  |
|  | (2) |  |  |  |
|  | (3) |  |  |  |
|  | (4) |  |  |  |
|  | (5) |  |  |  |
|  | (6) |  |  |  |
|  | (7) |  |  |  |
|  | (8) |  |  |  |
|  | (9) |  |  |  |
|  | (10) |  |  |  |
|  | (11) |  |  |  |
|  | (12) |  |  |  |
|  | (13) |  |  |  |
|  | (14) |  |  |  |
|  | (15) |  |  |  |
|  | (16) |  |  |  |
|  | (17) |  |  |  |
|  | (18) |  |  |  |
|  | (19) |  |  |  |
|  | (20) |  |  |  |

## ATTACHMENT 8: STATE LEVEL ENGAGEMENT PLAN

Provide responses to the following

| V.A.6. | STATE LEVEL ENGAGEMENT EVENT |  |  |
| --- | --- | --- | --- |
| V.A.6. | Describe, in detail, the plan for successfully completing all the tasks identified in Section IV.A.3., State Level Advocacy Event. |  |  |
| V.A.6.a. | 1. | Will your organization be providing all of the services by yourself or with others (e.g. individuals, associations, LLEs, etc.)?: |  |
| V.A.6.a. | 1. | (a) | If using other staff, identify the groups (if known; individuals do not need to be identified by name), describe their role, the number of staff they will be providing, the amount they will be paid: |
| V.A.6.a. | 2. | What are the expected outcomes/measurements of success from your plan?: |  |
| V.A.6.a. | 3. | What is your plan to promote the State Level Engagement Events in order to meet participation and attendance goals?: |  |

## ATTACHMENT 9: STATE LEVEL ENGAGEMENT TASKS AND ACTIVITIES

For each State Level Event, provide responses to the following

| V.A.7. | STATE LEVEL ENGAGEMENT TASKS AND ACTIVITIES |  |  |
| --- | --- | --- | --- |
| V.A.7.a. | Event Name (Enter the unique name of the Event): |  |  |
| V.A.7.b. | Event Location (The location can be specific to an actual physical location (e.g. school name) or a geographic location (e.g. city or county.): |  |  |
| V.A.7.c. | Event Date (Month and Year): |  |  |
| V.A.7.d. | Event Description (Provide a narrative describing the proposed event): |  |  |
| V.A.8. | PRE-EVENT ACTIVITIES |  |  |
| V.A.8.a. | List all the activities/tasks that are needed to plan and conduct the proposed event (Add additional lines to the template as, needed) |  | Date |
|  | (1) |  |  |
|  | (2) |  |  |
|  | (3) |  |  |
|  | (4) |  |  |
|  | (5) |  |  |
|  | (6) |  |  |
|  | (7) |  |  |
|  | (8) |  |  |
|  | (9) |  |  |
|  | (10) |  |  |
|  | (11) |  |  |
|  | (12) |  |  |
|  | (13) |  |  |
|  | (14) |  |  |
|  | (15) |  |  |
|  | (16) |  |  |
|  | (17) |  |  |
|  | (18) |  |  |
|  | (19) |  |  |
|  | (20) |  |  |
| V.A.9. | EVENT ACTIVITIES |  |  |
| V.A.9.a. | List ALL the activities that will be provided at this event (Provide a detailed list of the activities that will be available at the event. Add additional lines or pages to the template, if needed) |  |  |
|  | (1) |  |  |
|  | (2) |  |  |
|  | (3) |  |  |
|  | (4) |  |  |
|  | (5) |  |  |
|  | (6) |  |  |
|  | (7) |  |  |
|  | (8) |  |  |
|  | (9) |  |  |
|  | (10) |  |  |
|  | (11) |  |  |
|  | (12) |  |  |
|  | (13) |  |  |
|  | (14) |  |  |
|  | (15) |  |  |
|  | (16) |  |  |
|  | (17) |  |  |
|  | (18) |  |  |
|  | (19) |  |  |
|  | (20) |  |  |
| V.A.10. | POST EVENT ACTIVITIES |  |  |
| V.A.10.a. | List all the activities/tasks that are planned as part of your post-event wrap-up. (Add additional lines to the template as needed) |  | Date |
|  | Contract Year 1 |  | Date |
|  | (1) |  |  |
|  | (2) |  |  |
|  | (3) |  |  |
|  | (4) |  |  |
|  | (5) |  |  |
|  | (6) |  |  |
|  | (7) |  |  |
|  | (8) |  |  |
|  | (9) |  |  |
|  | (10) |  |  |
|  | (11) |  |  |
|  | (12) |  |  |
|  | (13) |  |  |
|  | (14) |  |  |
|  | (15) |  |  |
|  | (16) |  |  |
|  | (17) |  |  |
|  | (18) |  |  |
|  | (19) |  |  |
|  | (20) |  |  |
|  | Contract Year 2 (If Applicable) |  | Date |
|  | (1) |  |  |
|  | (2) |  |  |
|  | (3) |  |  |
|  | (4) |  |  |
|  | (5) |  |  |
|  | (6) |  |  |
|  | (7) |  |  |
|  | (8) |  |  |
|  | (9) |  |  |
|  | (10) |  |  |
|  | (11) |  |  |
|  | (12) |  |  |
|  | (13) |  |  |
|  | (14) |  |  |
|  | (15) |  |  |
|  | (16) |  |  |
|  | (17) |  |  |
|  | (18) |  |  |
|  | (19) |  |  |
|  | (20) |  |  |
|  | Contract Year 3 (If Applicable) |  | Date |
|  | (1) |  |  |
|  | (2) |  |  |
|  | (3) |  |  |
|  | (4) |  |  |
|  | (5) |  |  |
|  | (6) |  |  |
|  | (7) |  |  |
|  | (8) |  |  |
|  | (9) |  |  |
|  | (10) |  |  |
|  | (11) |  |  |
|  | (12) |  |  |
|  | (13) |  |  |
|  | (14) |  |  |
|  | (15) |  |  |
|  | (16) |  |  |
|  | (17) |  |  |
|  | (18) |  |  |
|  | (19) |  |  |
|  | (20) |  |  |

## ATTACHMENT 10: Cost Worksheet

(Do not change Document)

| No. | Requirement | First Year | Second Year | Third Year |
| --- | --- | --- | --- | --- |
| 1 | Event 1 Name: | $34,000 |  |  |
| 2 | Event 2 Name: | $34,000 |  |  |
| 3 | Event 3 Name: | $34,000 |  |  |
| 4 | Event 4 Name: | $34,000 |  |  |
| 5 | Event 5 Name: | $34,000 |  |  |
| 6 | Event 6 Name: |  | $34,000 |  |
| 7 | Event 7 Name: |  | $34,000 |  |
| 8 | Event 8 Name: |  | $34,000 |  |
| 9 | Event 9 Name: |  | $34,000 |  |
| 10 | Event 10 Name: |  | $34,000 |  |
| 11 | Event 11 Name: |  |  | $34,000 |
| 12 | Event 12 Name: |  |  | $34,000 |
| 13 | Event 13 Name: |  |  | $34,000 |
| 14 | Event 14 Name: |  |  | $34,000 |
| 15 | Event 15 Name: |  |  | $34,000 |
| 16 | Event 1: Additional Local Community Engagement | $30,000 | $13,000 | $13,000 |
| 17 | Event 2: Additional Local Community Engagement | $30,000 | $13,000 | $13,000 |
| 18 | Event 3: Additional Local Community Engagement | $30,000 | $13,000 | $13,000 |
| 19 | Event 4: Additional Local Community Engagement | $30,000 | $13,000 | $13,000 |
| 20 | Event 5: Additional Local Community Engagement | $30,000 | $13,000 | $13,000 |
| 21 | Event 6: Additional Local Community Engagement |  | $30,000 | $13,000 |
| 22 | Event 7: Additional Local Community Engagement |  | $30,000 | $13,000 |
| 23 | Event 8: Additional Local Community Engagement |  | $30,000 | $13,000 |
| 24 | Event 9: Additional Local Community Engagement |  | $30,000 | $13,000 |
| 25 | Event 10: Additional Local Community Engagement |  | $30,000 | $13,000 |
| 26 | Event 11: Additional Local Community Engagement |  |  | $30,000 |
| 27 | Event 12: Additional Local Community Engagement |  |  | $30,000 |
| 28 | Event 13: Additional Local Community Engagement |  |  | $30,000 |
| 29 | Event 14: Additional Local Community Engagement |  |  | $30,000 |
| 30 | Event 15: Additional Local Community Engagement |  |  | $30,000 |
| 31 | State Level Advocacy Event | $170,000 | $220,000 | $270,000 |
| 32 | State of the Community Report | $15,000 | $20,000 | $25,000 |
| 33 | Quarterly Report 1 | $3,000 | $3,000 | $3,000 |
| 34 | Quarterly Report 2 | $3,000 | $3,000 | $3,000 |
| 35 | Quarterly Report 3 | $3,000 | $3,000 | $3,000 |
| 36 | Quarterly Report 4 | $3,000 | $3,000 | $3,000 |
| 37 | Legislative Reports | $21,000 | $21,000 | $21,000 |
| 38 | Attend Collaboration Meetings | $12,000 | $12,000 | $12,000 |
|  | Total Cost | $ 550,000 | $ 670,000 | $ 790,000 |

## ATTACHMENT 11: References (Organization)

Reference for _____________________________

| Organization Name: |  |
| --- | --- |
| Time Period the Reference Covers (must have worked with the Proposer within the last 2 years of the release date of this RFP) |  |
| Service Provided: (Must be related to providing local advocacy for the identified population) |  |
| Reference Contact Name and Title: |  |
| Reference Contact Phone Number: |  |
| Reference Contact E Mail Address: |  |

Ratings:	Summarize contractor performance and circle in the column on the right the number which best corresponds to the performance rating for each question.  If the score is either 1 or 5, please provide an explanation.

Please follow the rating guidelines below for description of rating scale:

| Rating Guidelines and Description of Rating Scale: |  |
| --- | --- |
| Exceptional (5) | Performance/service provided was significantly above expectations |
| Very Good (4) | Performance/service was slightly above expectations |
| Satisfactory (3) | Performance met expectations |
| Marginal (2) | Performance/service was slightly below expectations |
| Unsatisfactory (1) | Performance/service provided was significantly below expectations |

| Category | Comments Provide a comment for a 1 or 5 rating | Rating (Circle One) |
| --- | --- | --- |
| 1. Demonstrated experience in advocacy, outreach, and training activities related to the mental health needs of Parents and Caregivers. |  | 1 2 3 4 5 |
| 2. Demonstrated capability to manage a project of similar duration and funding. |  | 1 2 3 4 5 |
| 3. Demonstrated experience in designing culturally competent approaches to engagement and outreach targeting Parents and Caregivers. |  | 1 2 3 4 5 |
| 4. Demonstrated experience with incorporating concepts of client and family resilience and recovery into programs, projects, training, and technical assistance. |  | 1 2 3 4 5 |
| - Have experience and capacity to coordinate a State Level Advocacy event with legislative visits. |  | 1 2 3 4 5 |

Rater’s Signature:								      Date:

## ATTACHMENT 12: References (Parents AND Caregivers)

Reference for _____________________________

| Individual/Reference Name: |  |
| --- | --- |
| Time Period the Reference Covers (must have worked with the Proposer within the last 2 years of the release date of this RFP) |  |
| Service Provided: (Must be for training and education, or outreach and engagement from the proposer related to mental health needs) |  |
| Reference Contact Phone Number: |  |
| Reference Contact E Mail Address: |  |

Ratings:	Summarize contractor performance and circle in the column on the right the number which best corresponds to the performance rating for each question.  If the score is either 1 or 5, please provide an explanation.

Please follow the rating guidelines below for description of rating scale:

| Rating Guidelines and Description of Rating Scale: |  |
| --- | --- |
| Exceptional (5) | Performance/service provided was significantly above expectations |
| Very Good (4) | Performance/service was slightly above expectations |
| Satisfactory (3) | Performance met expectations |
| Marginal (2) | Performance/service was slightly below expectations |
| Unsatisfactory (1) | Performance/service provided was significantly below expectations |

| Category | Comments Provide a comment for a 1 or 5 rating | Rating (Circle One) |
| --- | --- | --- |
| 1. Did the organization understand your issues/needs? |  | 1 2 3 4 5 |
| 2. Did the organization appear to have experience in advocacy, outreach, and/or training |  | 1 2 3 4 5 |
| 3. Rate the organization as to the quality of advocacy, outreach, and/or training activities that was provided. |  | 1 2 3 4 5 |
| 4. Did the organization successfully assist you? |  | 1 2 3 4 5 |
| 5. Rate the organization based on your overall experience. |  | 1 2 3 4 5 |

Rater’s Signature:								      Date:

## ATTACHMENT 13: Bidder Declaration (GSPD-05-105)

The Bidder Declaration form (GSPD-05-105) is a required submittal. It is available at the following website: http://www.documents.dgs.ca.gov/pd/delegations/GSPD105.pdf

## ATTACHMENT 14: Contract Certification Clauses (CCC-307)

CCC-307

CERTIFICATION

I, the official named below, CERTIFY UNDER PENALTY OF PERJURY that I am duly authorized to legally bind the prospective Contractor to the clause(s) listed below. This certification is made under the laws of the State of California.

| Contractor/Bidder Firm Name (Printed) |  | Federal ID Number |
| --- | --- | --- |
| By (Authorized Signature) |  |  |
| Printed Name and Title of Person Signing |  |  |
| Date Executed | Executed in the County of |  |

1. 	STATEMENT OF COMPLIANCE: Contractor has, unless exempted, complied with the nondiscrimination program requirements. (Gov. Code §12990 (a-f) and CCR, Title 2, Section 8103) (Not applicable to public entities.)

2. 	DRUG-FREE WORKPLACE REQUIREMENTS: Contractor will comply with the requirements of the Drug-Free Workplace Act of 1990 and will provide a drug-free workplace by taking the following actions:

a. 	Publish a statement notifying employees that unlawful manufacture, distribution, dispensation, possession or use of a controlled substance is prohibited and specifying actions to be taken against employees for violations.

b. 	Establish a Drug-Free Awareness Program to inform employees about:

1) The dangers of drug abuse in the workplace;

2) The person's or organization's policy of maintaining a drug-free workplace;

3) Any available counseling, rehabilitation and employee assistance programs; and,

4) Penalties that may be imposed upon employees for drug abuse violations.

c. 	Every employee who works on the proposed Agreement will:

1) Receive a copy of the company's drug-free workplace policy statement; and,

2) Agree to abide by the terms of the company's statement as a condition of employment on the Agreement.

Failure to comply with these requirements may result in suspension of payments under the Agreement or termination of the Agreement or both and Contractor may be ineligible for award of any future State agreements if the department determines that any of the following has occurred: the Contractor has made false certification, or violated the certification by failing to carry out the requirements as noted above. (Gov. Code §8350 et seq.)

3.	NATIONAL LABOR RELATIONS BOARD CERTIFICATION: Contractor certifies that no more than one (1) final unappealable finding of contempt of court by a Federal court has been issued against Contractor within the immediately preceding two-year period because of Contractor's failure to comply with an order of a Federal court, which orders Contractor to comply with an order of the National Labor Relations Board. (Pub. Contract Code §10296) (Not applicable to public entities.)

4. 	CONTRACTS FOR LEGAL SERVICES $50,000 OR MORE- PRO BONO REQUIREMENT: Contractor hereby certifies that contractor will comply with the requirements of Section 6072 of the Business and Professions Code, effective January 1, 2003.

Contractor agrees to make a good faith effort to provide a minimum number of hours of pro bono legal services during each year of the contract equal to the lessor of 30 multiplied by the number of full time attorneys in the firm’s offices in the State, with the number of hours prorated on an actual day basis for any contract period of less than a full year or 10% of its contract with the State.

Failure to make a good faith effort may be cause for non-renewal of a state contract for legal services, and may be taken into account when determining the award of future contracts with the State for legal services.

5. 	EXPATRIATE CORPORATIONS:  Contractor hereby declares that it is not an expatriate corporation or subsidiary of an expatriate corporation within the meaning of Public Contract Code Section 10286 and 10286.1, and is eligible to contract with the State of California.

6. 	SWEATFREE CODE OF CONDUCT:

a. 	All Contractors contracting for the procurement or laundering of apparel, garments or corresponding accessories, or the procurement of equipment, materials, or supplies, other than procurement related to a public works contract, declare under penalty of perjury that no apparel, garments or corresponding accessories, equipment, materials, or supplies furnished to the state pursuant to the contract have been laundered or produced in whole or in part by sweatshop labor, forced labor, convict labor, indentured labor under penal sanction, abusive forms of child labor or exploitation of children in sweatshop labor, or with the benefit of sweatshop labor, forced labor, convict labor, indentured labor under penal sanction, abusive forms of child labor or exploitation of children in sweatshop labor.  The contractor further declares under penalty of perjury that they adhere to the Sweatfree Code of Conduct as set forth on the California Department of Industrial Relations website located at www.dir.ca.gov, and Public Contract Code Section 6108.

b. 	The contractor agrees to cooperate fully in providing reasonable access to the contractor’s records, documents, agents or employees, or premises if reasonably required by authorized officials of the contracting agency, the Department of Industrial Relations, or the Department of Justice to determine the contractor’s compliance with the requirements under paragraph (a).

7. 	DOMESTIC PARTNERS:  For contracts over $100,000 executed or amended after January 1, 2007, the contractor certifies that contractor is in compliance with Public Contract Code section 10295.3.

DOING BUSINESS WITH THE STATE OF CALIFORNIA

The following laws apply to persons or entities doing business with the State of California.

1. 	CONFLICT OF INTEREST: Contractor needs to be aware of the following provisions regarding current or former state employees.  If Contractor has any questions on the status of any person rendering services or involved with the Agreement, the awarding agency must be contacted immediately for clarification.

Current State Employees (Pub. Contract Code §10410):

1)	No officer or employee shall engage in any employment, activity or enterprise from which the officer or employee receives compensation or has a financial interest and which is sponsored or funded by any state agency, unless the employment, activity or enterprise is required as a condition of regular state employment.

2)	No officer or employee shall contract on his or her own behalf as an independent contractor with any state agency to provide goods or services.

Former State Employees (Pub. Contract Code §10411):

1) 	For the two-year period from the date he or she left state employment, no former state officer or employee may enter into a contract in which he or she engaged in any of the negotiations, transactions, planning, arrangements or any part of the decision-making process relevant to the contract while employed in any capacity by any state agency.

2)	For the twelve-month period from the date he or she left state employment, no former state officer or employee may enter into a contract with any state agency if he or she was employed by that state agency in a policy-making position in the same general subject area as the proposed contract within the 12-month period prior to his or her leaving state service.

If Contractor violates any provisions of above paragraphs, such action by Contractor shall render this Agreement void. (Pub. Contract Code §10420)

Members of boards and commissions are exempt from this section if they do not receive payment other than payment of each meeting of the board or commission, payment for preparatory time and payment for per diem. (Pub. Contract Code §10430 (e))

2.	LABOR CODE/WORKERS' COMPENSATION: Contractor needs to be aware of the provisions which require every employer to be insured against liability for Worker's Compensation or to undertake self-insurance in accordance with the provisions, and Contractor affirms to comply with such provisions before commencing the performance of the work of this Agreement. (Labor Code Section 3700)

3. 	AMERICANS WITH DISABILITIES ACT: Contractor assures the State that it complies with the Americans with Disabilities Act (ADA) of 1990, which prohibits discrimination on the basis of disability, as well as all applicable regulations and guidelines issued pursuant to the ADA. (42 U.S.C. 12101 et seq.)

4. 	CONTRACTOR NAME CHANGE: An amendment is required to change the Contractor's name as listed on this Agreement. Upon receipt of legal documentation of the name change the State will process the amendment.  Payment of invoices presented with a new name cannot be paid prior to approval of said amendment.

5. 	CORPORATE QUALIFICATIONS TO DO BUSINESS IN CALIFORNIA:

a. 	When agreements are to be performed in the state by corporations, the contracting agencies will be verifying that the contractor is currently qualified to do business in California in order to ensure that all obligations due to the state are fulfilled.

b. 	"Doing business" is defined in R&TC Section 23101 as actively engaging in any transaction for the purpose of financial or pecuniary gain or profit.  Although there are some statutory exceptions to taxation, rarely will a corporate contractor performing within the state not be subject to the franchise tax.

c. 	Both domestic and foreign corporations (those incorporated outside of California) must be in good standing in order to be qualified to do business in California.  Agencies will determine whether a corporation is in good standing by calling the Office of the Secretary of State.

6. 	RESOLUTION: A county, city, district, or other local public body must provide the State with a copy of a resolution, order, motion, or ordinance of the local governing body which by law has authority to enter into an agreement, authorizing execution of the agreement.

7. 	AIR OR WATER POLLUTION VIOLATION: Under the State laws, the Contractor shall not be: (1) in violation of any order or resolution not subject to review promulgated by the State Air Resources Board or an air pollution control district; (2) subject to cease and desist order not subject to review issued pursuant to Section 13301 of the Water Code for violation of waste discharge requirements or discharge prohibitions; or (3) finally determined to be in violation of provisions of federal law relating to air or water pollution.

8. 	PAYEE DATA RECORD FORM STD. 204: This form must be completed by all contractors that are not another state agency or other governmental entity.

http://www.documents.dgs.ca.gov/dgs/fmc/pdf/std204.pdf

## ATTACHMENT 15: Darfur Contracting Act Certification (if applicable)

Public Contract Code Sections 10475 -10481 applies to any company that currently or within the previous three years has had business activities or other operations outside of the United States. For such a company to bid on or submit a Proposal for a State of California contract, the company must certify that it is either a) not a scrutinized company; or b) a scrutinized company that has been granted permission by the Department of General Services to submit a Proposal.

If your company has not, within the previous three years, had any business activities or other operations outside of the United States, you do not need to complete this form.

OPTION #1 - CERTIFICATION

If your company, within the previous three years, has had business activities or other operations outside of the United States, in order to be eligible to submit a bid or Proposal, please insert your company name and Federal ID Number and complete the certification below.

I, the official named below, CERTIFY UNDER PENALTY OF PERJURY that a) the prospective proposer/bidder named below is not a scrutinized company per Public Contract Code 10476; and b) I am duly authorized to legally bind the prospective proposer/bidder named below. This certification is made under the laws of the State of California.

| Company/Vendor Name (Printed) |  | Federal ID Number |
| --- | --- | --- |
| By (Authorized Signature) |  |  |
| Printed Name and Title of Person Signing |  |  |
| Date Executed | Executed in the County and State of |  |

OPTION #2 – WRITTEN PERMISSION FROM DGS

Pursuant to Public Contract Code section 10477(b), the Director of the Department of General Services may permit a scrutinized company, on a case-by-case basis, to bid on or submit a Proposal for a contract with a state agency for goods or services, if it is in the best interests of the state.  If you are a scrutinized company that has obtained written permission from the DGS to submit a bid or Proposal, complete the information below.

We are a scrutinized company as defined in Public Contract Code section 10476, but we have received written permission from the Department of General Services to submit a bid or Proposal pursuant to Public Contract Code section 10477(b).  A copy of the written permission from DGS is included with our bid or Proposal.

| Company/Vendor Name (Printed) | Federal ID Number |
| --- | --- |
| Initials of Submitter |  |
| Printed Name and Title of Person Initialing |  |

## ATTACHMENT 16: Payee Data Record (STD 204)

The Bidder must complete and submit Payee Data Record (STD. 204) with its Final Bid.

This form is available at: http://www.documents.dgs.ca.gov/dgs/fmc/pdf/std204.pdf

## ATTACHMENT 17: Sample Contract

### EXHIBIT A – Scope of Work

- GENERAL

The scope of work for this contract is contained in the proposal submitted by Contractor in response to RFP Stakeholder Parents and Caregivers_002 and is incorporated by reference and made part of this contract as if attached hereto.

- CONTACTS

| State Agency: MHSOAC | Contractor: |
| --- | --- |
| Name: | Name: |
| Phone: | Phone: |
| E-Mail: | E-Mail: |

Direct all administrative inquiries to:

| State Agency: MHSOAC | Contractor: |
| --- | --- |
| Section/Unit: | Section/Unit: |
| Attention: | Attention: |
| Address: 1325 J Street, Suite 1700, Sacramento, CA 95814 | Address: |
| Phone: | Phone: |
| Fax: (916) 445-4927 | Fax: |
| E-Mail: | E-Mail: |

- CONTRACT TERM

The term of this contract is for 39 months, with all funds allocated based on tasks/deliverables.

Contract funding is based on the Contractor’s compliance with the RFP requirements as submitted through the Contractor’s proposal, which is incorporated by reference and made part of this contract as if attached hereto.

The MHSOAC may withhold funds from the Contractor if the Contractor fails to meet the reporting requirements, falls behind schedule, or modifies the scope of the work performed.

- DELIVERABLES

Deliverables shall be submitted in an electronic format, to be agreed upon prior to start of work, which are easily posted on the MHSOAC website, pursuant to Government Code §11135, and in compliance with accessibility requirements of §508 of the Rehabilitation Act of 1973, as amended and implemented through regulations.

All deliverables shall be developed in consultation with the MHSOAC Project Representative.

The Contractor may seek advice from subject matter experts, form an advisory group, seek technical assistance from the Commission and/or pursue other strategies to support the development and completion of all deliverables. Subject to resources, the MHSOAC shall strive to provide consultation and technical assistance to support the implementation of this agreement.

The Contractor may submit deliverables prior to due dates. If Contractor experiences reasonable delays with regard to a deliverable, Contractor shall notify the MHSOAC Project Representative, prior to the deliverable due date for which a delay is anticipated. In no instance shall a delay exceed 30 calendar days. For any deliverable in which the delay is anticipated to exceed 30 calendar days, the MHSOAC Deputy Director may grant the Contractor additional time to complete the deliverable. Such additional time must be confirmed by the MHSOAC in writing.

- TERMINATION

Either party may terminate this agreement by giving 30-days written notice to the other party. The notice of termination shall specify the effective date of termination. In the event of such termination, MHSOAC agrees to pay the pro rata share of the contract based upon the actual services provided.

- AMENDMENTS

This agreement may be amended as necessary for project completion.

### Exhibit B - Budget Detail and Payment Provisions

- Payment Milestones

Contractor will be paid as follows:

  - Administration Costs

    - 15% of total annual payments will be released at the start of each contract year.  Upon contract execution, the Contractor may submit the first Payment Milestone Status Report for the Administration costs only.  At the start of each contract year the following funds will be released to the Contractor:

      - First year: $60,000 (15% x $400,000)

      - Second year: $68,250 (15% x $455,000)

      - Third year: $76,500 (15% x $510,000)

        - The 15% administration cost for the LLE payments will be released each year as part of the total LLE payment, since it is a pass-through to the LLE, and not retained by the Contractor.

  - Local Community Engagement

    - For each Local Community Engagement Event $28,900 ($34,000 – 15% administration cost already released) will be released to the Contractor after the following conditions are met:

      - Confirmation/proof that an event is scheduled, and

      - Confirmation/proof that the Contractor is scheduled to meet or has met with Local Level Leaders in support of the Local Community Engagement Event.

  - Additional Local Community Engagement

    - LLE

      - For each LLE, $30,000 will be released to the Contractor in the first year of the contract between the Contractor and the LLE, after the following is submitted and accepted by the MHSOAC:

        - Copy of the contract between the Contractor and the LLE, which includes the responsibilities identified in the RFP for the LLE to perform.

        - Contract must state that the first-year amount is $30,000, and that subsequent years, if applicable, are valued at $13,000 each year.

      - Subsequent payments of $13,000, if applicable, will be released to the Contractor at the start of the next contract year with the LLE.

      - These payments will be immediately transferred from the Contractor to the LLE.

    - Non-LLE

      - If an LLE will not be used, payment will be made to the Contractor in accordance with Section 1.B. Local Community Engagement, in the amount of $30,000 for each event.

      - Subsequent payments of $13,000, if applicable, will be released to the Contractor at the start of the next contract year.

  - State Level Advocacy Event

    - For each State Level Advocacy Event, payment will be released to the Contractor after the following condition is met: receipt of a copy of the executed agreement with the event facility showing the event location and date of the event.

      - Year 1, $144,500 ($170,000 – 15% admin costs already released)

      - Year 2, $187,000 ($220,000 – 15% admin costs already released)

      - Year 3, $229,500 ($270,000 – 15% admin costs already released)

  - State of the Community Report

    - Upon receipt and acceptance of the State of the Community Report, payment will be released to the Contractor as follows:

      - Year 1, $12,750 ($15,000 – 15% admin costs already released)

      - Year 2, $17,000 ($20,000 – 15% admin costs already released)

      - Year 3, $21,250 ($25,000 – 15% admin costs already released)

  - Quarterly Reports

    - Upon receipt and acceptance of each Quarterly Report, payment will be released to the Contractor as follows:

      - Year 1, $2,550 ($3,000 – 15% admin costs already released)

      - Year 2, $2,550 ($3,000 – 15% admin costs already released)

      - Year 3, $2,550 ($3,000 – 15% admin costs already released)

  - Legislative Reports

    - Upon receipt and acceptance of each Legislative Tracking Summary, which is included in each Quarterly Report, payment will be released to the Contractor as follows:

      - Year 1, $4,462.50 ($5,250 – 15% admin costs already released)

      - Year 2, $4,462.50 ($5,250 – 15% admin costs already released)

      - Year 3, $4,462.50 ($5,250 – 15% admin costs already released)

  - Attendance at Collaboration Meetings

    - Upon confirmation of attending or after attending each collaboration meeting, payment will be released to the Contractor as follows:

      - $2,550 ($3,000 – 15% admin costs already released)

    - In the event that there are less than 4 collaboration meetings in a year, or Contractor receives an exemption from attending, payment will be released to the Contractor for any outstanding meetings in the amount of $2,550 ($3,000 – 15% admin costs already released) per meeting.  Payment may be requested in the last Payment Milestone Status Report for each contract year.

- Invoicing and Payment

- For services satisfactorily rendered (i.e., upon receipt and approval of agreed upon deliverables), and upon receipt and approval of the invoices, the MHSOAC agrees to compensate the Contractor in accordance with the rates specified in this contract.

- Invoices shall include the Contract Number and shall be submitted in triplicate not more frequently than monthly in arrears to:

MHSOAC
Attention: Accounting Office
1325 J Street, Suite 1700
Sacramento, CA, 95814

- Budget Contingency Clause

  - It is mutually agreed that if the Budget Act of the current year and/or any subsequent years covered under this Contract does not appropriate sufficient funds for the program, this Contract shall no longer be in full force and effect.  In this event, the State shall have no liability to pay any funds whatsoever to Contractor or to furnish any other considerations under this Contract and Contractor shall not be obligated to perform any provisions of this Contract.

  - If funding for any fiscal year is reduced or deleted by the Budget Act for purposes of this program, the State shall have the option to either cancel this Contract with no liability occurring to the State, or offer an agreement amendment to Contractor to reflect the reduced amount.

  - If this Contract overlaps Federal and State fiscal years, should funds not be appropriated by Congress and approved by the Legislature for the fiscal year(s) following that during which this Contract was executed, the State may exercise its option to cancel this Contract.

  - In addition, this Contract is subject to any additional restrictions, limitations, or conditions enacted by Congress or the Legislature which may affect the provisions or terms of funding of this contract in any manner.

- Cost

The total amount of this Agreement shall not exceed:  $2,010,000

- Prompt Payment Clause

Payment will be made in accordance with, and within the time specified in, Government Code Chapter 4.5, commencing with Section 927. Payment for deliverables is meant to be inclusive of all of the preparatory work, planning, and material cost involved in the completion of the intent of the deliverable not just the report itself.

### EXHIBIT C – GENERAL TERMS AND CONDITIONS (GTC 610)

- APPROVAL: This Agreement is of no force or effect until signed by both parties and approved by the Department of General Services, if required. Contractor may not commence performance until such approval has been obtained.

- AMENDMENT: No amendment or variation of the terms of this Agreement shall be valid unless made in writing, signed by the parties and approved as required. No oral understanding or Agreement not incorporated in the Agreement is binding on any of the parties.

- ASSIGNMENT: This Agreement is not assignable by the Contractor, either in whole or in part, without the consent of the State in the form of a formal written amendment.

- AUDIT: Contractor agrees that the awarding department, the Department of General Services, the Bureau of State Audits, or their designated representative shall have the right to review and to copy any records and supporting documentation pertaining to the performance of this Agreement. Contractor agrees to maintain such records for possible audit for a minimum of three (3) years after final payment, unless a longer period of records retention is stipulated. Contractor agrees to allow the auditor(s) access to such records during normal business hours and to allow interviews of any employees who might reasonably have information related to such records. Further, Contractor agrees to include a similar right of the State to audit records and interview staff in any subcontract related to performance of this Agreement. (Gov. Code §8546.7, Pub. Contract Code §10115 et seq., CCR Title 2, Section 1896).

- INDEMNIFICATION: Contractor agrees to indemnify, defend and save harmless the State, its officers, agents and employees from any and all claims and losses accruing or resulting to any and all contractors, subcontractors, suppliers, laborers, and any other person, firm or corporation furnishing or supplying work services, materials, or supplies in connection with the performance of this Agreement, and from any and all claims and losses accruing or resulting to any person, firm or corporation who may be injured or damaged by Contractor in the performance of this Agreement.

- DISPUTES: Contractor shall continue with the responsibilities under this Agreement during any dispute.

- TERMINATION FOR CAUSE: The State may terminate this Agreement and be relieved of any payments should the Contractor fail to perform the requirements of this Agreement at the time and in the manner herein provided. In the event of such termination the State may proceed with the work in any manner deemed proper by the State. All costs to the State shall be deducted from any sum due the Contractor under this Agreement and the balance, if any, shall be paid to the Contractor upon demand.

- INDEPENDENT CONTRACTOR: Contractor, and the agents and employees of Contractor, in the performance of this Agreement, shall act in an independent capacity and not as officers or employees or agents of the State.

- RECYCLING CERTIFICATION: The Contractor shall certify in writing under penalty of perjury, the minimum, if not exact, percentage of post-consumer material as defined in the Public Contract Code Section 12200, in products, materials, goods, or supplies offered or sold to the State regardless of whether the product meets the requirements of Public Contract Code Section 12209.  With respect to printer or duplication cartridges that comply with the requirements of Section 12156(e), the certification required by this subdivision shall specify that the cartridges so comply (Pub. Contract Code §12205).

- NON-DISCRIMINATION CLAUSE: During the performance of this Agreement, Contractor and its subcontractors shall not deny the contract’s benefits to any person on the basis of race, religious creed, color, national origin, ancestry, physical disability, mental disability, medical condition, genetic information, marital status, sex, gender, gender identity, gender expression, age, sexual orientation, or military and veteran status, nor shall they discriminate unlawfully against any employee or applicant for employment because of race, religious creed, color, national origin, ancestry, physical disability, mental disability, medical condition, genetic information, marital status, sex, gender, gender identity, gender expression, age, sexual orientation, or military and veteran status.  Contractor shall insure that the evaluation and treatment of employees and applicants for employment are free of such discrimination.  Contractor and subcontractors shall comply with the provisions of the Fair Employment and Housing Act (Gov. Code §12900 et seq.), the regulations promulgated thereunder (Cal. Code Regs., tit. 2, §11000 et seq.), the provisions of Article 9.5, Chapter 1, Part 1, Division 3, Title 2 of the Government Code (Gov. Code §§11135-11139.5), and the regulations or standards adopted by the awarding state agency to implement such article.  Contractor shall permit access by representatives of the Department of Fair Employment and Housing and the awarding state agency upon reasonable notice at any time during the normal business hours, but in no case less than 24 hours’ notice, to such of its books, records, accounts, and all other sources of information and its facilities as said Department or Agency shall require to ascertain compliance with this clause.   Contractor and its subcontractors shall give written notice of their obligations under this clause to labor organizations with which they have a collective bargaining or other agreement.  (See Cal. Code Regs., tit. 2, §11105.)

Contractor shall include the nondiscrimination and compliance provisions of this clause in all subcontracts to perform work under the Agreement.

- CERTIFICATION CLAUSES: The CONTRACTOR CERTIFICATION CLAUSES contained in the document CCC 307 are hereby incorporated by reference and made a part of this Agreement by this reference as if attached hereto.

- TIMELINESS: Time is of the essence in this Agreement.

- COMPENSATION: The consideration to be paid Contractor, as provided herein, shall be in compensation for all of Contractor's expenses incurred in the performance hereof, including travel, per diem, and taxes, unless otherwise expressly so provided.

- GOVERNING LAW: This contract is governed by and shall be interpreted in accordance with the laws of the State of California.

- ANTITRUST CLAIMS: The Contractor by signing this agreement hereby certifies that if these services or goods are obtained by means of a competitive bid, the Contractor shall comply with the requirements of the Government Codes Sections set out below.

  - The Government Code Chapter on Antitrust claims contains the following definitions:

    - "Public purchase" means a purchase by means of competitive bids of goods, services, or materials by the State or any of its political subdivisions or public agencies on whose behalf the Attorney General may bring an action pursuant to subdivision (c) of Section 16750 of the Business and Professions Code.

    - "Public purchasing body" means the State or the subdivision or agency making a public purchase. Government Code Section 4550.

  - In submitting a bid to a public purchasing body, the bidder offers and agrees that if the bid is accepted, it will assign to the purchasing body all rights, title, and interest in and to all causes of action it may have under Section 4 of the Clayton Act (15 U.S.C. Sec. 15) or under the Cartwright Act (Chapter 2 (commencing with Section 16700) of Part 2 of Division 7 of the Business and Professions Code), arising from purchases of goods, materials, or services by the bidder for sale to the purchasing body pursuant to the bid. Such assignment shall be made and become effective at the time the purchasing body tenders final payment to the bidder. Government Code Section 4552.

  - If an awarding body or public purchasing body receives, either through judgment or settlement, a monetary recovery for a cause of action assigned under this chapter, the assignor shall be entitled to receive reimbursement for actual legal costs incurred and may, upon demand, recover from the public body any portion of the recovery, including treble damages, attributable to overcharges that were paid by the assignor but were not paid by the public body as part of the bid price, less the expenses incurred in obtaining that portion of the recovery. Government Code Section 4553.

  - Upon demand in writing by the assignor, the assignee shall, within one year from such demand, reassign the cause of action assigned under this part if the assignor has been or may have been injured by the violation of law for which the cause of action arose and (a) the assignee has not been injured thereby, or (b) the assignee declines to file a court action for the cause of action. See Government Code Section 4554.

- CHILD SUPPORT COMPLIANCE ACT:  For any Agreement in excess of $100,000, the contractor acknowledges in accordance with Public Contract Code 7110, that:

  - The contractor recognizes the importance of child and family support obligations and shall fully comply with all applicable state and federal laws relating to child and family support enforcement, including, but not limited to, disclosure of information and compliance with earnings assignment orders, as provided in Chapter 8 (commencing with section 5200) of Part 5 of Division 9 of the Family Code; and

  - The contractor, to the best of its knowledge is fully complying with the earnings assignment orders of all employees and is providing the names of all new employees to the New Hire Registry maintained by the California Employment Development Department.

- UNENFORCEABLE PROVISION: In the event that any provision of this Agreement is unenforceable or held to be unenforceable, then the parties agree that all other provisions of this Agreement have force and effect and shall not be affected thereby.

- PRIORITY HIRING CONSIDERATIONS:  If this Contract includes services in excess of $200,000, the Contractor shall give priority consideration in filling vacancies in positions funded by the Contract to qualified recipients of aid under Welfare and Institutions Code Section 11200 in accordance with Pub. Contract Code §10353.

- SMALL BUSINESS PARTICIPATION AND DVBE PARTICIPATION REPORTING REQUIREMENTS:

  - If for this Contract Contractor made a commitment to achieve small business participation, then Contractor must within 60 days of receiving final payment under this Contract (or within such other time period as may be specified elsewhere in this Contract) report to the awarding department the actual percentage of small business participation that was achieved.  (Govt. Code § 14841.)

  - If for this Contract Contractor made a commitment to achieve disabled veteran business enterprise (DVBE) participation, then Contractor must within 60 days of receiving final payment under this Contract (or within such other time period as may be specified elsewhere in this Contract) certify in a report to the awarding department: (1) the total amount the prime Contractor received under the Contract; (2) the name and address of the DVBE(s) that participated in the performance of the Contract; (3) the amount each DVBE received from the prime Contractor; (4) that all payments under the Contract have been made to the DVBE; and (5) the actual percentage of DVBE participation that was achieved.  A person or entity that knowingly provides false information shall be subject to a civil penalty for each violation.  (Mil. & Vets. Code § 999.5(d); Govt. Code § 14841.)

- LOSS LEADER: If this contract involves the furnishing of equipment, materials, or supplies then the following statement is incorporated: It is unlawful for any person engaged in business within this state to sell or use any article or product as a “loss leader” as defined in Section 17030 of the Business and Professions Code.  (PCC 10344(e).)

### EXHIBIT D – SPECIAL TERMS AND CONDITIONS (SAC 1216)

- SUBCONTRACTS: Except for subcontracts identified in the Proposal in accordance with the Request for Proposal, Contractor shall submit any subcontracts which are proposed to be entered into in connection with this Contract to the State Agency (State) for its prior written approval before entering into the same.  No work shall be subcontracted without the prior written approval of the State.  Upon the termination of any subcontract, State shall be notified immediately.  Any subcontract shall include all the terms and conditions of this Contract and its attachments.

- PUBLICATIONS AND REPORTS:

- The State reserves the right to use and reproduce all publications, reports, and data produced and delivered pursuant to this Contract.  State further reserves the right to authorize others to use or reproduce such materials, provided the author of the report is acknowledged in any such use or reproduction.

- If the publication and/or report are prepared by non-employees of the State, and the total cost for such preparation exceeds $5,000, the publication and/or report shall contain the numbers and dollar amounts of all contracts and subcontracts relating to the preparation of the publication and report in a separate section of the report (Government Code Section 7550).

- PROGRESS REPORTS: Unless otherwise specified in Exhibit A, if progress reports are required by the Contract, Contractor shall provide a progress report in writing, or orally if approved by the State Contract Manager, at least once a month to the State Contract Manager.  This progress report shall include, but not limited to, a statement that the Contractor is or is not on schedule, any pertinent reports, or interim findings. Contractor shall cooperate with and shall be available to meet with the State to discuss any difficulties, or special problems, so that solutions or remedies can be developed as soon as possible.

- PRESENTATION: Upon request, Contractor shall meet with the State to present any findings, conclusions, and recommendations required by the Contract for approval.  If set forth in the Contract, Contractor shall submit a comprehensive final report for approval.  Both the final meeting and the final report shall be completed on or before the date indicated in the Contract.

- MENTAL HEALTH SERVICES OVERSIGHT AND ACCOUNTABILITY COMMISSION STAFF: Mental Health Services Oversight and Accountability Commission staff shall be permitted to work side by side with Contractor’s staff to the extent and under conditions as directed by the State Contract Manager.  In this connection, Mental Health Services Oversight and Accountability Commission staff shall be given access to all data, working papers, etc., which Contractor seeks to utilize.

- CONFIDENTIALITY OF DATA AND DOCUMENTS:

- Contractor shall not disclose data or documents or disseminate the contents of the final or any preliminary report without written permission of the State Contract Manager.  However, all public entities shall comply with California Public Records Act (Government Code Sections 6250 et seq.) and the Freedom of Information Act (Title 5 of the United States Code Section 552), as applicable.

- Permission to disclose information or documents on one occasion shall not authorize Contractor to further disclose such information or documents on any other occasions except as otherwise provided in the Contract or required by law.

- Contractor shall not comment publicly to the press or any other media regarding the data or documents generated, collected, or produced in connection with this contract, or the State’s actions on the same, except to the Mental Health Services Oversight and Accountability Commission staff, Contractor’s own personnel involved in the performance of this Contract, or as required by law.

- If requested by State, Contractor shall require each of its employees or officers who will be involved in the performance of this Contract to agree to the above terms in a form to be approved by State and shall supply State with evidence thereof.

- Each subcontract shall contain the foregoing provisions related to the confidentiality of data and nondisclosure.

- After any data or documents submitted has become a part of the public records of the State, Contractor may at its own expense and upon written approval by the State Contract Manager, publish or utilize the same data or documents but shall include the following Notice:

LEGAL NOTICE

This report was prepared as an account of work sponsored by the Mental Health Services Oversight and Accountability Commission (MHSOAC), but does not necessarily represent the views of the MHSOAC or any of its employees except to the extent, if any, that it has formally been approved by the MHSOAC.  For information regarding any such action, communicate directly with the MHSOAC at 1325 J Street, Suite 1700, Sacramento, CA 95814.  Neither the MHSOAC nor the State of California, nor any officer or employee thereof, or any of its contractors or subcontractors makes any warranty, express or implied, or assumes any legal liability whatsoever for the contents of this document.  Nor does any party represent that use of the data contained herein, would not infringe upon privately owned rights without obtaining permission or authorization from any party who has any rights in connection with the data.

- PROVISIONS RELATING TO DATA:

- “Data” as used in this Contract means recorded information, regardless of form or characteristics, of a scientific or technical nature.  It may, for example, document research, experimental, developmental or engineering work; or be usable or be used to define a design or process; or support a premise or conclusion asserted in any deliverable document called for by this Contract.  The data may be graphic or pictorial delineations in media, such as drawings or photographs, charts, tables, mathematical modes, collections or extrapolations of data or information, etc.  It may be in machine form, as punched cards, magnetic tape, computer printouts, or may be retained in computer memory.

- “Generated data” is that data, which a Contractor has collected, collated, recorded, deduced, read out or postulated for utilization in the performance of this Contract.  Any electronic data processing program, model or software system developed or substantially modified by the Contractor in the performance of this Contract at State expense, together with complete documentation thereof, shall be treated in the same manner as generated data.

- “Deliverable data” is that data which under terms of this Contract is required to be delivered to the State.  Such data shall be property of the State.

- Prior to the expiration of any legally required retention period and before destroying any data, Contractor shall notify the State of any such contemplated action; and State may within 30 days of said notification determine whether or not this data shall be further preserved.  The State shall pay the expense of further preserving this data.  State shall have unrestricted reasonable access to the data that is preserved in accordance with this Contract.

- Contractor shall use best efforts to furnish competent witnesses or to identify such competent witnesses to testify in any court of law regarding data used in or generated under the performance of this Contract.

- APPROVAL OF PRODUCT: Unless otherwise specified in Exhibit A, each product to be approved under this Contract shall be approved by the Contract Manager.  The State’s determination as to satisfactory work shall be final absent fraud or mistake.

- SUBSTITUTIONS: Contractor’s key personnel as indicated in its Proposal may not be substituted without Contract Manager’s prior written approval.

- NOTICE: Notice to either party shall be given by first class mail properly addressed, postage fully prepaid, to the address listed in Exhibit A for each respective party.  Such notice shall be effective when received as indicated by post office records or if deemed undeliverable by post office, such notice shall be effective nevertheless 15 days after mailing.  Alternatively, notice may be given by personal delivery by any means whatsoever to the party, and such notice shall be deemed effective when delivered.

- WAIVER: No waiver of any breach of this Contract shall be held to be a waiver of any other or subsequent breach.  All remedies afforded in this Contract shall be taken and construed as cumulative; that is, in addition to every other remedy provided therein or by law.  The failure of State to enforce at any time the provisions of this Contract, or to require at any time performance by the Contractor of any of the provisions, shall in no way be construed to be a waiver of such provisions not to affect the validity of this Contract or the right of State to enforce said provisions.

- GRATUITIES AND CONTINGENCY FEES: The State, by written notice to the Contractor, may terminate the right of Contractor to proceed under this Contract if it is found, after notice and hearing by the State, that gratuities were offered or given by the Contractor or any agent or representative of the Contractor to any officer or employee of the State with a view toward securing a contract or securing favorable treatment with respect to the awarding, amending, or performing of such contract.

In the event this Contract is terminated as provided in the paragraph above, State shall be entitled (a) to pursue the same remedies against Contractor as it could pursue in the event of the breach of the Contract by the Contractor, and (b) as a predetermined amount of liquidated damages, to exemplary damages in an amount which shall not be less than three times the cost incurred by the Contractor in providing any such gratuities to any such officer or employee.

The rights and remedies of the State provided in this clause shall not be exclusive and are in addition to any other rights and remedies provided by law or under this Contract.

The Contractor warrants by execution of this Contract that no person or selling agency has been employed or retained to solicit or secure this Contract for a commission, percentage, brokerage or contingent fee, excepting bona fide employees of Contractor, for the purpose of securing business.  For breach or violation of this warranty, the State shall have the right to annul this Contract without liability, paying only for the values of the work actually returned, or in its discretion to deduct from the contract price or consideration, or otherwise recover, the full amount of such commission, percentage, brokerage, or contingent fee.

- WORKERS’ COMPENSATION: Contractor hereby warrants that it carries and shall maintain in full force and effect during the full term of this contract and any extensions to said term, sufficient and adequate Worker’s Compensation Insurance for all of its employees who shall be engaged in the performance of this Contract and agrees to furnish to State satisfactory evidence thereof at any time the State may request the same.

- CONTRACT IS COMPLETE: Other than as specified herein, no document or communication passing between the parties hereto shall be deemed a part of this Contract.

- CAPTIONS: The clause headings appearing in this Contract have been inserted for the purpose of convenience and ready reference.  They do not purport to and shall not be deemed to define, limit or extend the scope or intent of the clauses to which they pertain.

- PUBLIC HEARINGS: If public hearings on the subject matter dealt with in this Contract are held within one year from the contract expiration date, Contractor shall make available to testify the personnel assigned to this Contract at the hourly rates specified in the Contractor’s proposed budget.  State shall reimburse Contractor for travel of said personnel at the contract rates for such testimony as may be requested by State.

- FORCE MAJEURE: Neither the State nor the Contractor shall be deemed to be in default in the performance of the terms of this Contract if either party is prevented from performing the terms of this Contract by causes beyond its control, including without being limited to:  acts of God; interference, rulings or decision by municipal, Federal, State or other governmental agencies, boards or commissions; any laws and/or regulations of such municipal, State, Federal, or other governmental bodies; or any catastrophe resulting from flood, fire, explosion, or other causes beyond the control of the defaulting party.  If any of the stated contingencies occur, the party delayed by force majeure shall immediately give the other party written notice of the cause of delay.  The party delayed by force majeure shall use reasonable diligence to correct the cause of the delay, if correctable.

- PERMITS AND LICENSES: The Contractor shall procure and keep in full force and effect during the term of this Contract all permits, registrations and licenses necessary to accomplish the work specified in this Contract, and give all notices necessary and incident to the lawful prosecution of the work.

The Contractor shall keep informed of, observe, comply with, and cause all of its agents and employees to observe and to comply with all prevailing Federal, State, and local laws, and rules and regulations made pursuant to said Federal, State, and local laws, which in any way affect the conduct of the work of this Contract.  If any conflict arises between provisions of the plans and specifications of this Contract and any such law above referred to, then the Contractor shall immediately notify the State in writing.

- LITIGATION: The State, promptly after receiving notice thereof, shall notify the Contractor in writing of the commencement of any claim, suit, or action against the State or its officers or employees for which the Contractor must provide indemnification under this Contract.  The failure of the State to give such notice, information, authorization or assistance shall not relieve the Contractor of its indemnification obligations.  The Contractor shall immediately notify the State of any claim or action against it which affects, or may affect, this Contract, the terms and conditions hereunder, or the State, and shall take such action with respect to said claim or action which is consistent with the terms of this Contract and the interest of the State.

- DISPUTES: Contractor shall first discuss and attempt to resolve any dispute arising under or relating to the performance of this Contract, which is not disposed of by the Contract, informally with the State Contract Manager.  If the dispute cannot be disposed of at this level, then the dispute shall be decided by the MHSOAC’s Executive Director.  All issues pertaining to this dispute shall be submitted in written statements and addressed to the Executive Director, MHSOAC, 1325 J Street, Suite 1700, Sacramento, California 95814.  Such written notice must contain the Contract Number.  The decision of the Executive Director of the MHSOAC shall be final and binding to all parties.  Within ten days of receipt of the written grievance report from the Contractor, the Executive Director, or his/her designee, shall meet with the Contractor and Project Manager for the purposes of resolving the dispute.  The decision of the Executive Director shall be final.  During the dispute process the Contractor shall proceed diligently with the performance of the Contract.  Neither the pendency of a dispute, nor its consideration by the Executive Director, shall excuse the Contractor from full and timely performance of the services required in accordance with the terms of the contract.

Notwithstanding any other provisions of this Contract, after recourse to the procedure set forth in the paragraph above, any controversy or claim arising out of or relating to this Contract or breach thereof shall be settled by arbitration at the election of either party in accordance with California Public Contract Code Section 10240 et. seq. and judgment upon the award rendered by the arbitration may be entered in any court having jurisdiction thereof.

- EVALUATION OF CONTRACTOR’S PERFORMANCE: The Contractor’s performance under this Contract shall be evaluated by the State after completion of the contract.  A copy of the written evaluation shall be maintained in the contract file and may be submitted to the Office of Legal Services, Department of General Services.

- CONFIDENTIALITY AND INFORMATION SECURITY PROVISIONS:

- The Contractor shall comply with applicable laws and regulations, including but not limited to Sections 14100.2 and 5328 et seq. of the Welfare and Institutions Code, Section 431.300 et seq. of Title 42, Code of Federal Regulations, and the Health Insurance Portability and Accountability Act (HIPAA), and it’s implementing regulations (including but not limited to Title 45, CFR, Parts 160, 162 and 164) regarding the confidentiality and security of individually identifiable health information (IIHI).

- Nondisclosure.  Contractor shall not use or disclose confidential, individually identifiable, or sensitive information other than as permitted or required by the Contract and as permitted or required by law.

- INSPECTION AND ENFORCEMENT:

- From time to time, the State may inspect the facilities, systems, books and records of Contractor to monitor compliance with the Contract.

- Contractor shall promptly remedy any violation of any provision of the Contract and shall certify the same to the MHSOAC in writing.

- The fact that the State inspects, or fails to inspect, or has the right to inspect Contractor’s facilities, systems, and procedures does not relieve Contractor of its responsibility to comply with the Contract.

- The State’s failure to detect or the State’s detection of any unsatisfactory practices, but failure to notify Contractor or require Contractor’s remediation of the unsatisfactory practices does not constitute acceptance of such practice or a waiver of the State’s enforcement rights under the Contract.

- USE OF STATE FUNDS: Contractor, including its officers and members, shall not use funds received from the MHSOAC pursuant to this contract to support or pay for costs or expenses related to the following:

- Campaigning or other partisan activities to advocate for either the election or defeat of any candidate for elective office, or for or against the passage of any proposition or ballot measure; or,

- Lobbying for either the passage or defeat of any legislation.

This provision is not intended and shall not be construed to limit any activities specified in this Contract that are intended to inform, educate, and support advocacy before local and state administrative and legislative bodies regarding policies and issue-based legislation consistent with the Mental Health Services Act.

This provision is not intended and shall not be construed to limit any expression of a view, opinion, or position of any member of Contractor as an individual or private citizens, as long as state funds are not used; nor does this provision limit Contractor from merely reporting the results of a poll or survey of its membership.

## ATTACHMENT 18: Questions Template

Use this template for submitting questions in relation to this procurement. Add rows as needed. Follow Key Action Dates in Section I.B, and submit to the procurement official identified in Section I.E.

| Parents and Caregivers RFP |  |  |
| --- | --- | --- |
|  | RFP Section Reference | Question |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| 4 |  |  |
| 5 |  |  |
| 6 |  |  |
| 7 |  |  |
| 8 |  |  |