REQUEST FOR PROPOSAL (RFP)

Transition Age Youth Advocacy

RFP TAY-005

November 20, 2025

Behavioral Health Services

Oversight and Accountability Commission

1812 9th Street

Sacramento, CA 95811

https://www.bhsoac.ca.gov

Contents

1.	INTRODUCTION	3

2.	PURPOSE	4

3.	BACKGROUND	4

4.	KEY ACTION DATES	6

5.	CONTRACT TERM AND FUNDING	7

6.	SCOPE OF WORK	8

7.	INFORMATION REQUIRED IN THE PROPOSAL	16

8.	PROPOSER INSTRUCTIONS	22

9.	SUBMISSION INSTRUCTIONS	27

10.	SCORING PROCESS	28

ATTACHMENT 1: PROPOSAL COVER SHEET	39

ATTACHMENT 2: MINIMUM QUALIFICATIONS	40

ATTACHMENT 3: PROPOSER BACKGROUND	41

ATTACHMENT 4: PROPOSED WORKPLAN	45

ATTACHMENT 5: COST SHEET	48

ATTACHMENT 6: REFERENCES	50

ATTACHMENT 7: BIDDER DECLARATION (GSPD-05-105)	53

ATTACHMENT 8: CONTRACTOR CERTIFICATION CLAUSES	54

ATTACHMENT 9: DARFUR CONTRACTING ACT CERTIFICATION	58

ATTACHMENT 10: PAYEE DATA RECORD (STD 204)	59

ATTACHMENT 11: FINAL SUBMISSION CHECKLIST	60

ATTACHMENT 12: QUESTIONS TEMPLATE	61

APPENDIX 1: CONTRACT EXHIBITS B and C	62

EXHIBIT D: BUDGET AND NARRATIVE	76

APPENDIX 2: WORKPLAN	77

## INTRODUCTION

The Behavioral Health Services Oversight and Accountability Commission (Commission) was established by the Behavioral Health Services Act (BHSA) to promote transformational change in California’s public behavioral health system. The BHSA is a landmark law designed to improve behavioral health services for California’s most vulnerable populations by notably incorporating the voices of people with lived experience through robust community planning and engagement processes. The BHSA recognizes transition age youth (TAY), defined in the California Code of Regulations, title 9, section 3200.280, as ages sixteen (16) to twenty-five (25), as a key population whose voices must be heard to ensure that services and supports accurately reflect their needs and ultimately improve outcomes. In alignment with these values, the Commission supports community-driven efforts that reach and elevate these voices at both the local and state levels, increasing participation so that the behavioral health system truly reflects the realities and needs of the populations it serves.

This Request for Proposal (RFP) seeks a contractor to lead an advocacy initiative that builds the leadership, systems knowledge, and advocacy capacity of TAY, with a focus on those from BHSA priority populations. These include TAY with a serious mental illness (SMI), serious emotional disturbance (SED), substance use disorder (SUD), or co-occurring conditions who are also experiencing or at risk of:

- chronic homelessness;

- involvement in the criminal or juvenile justice system;

- reentry from incarceration or youth correctional facilities;

- placement in or transition from the child welfare system;

- conservatorship; or

- institutionalization.

This RFP is designed to empower TAY to advocate for themselves and their peers while creating a safe, supportive environment that fosters connection, belonging, purpose, and a sense of agency through shared experience and peer leadership.

## PURPOSE

The Commission is releasing this RFP to award a contract to one (1) organization to develop and facilitate a program that builds the leadership, advocacy, training and education, and outreach and engagement capacity of TAY populations. The contractor will support and empower TAY, especially those from BHSA priority populations, to lead advocacy efforts and engage meaningfully with behavioral health systems and decision-makers.

Proposers must demonstrate that they have the personnel and organizational capacity to effectively carry out a contract of this scope and magnitude, including meeting minimum requirements and demonstrating experience working with TAY from BHSA priority populations.

## BACKGROUND

- BHSA Community Planning Process

The BHSA requires counties to participate in a transparent and collaborative Community Planning Process every three years, with annual updates, to ensure that state and county agencies fully consider consumers’ concerns about the quality, structure, and accessibility of behavioral health services￼ including those of TAY. The BHSA Community Planning Process results in the development of County Integrated Plans, which outline how counties will utilize various behavioral health funding sources (i.e., BHSA, 1991 and 2011 Realignment, federal grant programs, federal financial participation from Medi-Cal, opioid settlement funds, local funding, and other funding) to meet statewide and local outcome measures, reduce disparities, and address unmet needs along the Behavioral Health Care Continuum￼

The BHSA intends to fund services for TAY across all county and state level funding streams including full service partnerships, housing interventions, and behavioral health services and supports at the local level, and population-based prevention on the state level. Notably, it requires that at least 51% of the California Department of Public Health’s population-based prevention efforts, and at least 51% of counties’ Behavioral Health Services and Supports funding for early intervention, serve individuals aged 25 and under.

- TAY Population

The California Code of Regulations, title 9, section 3200.280 defines TAY as individuals aged sixteen (16) to twenty-five (25), which represents about 15% of the state’s population. They face a unique set of challenges during the critical transition from adolescence to adulthood. Many struggle with physical, behavioral health and emotional health issues, housing instability, educational and employment barriers, and fragmented access to services as they move from child-serving systems to adult behavioral health systems. During a listening session held by the Commission at Sacramento City College, TAY in attendance confirmed these realities, expressing the need for connections to resources and guidance when aging out of services.

- Previous Commission Advocacy Contracts

To elevate the voices of underserved populations in shaping behavioral health policy and funding, the Commission issues advocacy contracts that support community-driven efforts in training and education, outreach and engagement, and policy engagement. The Budget Act of 2015 identified TAY as one of the populations to be supported by the Commission’s advocacy contracts. Currently, $670,000 per year is allocated for TAY Advocacy programming, totaling $2,010,000 over three years. Since 2017, the Commission has conducted three rounds of procurement for TAY Advocacy contracts, awarding one three-year contract in April 2017, August 2019, and December 2022.

The awarded contractors have supported TAY to lead advocacy, training and education, and outreach and engagement activities in partnership with local-level entities across California’s Superior, Bay Area, Central, Los Angeles, and Southern regions. These efforts have convened hundreds of TAY in local and state-level spaces and successfully elevated their voices to decision-makers throughout the state.

With the forthcoming full enactment of the BHSA, this RFP continues to advance advocacy, training and education, and outreach and engagement while aligning with updated BHSA priorities and incorporating feedback from TAY gathered from the Commission’s community engagement efforts. It aims to provide TAY, particularly those reflected in the BHSA priority populations, with increased opportunities to lead advocacy efforts and shape behavioral health policies that affect their communities. These efforts recognize that peer-led advocacy not only informs better policy, but also supports improved behavioral health by fostering connection, belonging, and empowerment among TAY through shared experiences.

## KEY ACTION DATES

Key actions, including dates and times for this RFP, are presented in the chart below. An addendum to this RFP will be released if any of these dates change.

Table 4-1: Key Action Dates

| Action | Action Date & Time |
| --- | --- |
| RFP Release | 11/20/2025 |
| Deadline for Written Questions | 12/03/2025 |
| Distribute Responses to Questions | 12/10/2025 |
| Deadline to Submit Proposals | 01/16/2026 by 12:00 pm (pacific) |
| Notice of Intent to Award* | 03/26/2026 |

* Dates after Deadline to Submit Proposals are estimates and may be changed by the Commission without the issuance of an addendum.

- RFP RELEASE

The RFP will be posted on the Commission’s website at: www.bhsoac.ca.gov.

- DEADLINE FOR WRITTEN QUESTIONS

All questions must be submitted directly to the Commission via email to: procurements@bhsoac.ca.gov by the deadline listed in Table 4-1 above and must include in the Subject Line: RFP TAY-005. Use Attachment 12, Questions Template, to submit questions. At its discretion, the Commission reserves the right to contact candidates to seek clarification of any inquiry received.

- DISTRIBUTE QUESTIONS AND RESPONSES

All questions submitted in writing will be answered in writing by the Commission. The questions and responses will be posted on the Commission’s website (www.bhsoac.ca.gov) by the deadline listed in Table 4-1 above.

The Commission may change the RFP as a result of the Question/Response process in the form of an Addendum. Please note that oral information to or from the Commission will not be binding unless it is confirmed in writing.

- DEADLINE TO SUBMIT PROPOSALS

Proposals must be submitted electronically to the Commission, via e-mail, to: procurements@bhsoac.ca.gov by the deadline listed in Table 4-1 above and must include in the Subject Line: RFP TAY-005. For the purposes of this RFP, the official time that will be used to determine if a proposal was submitted on time is when the Commission receives the proposal.

- NOTICE OF INTENT TO AWARD

The Notice of Intent to Award is anticipated to be announced at the January 2026 Commission meeting, if a meeting is held, and posted on the Commission’s website (www.bhsoac.ca.gov) by the date listed in Table 4-1 above.

## CONTRACT TERM AND FUNDING

Following the award, the Proposer will be required to enter into a written Contract with the Commission. (See Appendix 1.)

The term of this Contract is upon execution for thirty-six (36) months.

One contract will be issued for $2,010,000.

- AWARD PROCEDURES

An award, if made, will go to the highest scoring Proposal. If there are two or more Proposals with the same total score, the tie will be broken by a coin toss administered by the Commission.

Prior to awarding the Contract, a Notice of Intent to Award will be posted on the Commission’s website (www.bhsoac.ca.gov) for a period of no less than five (5) working days.

- CONTRACT PERFORMANCE

Services are expected to begin upon contract execution. Performance means the satisfactory completion and receipt of each deliverable under the due dates set forth in Exhibit B. Payment Detail. Contract performance and payment will also be governed by Exhibit C: General Terms and Conditions.

## SCOPE OF WORK

- GOALS AND OBJECTIVES

The overarching goal of this contract is to help ensure that TAY, including those who are reflected in the BHSA priority populations, have opportunities to develop sustainable leadership and advocacy skills that enable them to authentically and meaningfully engage in community-led discussions to help shape behavioral health systems. To support this aim, this contract includes the following goals focused on training and education, outreach and engagement, and advocacy:

- Training and education: Develop TAY population leadership and advocacy skills by increasing their knowledge of behavioral health systems and helping them build the confidence, networks, and capabilities needed to organize, educate peers, and participate in local and state decision-making processes.

- Outreach and engagement: Support TAY to build trust with each other and with a broad and diverse range of vulnerable individuals, expanding participation, fostering connection, and reaching new voices across California

- Advocacy: Support TAY in identifying their priorities, developing strategies, and engaging directly with decision-makers to influence behavioral health systems at both the local and state levels.

- CONTRACTOR RESPONSIBILITIES

To achieve the goals and objectives of this contract, the Contractor will implement a TAY-led Leadership Academy comprised of three (3) nine (9) month long cohorts focused on developing leadership and advocacy skills, broadening outreach and engagement, facilitating advocacy efforts, and providing supportive funding to TAY, giving precedence to TAY from BHSA priority populations. This contract will be executed in three phases:

- A six (6) month Planning Phase for curriculum development and recruitment design and implementation.

- A twenty-seven (27) month Operations Phase to implement three (3) 
nine (9) month cohorts.

- A three (3) month Evaluation Phase to assess program outcomes, organizational effectiveness, and TAY participant growth.

Each of these phases are outlined below.

- Planning Phase

During the first six (6) month Planning Phase, the Contractor shall:

- Develop a Leadership Academy curriculum that is co-designed with TAY members, culturally responsive, and covers leadership skills, advocacy strategies, behavioral health policy and systems knowledge, and effective communication.

- Produce an Advocacy Toolkit informed by the Leadership Academy.

- Design and implement a recruitment strategy that attracts a diverse group of TAY to each cohort, prioritizing outreach to BHSA priority populations at risk of or in high-needs settings such as youth detention facilities, homeless shelters and transitional housing, foster homes and congregate care, and alternative or continuation schools. In line with the strategy developed, recruitment shall occur prior to initiating each nine (9) month cohort.

- Operations Phase

Following the first six (6) month Planning Phase, the Contractor shall begin the Operations Phase by establishing and facilitating three (3) nine (9) month cohorts of recruited TAY members who will receive, engage with, and apply the co-designed Leadership Academy curriculum and practice learned skills. The Operations Phase shall include implementation of the TAY advocacy projects, the provision of additional supportive services to enhance the personal and professional growth of TAY cohort participants, as well as supportive funding to enable TAY participation. Each of these activities are described below.

- Implementation

Implementation activities for the TAY advocacy projects include efforts to:

- Support cohort members in identifying and developing TAY advocacy projects that reflect the needs of their communities, with an emphasis on BHSA priority populations.

- Provide opportunities for cohort members to perform outreach and engagement to TAY communities to ensure their voices and priorities are reflected in their TAY advocacy projects.

- Facilitate opportunities for cohort members to practice advocating for their TAY advocacy projects in state and local settings, such as the BHSA Community Planning Process.

- Foster peer-to-peer connections and community-building within cohorts and the broader TAY network including, but not limited to, TAY individuals and TAY-focused organizations to promote trust, belonging, and sustained engagement.

- Encourage cohort members to co-lead and co-facilitate learning sessions on topics identified by each cohort to inform their final projects, whenever possible, ensuring ongoing input and adaptation based on cohort feedback.

- Additional Supportive Services

The Contractor shall connect cohort members with opportunities to enhance their personal and professional growth by providing access to resources that support career development, financial stability, and educational advancement. These services include, but are not limited to:

- Behavioral Health Career Pathways. The Contractor shall provide information and guidance on career options related to behavioral health and advocacy such as:

  - Medi-Cal Peer Support Specialists

  - Behavioral Health Wellness Coaches

  - Community Health Workers

  - Substance Use Disorder Counselors

  - Other relevant behavioral health or advocacy careers

- Educational and Financial Resources: The Contractor shall offer participants access to programs and services that support financial literacy, educational attainment, and overall well-being including:

  - Financial literacy education

  - Federal and state aid programs

  - California College Promise Program

  - Other relevant grants and resources

- Supportive Funding

A portion of the contract funding shall be allocated to enable and support TAY participation, broken into two categories:

- Recruitment and Retention Funds. Funds used to compensate cohort members following the fulfillment of cohort obligations, as specified in a Recruitment and Retention Fund Plan. Payment frequency, amount, and method of distribution to be determined by the Contractor.

- Equity Access Funds. Ten percent (10%) of the total contract shall be reserved to promote equitable access for TAY to participate in the advocacy cohorts, as specified in an Equity Access Fund Plan. Specifically, these funds may be used to remove financial barriers that may otherwise prevent TAY from participating including, but not limited to, technology, Internet, transportation, and professional clothing. Requirements for the Equity Access Funding are as follows:

  - The Contractor shall have spending authority for individual expenses under $250. Expenses $250 or greater will require Commission pre-approval.

  - The Contractor shall submit receipts and details related to equity access spending with quarterly reports.

The Contractor shall develop a TAY Impact Showcase and Story Collection as a required deliverable due at the end of each cohort period.

- Evaluation Phase

The Contractor shall conduct ongoing evaluation activities throughout the Planning and Operations Phases, collecting data on the key indicators for each of the evaluation dimensions listed in the table below. This data will be used to develop an Evaluation and Final Report during the final three (3) month Evaluation Phase.

Table 6-1: Evaluation Dimensions and Key Indicators

| Evaluation Dimension | Key Indicators |
| --- | --- |
| Training & Curriculum Quality | - Relevance and accessibility of content - Youth-led modifications over time - Participation and satisfaction rates - Cultural and linguistic responsiveness |
| Organizational Capacity & Execution | - Staffing and training of facilitators - Timeliness and quality of deliverables - Use of discretionary funds to support equitable participation - Ability to recruit diverse TAY |
| Outreach & Engagement Reach | - Number and diversity of TAY engaged - TAY-led planning and delivery - Safe spaces created - Representation of BHSA-defined TAY Priority Populations |
| Adaptability & Learning | - Updates to workplans and curriculum based on TAY feedback - Responsiveness to challenges (e.g., recruitment, engagement) - Transparency about lessons learned |
| TAY Participant Growth & Empowerment | - Growth in confidence, leadership, behavioral health literacy - Familiarity of and comfort with civic processes - Uptake of peer mentoring or facilitation roles - Sense of belonging and voice |
| Advocacy Skill-Building & Systems Exposure | - Participation in advocacy simulations, panels, planning processes (BHSA-Community Planning Process) - Understanding of local/state systems - Comfort engaging decision-makers - Youth-set advocacy goals |
| Field-Level Learning & Influence | - Sharing of tools, frameworks, or curriculum - Participation in youth-led coalitions - Replication of model in other spaces - Impact on local/state systems |

- DELIVERABLES

To fulfill the Scope of Work requirements, the Contractor shall produce the deliverables specified below in accordance with the contract goals and objectives. See Figure 6-1 for a quarterly breakout of the project deliverables and activities for the three project phases (planning, operations and evaluation).

- Final Workplan

During the six (6) month Planning Phase, the Contractor shall submit a Final Workplan that outlines how each of the Scope of Work activities and deliverables will be achieved.
At a minimum, the Workplan shall address the following:

  - Leadership Academy Development: a description of the process and timeline for co-designing with TAY the Leadership Academy curriculum, as well as the cohort recruitment strategy to attract diverse TAY participants.

  - Implementation: approach and schedule for launching and facilitating the three (3) TAY advocacy cohorts.

  - Additional Supportive Services: strategies for connecting TAY cohort participants to behavioral health and/or advocacy career pathways, as well as relevant educational and financial resources.

  - Supportive Funding: use of funds to compensate TAY cohort participants and equitably support their participation in the TAY advocacy projects.

  - Evaluation: a description of the evaluation methodology for the Leadership Academy Curriculum and Recruitment Strategy, as well as on the TAY Cohort Participant Outcomes.

- Quarterly Progress Reports

The Contractor shall submit Quarterly Progress Reports within thirty (30) days of the end of each quarter. Reports shall provide:

- Progress updates on Scope of Work activities and deliverables.

- Summary of data collected as part of the ongoing evaluation, including participant feedback and outcomes measures.

- Challenges encountered, solutions applied, and continuous improvement actions.

- Documentation of all Supportive Funding efforts, including purchase justification and receipts.

- A reporting template will be provided by the Commission.

- Leadership Academy Curriculum

The Contractor shall develop and deliver the initial Leadership Academy Curriculum during the six (6) month Planning Phase which shall include:

- A finalized, ready-to-implement curriculum to be used across the three (3) nine-month TAY cohorts, including any facilitator guidance, session plans, and learning modules.

- The curriculum shall be used to guide learning and skill development throughout all cohorts and will be made available to the Commission for future use, adaptation, and dissemination.

- The Contractor shall re-deliver the curriculum, including any updated facilitator guidance, session plans, and learning modules, after any material updates or changes are made.

- TAY Impact Showcase and Story Collection

The Contractor shall develop a TAY Impact Showcase and Story Collection, due at the end of each cohort period, that shall:

- Highlight participant experiences, leadership growth, and advocacy efforts.

- Include written, visual, or multimedia testimonials or creative products.

- Reflect the voices and perspectives of TAY participants, especially those from BHSA priority populations.

- Be suitable for Commission use in education, communication, public awareness, or advocacy efforts.

- Advocacy Toolkit

The Contractor shall develop and deliver an Advocacy Toolkit during the six (6) month Planning Phase which shall include:

- Documents summarizing effective advocacy strategies and practical tools, such as templates, all of which will be used to inform and support TAY-led advocacy efforts during the Operations Phase.

- All materials shall be made available to the Commission for future use, adaptation, and dissemination.

- Final Report & Evaluation

In the final quarter of the contract, the Contractor shall submit a Final Report and Evaluation in lieu of a quarterly report. This comprehensive deliverable shall include:

- A summary of all program activities and outcomes over the contract term, including documentation of how TAY input shaped the content and design of the Leadership Academy and Advocacy Toolkit.

- A highlight of intentional engagement with BHSA priority populations.

- A summary that addresses cultural responsiveness throughout the project and identifies opportunities to better connect and engage with TAY, including ways to empower youth voice and encourage participation and suggest areas where TAY influence can have the greatest impact.

- A final evaluation produced using the framework provided by the Commission and incorporating data and information collected throughout the contract. This evaluation shall include:

  - Analyses aligned with the key dimensions outlined in the Commission’s framework including, but not limited to, participant growth, curriculum quality, organizational effectiveness, and broader field impact.

  - Quantitative and qualitative data from self-assessments, participation tracking, surveys, and interviews.

  - Documentation of youth input and program adaptations over time.

  - Recommendations for future TAY advocacy and youth leadership initiatives.

Figure 6-1: Quarterly Planning, Operations and Evaluation Activities and Deliverables

- Other Requirements

The Contractor is required to engage in ongoing communications with the Commission and relevant constituents regarding all phases of this project, which includes, but is not limited to, the following:

- Maintain ongoing interaction with Commission staff and other Commission constituents.

- Participate in monthly check-ins, at a minimum, with Commission staff to discuss project progress.

- Provide updates and presentations to the Commission.

- Develop and provide a plan for the dissemination of deliverables to Commission community partners and other interested parties.

- DELIVERABLE ACCEPTANCE

- This is a deliverables-based contract.

- Deliverables must be approved by the Commission before an invoice is submitted for payment.

- Upon receiving a contract deliverable, the Commission will review the deliverable in a timely manner and choose one of the following options:

  - Approve the deliverable and notify the Contractor to submit an invoice for payment, or

  - Request additional information before approving the deliverable, or

  - Reject the deliverable, provide the Contractor with the reason for the rejection,  and inform the Contractor of the corrective action that is needed before the deliverable will be approved.

## INFORMATION REQUIRED IN THE PROPOSAL

The following information is required for all Proposals. Attachments are provided for the proposer to respond to all the requirements, and the fields for each attachment expand as text is entered into the document. Proposers must provide a response to all requirements. Responses should be succinct and to the point of responding to the requirement. There are no additional points for the length of a response. If there is a requirement that a Proposer deems “Not Applicable,” the Proposer must respond that the requirement is “Not Applicable” and provide a reason to support the statement.

- PROPOSAL COVER SHEET (ATTACHMENT 1)

  - Enter the Proposer’s Name and other requested information.

  - Provide the signature of someone authorized by the organization to enter into a contract and to attest that all information included in the proposal is true and accurate. Electronic signatures are accepted.

  - Provide a Program Coordinator contact designated to receive all communications.

- MINIMUM QUALIFICATIONS (ATTACHMENT 2)

Each of the minimum qualifications below must be met by the Proposer. The Proposer must include documentation and reference the documentation within the proposal that verifies each qualification. The purpose of establishing these minimum qualifications is to ensure that the entities submitting a proposal have adequate experience and capacity to perform the duties as outlined in the RFP.

  - Be an established organization which has been in operation for at least two (2) years and has at least two (2) years’ experience supporting, facilitating, or partnering with TAY youth-led or youth-serving programs. Documentation must be provided to support the Proposer’s experience.

  - Be a 501(c)(3) non-profit corporation, registered to do business in California. Evidence that the Proposer is registered to do business in California. The support can be provided with a copy or screen shot of your California Secretary of State certification showing an “Active Status”. This can be found at https://bizfileonline.sos.ca.gov/search/business.

- PROPOSER BACKGROUND (ATTACHMENT 3)

Provide a response to the following:

- Describe how long your organization has been in existence, including your mission, core activities, and organizational structure. Provide support in the form of documentation.

- Describe your experience engaging, mentoring, or supporting TAY, particularly from BHSA priority populations.

  - Include examples of programs or initiatives that demonstrate your ability to reach, teach, and support TAY, build leadership, and develop advocacy skills.

  - Describe your ability to teach TAY how to understand, navigate, and engage with local and state behavioral health systems.

- How many staff are employed by your organization? This does not include volunteers or contractors. Provide support in the form of documentation.

- Describe your organization’s operational capacity, systems, and partnerships that demonstrate your ability to:

  - Recruit and engage diverse TAY participants particularly from BHSA priority populations in high-needs settings (e.g., juvenile justice facilities, homeless shelters, foster care, alternative schools).

  - Facilitate multi-cohort programs.

  - Deliver curriculum and workshops effectively.

  - Provide supportive services to TAY participants.

  - Support TAY in engaging with behavioral health systems and practicing advocacy skills.

- Describe your experience designing, developing, or delivering curriculum, workshops, or structured learning experiences for TAY populations.

  - Highlight how your experience demonstrates your ability to develop and implement the Leadership Academy curriculum, including co-design and co-facilitation with TAY participants, and including teaching TAY to apply leadership and advocacy skills in real-world contexts.

  - Describe your approach to ensuring curriculum is culturally responsive and accessible.

- Describe your approaches and methods for connecting TAY, particularly BHSA priority populations, to programs, services, or supportive networks.

  - Provide examples that demonstrate your capacity to recruit participants, foster peer connections, and maintain engagement over time.

- Provide evidence of outcomes achieved through your TAY programs (e.g., leadership growth, skill development, confidence, engagement).

  - Include supporting documentation (e.g., evaluations, testimonials, reports, or examples of participant work).

  - Explain how these outcomes demonstrate your organization’s ability to achieve the goals and objectives of this RFP, including youth engagement in advocacy and system navigation.

- PROPOSED WORKPLAN (ATTACHMENT 4)

Describe your approach and timeline for completing the indicated Scope of Work responsibilities and deliverables. Indicate project milestones and completion dates for each item, and specify all date(s) as days, weeks, months, quarters, and/or years.

- Planning Phase

  - Develop a Leadership Academy curriculum that is co-designed with TAY members, culturally responsive, and covers leadership skills, advocacy strategies, behavioral health policy and systems knowledge, and effective communication.

  - Produce an Advocacy Toolkit informed by the Leadership Academy.

  - Design and implement a recruitment strategy that attracts a diverse group of TAY to each cohort.

- Operations Phase

  - Implementation

  - Establish and facilitate three (3) nine (9) month cohorts of recruited TAY members who will receive, engage with, and apply the co-designed Leadership Academy curriculum and practice learned skills.

  - Support cohort members in identifying and developing TAY advocacy projects that reflect the needs of their communities, with an emphasis on BHSA priority populations.

  - Provide opportunities for cohort members to perform outreach and engagement to TAY communities to ensure their voices and priorities are reflected in their TAY advocacy projects.

  - Facilitate opportunities for cohort members to practice advocating for their TAY advocacy projects in state and local settings, such as the BHSA Community Planning Process.

  - Foster peer-to-peer connections and community-building within cohorts and the broader TAY network including, but not limited to, TAY individuals and TAY-focused organizations to promote trust, belonging, and sustained engagement.

  - Encourage cohort members to co-lead and co-facilitate learning sessions on topics identified by each cohort to inform their final projects, whenever possible, ensuring ongoing input and adaptation based on cohort feedback.

  - Additional Supportive Services

- Behavioral Health Career Pathways

- Educational and Financial Resources

- Supportive Funding

  - Recruitment and Retention Funds

  - Equity Access Funds

- Evaluation Phase

  - Training and Curriculum Quality

  - Organizational Capacity and Execution

  - Outreach and Engagement Reach

  - Adaptability and Learning

  - TAY Participant Growth and Empowerment

  - Advocacy Skill-Building and Systems Exposure

  - Field-Level Learning and Influence

- Deliverables

  - Final Workplan: During the six (6) month Planning Phase, the Contractor shall submit a Final Workplan during the Planning Phase that outlines how all Scope of Work activities and deliverables will be achieved.

  - Quarterly Progress Reports: The Contractor shall submit Quarterly Progress Reports within thirty (30) days of the end of each quarter.

  - Leadership Academy Curriculum: The Contractor shall develop and deliver the initial Leadership Academy Curriculum during the six (6) month Planning Phase.

  - TAY Impact Showcase and Story Collection: The Contractor shall develop a TAY Impact Showcase and Story Collection, due at the end of each cohort period.

  - Advocacy Toolkit: The Contractor shall develop and deliver an Advocacy Toolkit during the six (6) month Planning Phase.

  - Final Report & Evaluation: In the final quarter of the contract, the Contractor shall submit a Final Report and Evaluation in lieu of a quarterly report.

- COST SHEET (ATTACHMENT 5)

- This section requires the completion of the Cost Sheet (Attachment 5) and the RFP TAY-005 - Budget and Narrative (Exhibit D).

- This is a deliverables-based contract. Contractor will only be paid for the successful completion of the deliverables and activities listed on the Cost Sheet. Payments will be made no more frequent than on a quarterly basis.

- The Cost sheet is pre-filled with the deliverables listed in Section 6.D. Proposer must propose a cost for each deliverable.

- In addition, the Proposer will complete Exhibit D – Budget and Narrative (See separate Excel workbook) to identify and explain all costs that will be incurred by the Proposer in completing the SOW and deliverables. The total of the annual costs by Budget Year shall agree to the total annual costs on the Cost Sheet (Attachment 5).

- The Commission reserves the right to negotiate to execute a contract, including but not limited to the approval and acceptance of all Cost Sheet line items (deliverables, activities, and cost).

- REFERENCES (ATTACHMENT 6)

Provide two (2) references from TAY individuals who have participated in programs or services provided by the Proposer related to leadership development, advocacy, behavioral health, or youth engagement. All references shall be from activities performed within the last two (2) years.

- References cannot be a family member of a board member and/or employee of the Proposer, or employed by the Proposer, or previously employed by the Proposer during the time period referred to in the reference.

- The same individual cannot be used for both references.

- The references will attest to the services or programs they received from the Proposer and provide an objective assessment of their experience 
(ATTACHMENT 6).

- BIDDER DECLARATION (GSPD-05-105) ATTACHMENT (ATTACHMENT 7)

- The Bidder Declaration form (GSPD-05-105) is a required submittal. It is available at the following website: https://www.documents.dgs.ca.gov/dgs/fmc/gs/pd/gspd05-105.pdf. This document will be used to identify all subcontractors in the proposal.

- CONTRACTOR CERTIFICATIONS CLAUSES (CCC-307) (ATTACHMENT 8)

  - Required certification to enter into a contract with the State.

- DARFUR CONTRACTING ACT CERTIFICATIONS (ATTACHMENT 9)

- Effective January 1, 2009, Public Contract Code sections 10475, et. seq.; Stats. 2008, Ch. 272, requires that all solicitations must address the requirements of the Darfur Contracting Act of 2008 (Act). (Public Contract Code sections 10475, et seq.; Stats. 2008, Ch. 272). The Act was passed by the California Legislature and signed into law by the Governor to preclude State agencies generally from contracting with “scrutinized” companies that do business in the African nation of Sudan (of which the Darfur region is a part), for the reasons described in Public Contract Code section 10475.

- A scrutinized company is a company doing business in Sudan as defined in Public Contract Code section 10476. Scrutinized companies are ineligible to, and cannot, bid on or submit a Proposal for a contract with a State agency for goods or services. (Public Contract Code section 10477(a)).

- Therefore, Public Contract Code section 10478 (a) requires a company that currently has (or within the previous three years has had) business activities or other operations outside of the United States to certify that it is not a “scrutinized” company when it submits a bid or Proposal to a State agency. (See option #1 on ATTACHMENT 12).

- A scrutinized company may still, however, submit a bid or Proposal for a contract with a State agency for goods or services if the company first obtains permission from the Department of General Services according to the criteria set forth in Public Contract Code section 10477(b). (See option #2 on ATTACHMENT 12).

- PAYEE DATA RECORD (STD 204) (ATTACHMENT 10)

- The Payee Data Record (STD 204) is required to receive a payment from the State of California and is completed in lieu of an IRS W-9 or W-7. The information provided is used to populate the check (warrant) when payments are made. In addition, the information is used for California state agencies to prepare Information Returns (Form 1099)

- GENERATIVE ARTIFICIAL INTELLIGENCE (GENAI)

- The State of California seeks to realize the potential benefits of GenAI, through the development and deployment of GenAI tools, while balancing the risks of these new technologies.

- Bidder/Offeror must notify the State in writing if it: (1) intends to provide GenAI as a deliverable to the State; or (2), intends to utilize GenAI, including GenAI from third parties, to complete all or a portion of any deliverable that materially impacts: (i) functionality of a State system, (ii) risk to the State, or (iii) Contract performance. For avoidance of doubt, the term "materially impacts" shall have the meaning set forth in State Administrative Manual (SAM) 4986.2.

- Failure to report GenAI to the State may result in disqualification. The State reserves its right to seek any and all relief it may be entitled to as a result of such non-disclosure.

- Upon notification by a Bidder/Offeror of GenAI as required, the state reserves the right to incorporate GenAI Special Provisions into the final contract or reject bids/offers that present an unacceptable level of risk to the state.

- Government Code 11549.64 defines “Generative Artificial Intelligence (GenAI)” as an artificial intelligence system that can generate derived synthetic content, including text, images, video, and audio that emulates the structure and characteristics of the system’s training data.

## PROPOSER INSTRUCTIONS

- PROPOSER ADMONISHMENT

This solicitation will follow an approach designed to increase the likelihood that proposers have a full understanding of the requirements before attempting to develop their proposal.

It is the proposer’s responsibility to:

      - Carefully read the entire solicitation,

      - Ask appropriate questions in a timely manner, if clarification is necessary,

      - Submit all required responses by the deadlines,

      - Make sure that all procedures and requirements in the solicitation are accurately followed and appropriately addressed, and

      - Carefully re-read the entire solicitation before submitting an application.

Proposals are to be prepared in such a way as to provide a straightforward, concise explanation of capabilities to satisfy the requirements of this RFP. Colored displays, promotional materials, etc., are not necessary or desired. Emphasis should be concentrated on conformance to the RFP instructions, responsiveness to the RFP requirements, and on completeness and clarity of content.

Proposers are encouraged to submit their proposal in either a Word format or a searchable PDF format. Proposers are responsible for ensuring all pages, attachments and signatures are included in the proposal. In addition, Proposer is responsible for ensuring all pages on the Proposal are legible.

Proposals must comply with all RFP requirements. Before submitting a response to this RFP, Proposers should review the Proposal, correct all errors, and confirm compliance with the RFP requirements. Not complying with the RFP requirements is cause for a Proposal to be rejected. The Commission reserves the right to contact a proposer about any errors and/or omissions in the Proposal.

- WRITTEN QUESTIONS

Written questions must be submitted by email to procurements@bhsoac.ca.gov, using ATTACHMENT 12, Questions Template. Email subject line shall be RFP TAY-005. Only questions submitted in writing and answered in writing by the Commission shall be binding and official. All written questions submitted by the deadline, specified in the Key Action Dates (Table 4-1), will be responded to by the Commission. At its discretion, the Commission reserves the right to contact a proposer to seek clarification of any inquiry received.

Any changes to the RFP will be made in the form of an addendum. Please note that no verbal information given will be binding upon the Commission unless such information is confirmed in writing.

The Commission’s website (www.bhsoac.ca.gov) will be the official means to communicate with prospective proposers. Information and ongoing communications for this solicitation will be posted on the website.

- SOLICITATION DOCUMENT

This solicitation document includes, in addition to an explanation of the Commission’s requirements which must be met, instructions which prescribe the format and content of bids to be submitted and the model of the contract to be executed between the Commission and the successful proposer.

If a proposer discovers any ambiguity, conflict, discrepancy, omission, or other error in this solicitation document, the proposer shall immediately notify the Commission by email at procurements@mhsoac.ca.gov of such error in writing and request clarification or modification of the document.

If the solicitation document contains an error known to the proposer, or an error that reasonably should have been known, the proposer shall bid at its own risk. If the proposer fails to notify the Commission of the error prior to the date fixed for submission of bids, and is awarded the contract, the proposer shall not be entitled to additional compensation or time by reason of the error or its later correction.

- CONFIDENTIALITY

Proposer’s material becomes public only after the Notice of Intent to Award is released. If material marked “confidential,” “proprietary,” or “trade secret” is requested pursuant to the California Public Records Act, Government Code Section 6250 et seq., the Commission will independently assess whether it is exempt from disclosure.

The Proposer should be aware that marking a document “confidential” or “proprietary” in a bid may exclude it from consideration for award and will not keep that document from being released after Notice of Intent to Award as part of the public record.

- ADDENDA

The Commission may modify the solicitation prior to contract award by issuance of an addendum. The addendum will be published on the Commission’s website.

- RFP CANCELLATION

If it is in the State’s best interest, the Commission reserves the right to do any of the following:

- Cancel this RFP;

- Amend this RFP as needed; or

- Reject any or all Proposals received in response to this RFP.

- PROPOSER’S COST

Costs for developing the proposal is the responsibility entirely of the proposer and shall not be chargeable to the Commission.

- SIGNATURE OF BID (PROPOSAL)

A cover letter (which shall be considered an integral part of the proposal), and any bid form requiring signature, must be signed by an individual who is authorized to bind the bidding organization contractually. Electronic signatures will be accepted for the submission of an application. The signature block must indicate the title or position that the individual holds in the bidding organization. An unsigned proposal may be rejected.

- FALSE OR MISLEADING STATEMENTS

Proposals which contain false or misleading statements may be rejected. If, in the opinion of the Commission, such information was intended to mislead the Commission in its scoring of the bid, and the attribute, condition, or capability is a requirement of this solicitation document, it will be the basis for rejection of the proposal.

- DISPOSITION OF PROPOSALS

All materials submitted in response to this solicitation will become the property of the State of California and will be returned only at the Commission’s option and at the proposer’s request. A copy of the proposal shall be retained for official files and will become a public record after the Notice of Intent to Award is posted. However, materials the Commission considered as confidential information will be returned upon request of the proposer.

- MODIFYING OR WITHDRAWAL OF PROPOSAL

A Proposer may, by letter to the Procurement Official, withdraw or modify a submitted Proposal before the deadline to submit Proposals. Proposals cannot be changed after the deadline to submit.

- IMMATERIAL DEFECT

The Commission may waive any immaterial defect or deviation contained in a Proposer’s Proposal. The Commission’s waiver shall in no way modify the Proposal or excuse the successful Proposer from full compliance.

- PROTEST

This RFP is solicited in accordance with the Welfare and Institutions Code Section 5897(f) which exempts the Commission from the Public Contract Code and the State Administrative Manual and the Department of General Services approval. Therefore, the provisions to protest the award of a contract under this RFP shall be as stated below.

There is no basis for protest if the Commission rejects all proposals based on the best interest of the State or if the Commission cancels the RFP. Only a Proposer who submitted a proposal to this RFP may protest the award of a contract under this RFP.

An Intent to Protest letter from a Proposer must be received at the following address no later than 3:00pm (Pacific Time) five (5) working days from the date of the posting of Notice of Intent to Award. The only acceptable delivery method for Intent to Protest letter is by a postal service (United States Post Office, Federal Express, etc.). The Intent to Protest letter cannot be hand delivered by the Proposer, faxed, or sent by electronic mail. Any Intent to Protest letter received without an original signature and/or by a delivery method other than a postal service will not be considered.

Include the following label information and deliver your Intent to Protest, in a sealed envelope:

Proposer Name

Street Address

City, State, Zip Code

INTENT TO PROTEST

RFP TAY-005

Riann Kopchak

Behavioral Health Services Oversight & Accountability Commission

1812 9th Street, Sacramento, California 95811

Within five (5) working days from the date the Commission receives the Intent to Protest letter, the protesting Proposer must file with the Commission at the above address a Letter of Protest detailing the grounds for the protest. The only acceptable delivery method for the Letter of Protest is by a postal service (United States Post Office, Federal Express, etc.). The Letter of Protest cannot be hand delivered by the Proposer, faxed or sent by electronic mail. Any Letter of Protest received without an original signature and/or by a delivery method other than a postal service will not be considered.

The Letter of Protest must describe the factors that support the protesting Proposer’s claim that the protesting Proposer would have been awarded the contract had the Commission correctly applied the prescribed evaluation rating standards in the RFP or if the Commission had followed the evaluation and scoring methods in the RFP. The Letter of Protest must identify specific information in the Proposal that the Proposer believes was overlooked or misinterpreted. The Letter of Protest may not provide any additional information that was not included in the original Proposal. The Letter of Protest cannot protest the scoring of another Proposer’s proposal.

If a Letter of Protest is filed, the contract shall not be awarded until the Commission has reviewed and resolved the protest.

The Executive Director of the Commission, or designee, will render a decision in writing to the Protest and the decision will be considered final. The written decision will be sent to the protesting Proposer via a postal service.

## SUBMISSION INSTRUCTIONS

This section contains the format requirements and instructions on how to submit a proposal. The format is prescribed to assist the proposer in meeting State bidding requirements and to enable the Commission to evaluate each proposal uniformly and fairly. Proposer must follow all proposal format instructions, answer all questions, and supply all required documents.

- REQUIRED DOCUMENTS

Proposals must include all required attachments organized in the following order:

Attachment 1: Proposal Cover Sheet

Attachment 2: Minimum Qualifications

Attachment 3: Proposer Background

Attachment 4: Proposed Workplan

Attachment 5: Cost Sheet

Attachment 6: References

Attachment 7: Bidder Declaration (GSPD-05-105)

Attachment 8: Contractor Certification Clauses (CCC-307)

Attachment 9: Darfur Contracting Act Certification (if applicable)

Attachment 10: Payee Data Record (STD 204)

Attachment 11: Final Submission Checklist

Exhibit D: Budget and Narrative

Proposals that do not include all of the above listed items, including proper signatures when required, shall be deemed non-compliant. A non-compliant proposal is one that does not meet the basic proposal requirements and may be rejected.

- REQUIRED PROPOSAL FORMAT

Proposals must be submitted electronically to:

procurements@bhsoac.ca.gov
Subject Line: RFP TAY-005

Proposals may be submitted in either Word or PDF format. If submitting in PDF format, a readable PDF format is preferable. Proposals should have a Table of Contents and page numbers on each page. Proposals must comply with all RFP requirements. Before submitting a response to this RFP, Proposers should review the application, correct all errors, and confirm compliance with the RFP requirements. Not complying with all of the RFP requirements is cause for a proposal to be rejected.

Due to file size restrictions, please ensure the Proposal does not exceed 25mb in size. If it does, please consider reducing the size of the file, while still maintaining the integrity of the contents, or sending multiple files to complete your submission. If submitting multiple files, all files must be received by the date and time listed on the Key Action Dates in Table 4-1. It is recommended that Proposer submit a follow-up email to ensure the Commission has received the complete Proposal submission.

The Commission reserves the right to contact any Proposer to ensure a complete proposal was received, including clarification of submitted items.

- LATE SUBMISSIONS

Late proposals will not be accepted. Proposers assume all risk of late submission. Proposals received after the deadline will be rejected without review. Incomplete submissions may also be rejected without review.

## SCORING PROCESS

This section explains how the proposals will be scored.

- PROPOSAL SCORING

Proposals will be evaluated and scored based on their response to the information requested in this RFP. All elements of the RFP require a response unless otherwise indicated. Evaluation will be conducted based on consensus scoring of the Evaluation Panel. The entire procurement process, from issuance of the RFP to the receipt of proposals, and scoring of the proposals until completion of the competitive process, with the issuance of the Notice of Intent to Award is confidential. All Proposals and the final evaluation and scoring sheet will be considered public documents upon completion of the competitive process and the issuance of the Notice of Intent to Award.

Proposals will be evaluated as follows:

#### Administrative Review

Initially, each Proposal will be reviewed by the Commission for the presence of all required documents as listed in Section 7. In addition, the Proposal Cover Sheet (Attachment 1) and the Minimum Qualifications (Attachment 2) will be reviewed for completeness. The review will be scored on a pass/fail basis. Those Proposals that pass the Administrative Review move on to the Technical Review. Those Proposals that do not meet the requirements of Administrative Review will be deemed non-compliant and will not be eligible to receive an award.

#### Technical Review

Each Proposal will be evaluated and scored based on the Proposer’s response to each requirement. The Evaluation will be based on meeting all aspects of the following requirements:

- Attachment 3: Proposer Background

- Attachment 4: Proposed Workplan

- Attachment 5: Cost Sheet

- Attachment 6: References

- Exhibit D: Budget and Narrative

Total Points Available:

| No. | Requirement | Points Available |
| --- | --- | --- |
| 1 | Administrative Review | Pass/Fail |
| 2 | Proposer Background | 3,400 |
| 3 | Proposed Workplan | 3,600 |
| 4 | Cost Sheet | 2,000 |
| 5 | References | 2,000 |
| 6 | Total Evaluation Points | 11,000 |

Evaluation Criteria

The following criteria will be used, where applicable:

| No. | Criteria | Definition |
| --- | --- | --- |
| 1 | Clarity | The ease at which the information presented is understood. |
| 2 | Reasonableness | The reasonableness of the information presented being accomplished successfully and is in alignment with the requirement. |
| 3 | Completeness | The thoroughness of a response in addressing a requirement. |
| 4 | Alignment with current functions being performed by Proposer. | Focus is on activities that have proven successful in the past for the organization. |

Scoring

| Minimally addresses the requirement (25% or less) | Partially meets the requirement (Less than 50%) | Partially meets the requirement (More than 50%) | Fully meets the requirement (At least 90%) |
| --- | --- | --- | --- |
| 1 | 2 | 3 | 5 |

Each Evaluation Criteria used will be given a score of 0, 1, 2, 3, or 5. Scores will be converted to points. Multiple Evaluation Criteria may be used for each requirement. See Evaluation Scoring Detail.

Evaluation Scoring Detail

| No. | Requirement* | Points Available |
| --- | --- | --- |
| PROPOSER BACKGROUND |  |  |
| C.1. | Describe how long your organization has been in existence, including your mission, core activities, and organizational structure. Scoring Criteria: Clarity and Reasonableness (Max 100 points available. Calculated: Clarity and Reasonableness are worth 5 points each. Score will be multiplied by 10 to award max points) | 100 |
| C.1.a. | Provide support. Scoring Criteria: Clarity and Reasonableness (Max 200 points available. Calculated: Clarity and Reasonableness are worth 5 points each. Score will be multiplied by 20 to award max points) | 200 |
| C.1. Calc | Existence Scoring: The Proposer(s) with the most fully supported years of experience will receive full points. All other will receive a ratio of points based on the number of fully supported years of experience compared to the Proposer(s) who has the most fully supported years of experience. (Max 100 points available. Calculated: Number of fully supported years of experience / Proposer(s) with the most fully supported years of experience x 100 points) | 100 |
| C.2. | Describe your experience engaging, mentoring, or supporting TAY, particularly from BHSA priority populations. Scoring Criteria: Clarity and Reasonableness (Max 100 points available. Calculated: Clarity and Reasonableness are worth 5 points each. Score will be multiplied by 10 to award max points) | 100 |
| C.2.a. | Include examples of programs or initiatives that demonstrate your ability to reach, teach, and support TAY, build leadership, and develop advocacy skills. Scoring Criteria: Clarity and Reasonableness (Max 200 points available. Calculated: Clarity and Reasonableness are worth 5 points each. Score will be multiplied by 20 to award max points) | 200 |
| C.2.b. | Describe your ability to teach TAY how to understand, navigate, and engage with local and state behavioral health systems. Scoring Criteria: Clarity and Reasonableness (Max 200 points available. Calculated: Clarity and Reasonableness are worth 5 points each. Score will be multiplied by 20 to award max points) | 200 |
| C.3. | How many staff are employed by your organization? This does not include volunteers or contractors. Scoring Criteria: Clarity and Reasonableness (Max 100 points available. Calculated: Clarity and Reasonableness are worth 5 points each. Score will be multiplied by 10 to award max points) | 100 |
| C.3.a. | Provide support. Scoring Criteria: Clarity and Reasonableness (Max 200 points available. Calculated: Clarity and Reasonableness are worth 5 points each. Score will be multiplied by 20 to award max points) | 200 |
| C.3. Calc | Existence - Staffing Scoring: The Proposer(s) with the most fully supported number of staff will receive full points. All other will receive a ratio of points based on the number of fully supported staff compared to the Proposer(s) who has the most fully supported staff. (Max 200 points available. Calculated: Number of fully supported years of experience / Proposer(s) with the most fully supported years of experience x 200 points) | 200 |
| C.4.a. | Describe your organization’s operational capacity, systems, and partnerships that demonstrate your ability to: - Recruit and engage diverse TAY participants particularly from BHSA priority populations in high-needs settings (e.g., juvenile justice facilities, homeless shelters, foster care, alternative schools). - Facilitate multi-cohort programs. - Deliver curriculum and workshops effectively. - Provide supportive services to TAY participants. - Support TAY in engaging with behavioral health systems and practicing advocacy skills. Scoring Criteria: Clarity and Reasonableness (Max 400 points available. Calculated: Clarity and Reasonableness are worth 5 points each. Score will be multiplied by 40 to award max points) | 400 |
| C.5. | Describe your experience designing, developing, or delivering curriculum, workshops, or structured learning experiences for TAY populations. Scoring Criteria: Clarity and Reasonableness (Max 200 points available. Calculated: Clarity and Reasonableness are worth 5 points each. Score will be multiplied by 20 to award max points) | 200 |
| C.5.a. | Highlight how your experience demonstrates your ability to develop and implement the Leadership Academy curriculum, including co-design and co-facilitation with TAY participants, and including teaching TAY to apply leadership and advocacy skills in real-world contexts. Scoring Criteria: Clarity and Reasonableness (Max 200 points available. Calculated: Clarity and Reasonableness are worth 5 points each. Score will be multiplied by 20 to award max points) | 200 |
| C.5.b. | Describe your approach to ensuring curriculum is culturally responsive and accessible. Scoring Criteria: Clarity and Reasonableness (Max 100 points available. Calculated: Clarity and Reasonableness are worth 5 points each. Score will be multiplied by 10 to award max points) | 100 |
| C.6. | Describe your approaches and methods for connecting TAY, particularly BHSA priority populations, to programs, services, or supportive networks. Scoring Criteria: Clarity and Reasonableness (Max 200 points available. Calculated: Clarity and Reasonableness are worth 5 points each. Score will be multiplied by 20 to award max points) | 200 |
| C.6.a. | Provide examples that demonstrate your capacity to recruit participants, foster peer connections, and maintain engagement over time. Scoring Criteria: Clarity and Reasonableness (Max 300 points available. Calculated: Clarity and Reasonableness are worth 5 points each. Score will be multiplied by 30 to award max points) | 300 |
| C.7. | Provide evidence of outcomes achieved through your TAY programs (e.g., leadership growth, skill development, confidence, engagement). Scoring Criteria: Clarity and Reasonableness (Max 200 points available. Calculated: Clarity and Reasonableness are worth 5 points each. Score will be multiplied by 20 to award max points) | 200 |
| C.7.a. | Include supporting documentation (e.g., evaluations, testimonials, reports, or examples of participant work). Scoring Criteria: Clarity and Reasonableness (Max 200 points available. Calculated: Clarity and Reasonableness are worth 5 points each. Score will be multiplied by 20 to award max points) | 200 |
| C.7.b. | Explain how these outcomes demonstrate your organization’s ability to achieve the goals and objectives of this RFP, including youth engagement in advocacy and system navigation. Scoring Criteria: Clarity and Reasonableness (Max 200 points available. Calculated: Clarity and Reasonableness are worth 5 points each. Score will be multiplied by 20 to award max points) | 200 |
| PROPOSED WORKPLAN |  |  |
| D. | Describe your approach and timeline for completing the indicated Scope of Work responsibilities and deliverables. Indicate project milestones and completion dates for each item, and specify all date(s) as days, weeks, months, quarters, and/or years. |  |
| D.1. | Planning Phase - Develop a Leadership Academy curriculum that is co-designed with TAY members, culturally responsive, and covers leadership skills, advocacy strategies, behavioral health policy and systems knowledge, and effective communication. - Produce an Advocacy Toolkit informed by the Leadership Academy. - Design and implement a recruitment strategy that attracts a diverse group of TAY to each cohort. Scoring Criteria: Clarity, Reasonableness, Completeness, and Alignment. (Max 700 points available. Calculated: Clarity, Reasonableness, Completeness, and Alignment are worth 5 points each. Score will be multiplied by 35 to award max points) | 700 |
| D.2 | Operations Phase |  |
| D.2.a | Implementation - Establish and facilitate three (3) nine (9)-month cohorts of recruited TAY members who will receive, engage with, and apply the co-designed Leadership Academy curriculum and practice learned skills. - Support cohort members in identifying and developing TAY advocacy projects that reflect the needs of their communities, with an emphasis on BHSA priority populations. - Provide opportunities for cohort members to perform outreach and engagement to TAY communities to ensure their voices and priorities are reflected in their TAY advocacy projects. - Facilitate opportunities for cohort members to practice advocating for their TAY advocacy projects in state and local settings, such as the BHSA Community Planning Process. - Fostering peer-to-peer connection and community building within cohorts and the broader TAY network including, but not limited to, TAY individuals and TAY-focused organizations to promote trust, belonging, and sustained engagement. - Encourage cohort members to co-lead and co-facilitate learning sessions on topics identified by each cohort to inform their final projects, whenever possible, ensuring ongoing input and adaptation based on cohort feedback. Scoring Criteria: Clarity, Reasonableness, Completeness, and Alignment. (Max 700 points available. Calculated: Clarity, Reasonableness, Completeness, and Alignment are worth 5 points each. Score will be multiplied by 35 to award max points) | 700 |
| D.2.b. | Additional Supportive Services - Behavioral Health Career Pathways - Educational and Financial Resources Scoring Criteria: Clarity, Reasonableness, Completeness, and Alignment. (Max 500 points available. Calculated: Clarity, Reasonableness, Completeness, and Alignment are worth 5 points each. Score will be multiplied by 25 to award max points) | 500 |
| D.2.c | Supportive Funding - Recruitment and Retention Funds - Equity Access Funds Scoring Criteria: Clarity, Reasonableness, Completeness, and Alignment. (Max 500 points available. Calculated: Clarity, Reasonableness, Completeness, and Alignment are worth 5 points each. Score will be multiplied by 25 to award max points) | 500 |
| D.3. | Evaluation Phase - Training and Curriculum Quality - Organizational Capacity and Execution - Outreach and Engagement Reach - Adaptability and Learning - TAY Participant Growth and Empowerment - Advocacy Skill-Building and Systems Exposure - Field-Level Learning and Influence Scoring Criteria: Clarity, Reasonableness, Completeness, and Alignment. (Max 500 points available. Calculated: Clarity, Reasonableness, Completeness, and Alignment are worth 5 points each. Score will be multiplied by 25 to award max points) | 500 |
| D.4. | Deliverables - Final Workplan: During the six (6) month Planning Phase, the Contractor shall submit a Final Workplan during the Planning Phase that outlines how all Scope of Work activities and deliverables will be achieved. - Quarterly Progress Reports: The Contractor shall submit Quarterly Progress Reports within thirty (30) days of the end of each quarter. - Leadership Academy Curriculum: The Contractor shall develop and deliver the initial Leadership Academy Curriculum during the six (6) month Planning Phase. - TAY Impact Showcase and Story Collection: The Contractor shall develop a TAY Impact Showcase and Story Collection, due at the end of each cohort period. - Advocacy Toolkit: The Contractor shall develop and deliver an Advocacy Toolkit during the six (6) month Planning Phase. - Final Report & Evaluation: In the final quarter of the contract, the Contractor shall submit a Final Report and Evaluation in lieu of a quarterly report. Scoring Criteria: Clarity, Reasonableness, Completeness, and Alignment. (Max 700 points available. Calculated: Clarity, Reasonableness, Completeness, and Alignment are worth 5 points each. Score will be multiplied by 35 to award max points) | 700 |
| COST SHEET |  |  |
| E. | - This section requires the completion of the Cost Sheet (Attachment 5) and the Budget and Narrative (Exhibit D). - This is a deliverables-based contract. Contractor will only be paid for the successful completion of the deliverables and activities listed on the Cost Sheet. Payments will be made no more frequent than on a quarterly basis. - The Cost sheet is pre-filled with the deliverables listed in Section 6.D. Proposer must propose a cost for each deliverable. - In addition, the Proposer will complete Exhibit D – Budget and Narrative (See separate Excel workbook) to identify and explain all costs that will be incurred by the Proposer in completing the SOW and deliverables. The total of the annual costs by Budget Year shall agree to the total annual costs on the Cost Sheet (Attachment 5). Scoring Criteria: Clarity, Reasonableness, and Completeness. (Max 2000 points available. Calculated: Clarity, Reasonableness, and Completeness are worth 5 points each. Score will be multiplied by 133.33 to award max points) | 2000 |
| REFERENCES |  |  |
| F. | Provide two (2) references from TAY individuals who have participated in programs or services provided by the Proposer related to leadership development, advocacy, behavioral health, or youth engagement. All references shall be from activities performed within the last two (2) years |  |
| F. | - References cannot be a family member of a board member and/or employee of the Proposer, or employed by the Proposer, or previously employed by the Proposer during the time period referred to in the reference. - The same individual cannot be used for both references. - The references will attest to the services or programs they received from the Proposer and provide an objective assessment of their experience (ATTACHMENT 6). Scoring Criteria: Actual reference scores. (Max 1000 points per reference, 2000 total points. Calculated: Each reference is worth 25 points. Each reference score will be multiplied by 40 to award max points) | 2000 |
| TOTAL EVALUATION POINTS |  | 11,000 |

* The requirements stated in the scoring table may not reflect the full actual requirement being scored. The information presented here is for reference only. Refer to actual requirements in Section 7.

The Commission reserves the right to negotiate to finalize a contract. This includes but is not limited to all of the responses provided in the winning proposal. The intent is to ensure that the winning proposal is complete to the point that the Commission accepts and approves all content in the proposal and subsequent contract.

## ATTACHMENT 1: PROPOSAL COVER SHEET

Provide the information below.

| Proposer Name |  |
| --- | --- |
| Proposer Address and Telephone Number |  |
| Name of Authorized Signor (Print) |  |
| Signature of Authorized Signor | Date |

I HEREBY CERTIFY under penalty of perjury that I have the authority to sign this proposal on behalf of the named Proposer above and that all information provided in this proposal is true and accurate.

I further understand and agree to accept and comply with all the requirements in the RFP and related documents. In addition, if there is any false information in the proposal that it is grounds for the proposal to be rejected, and if any false information comes to light after contract award, that it is grounds for the contract to be terminated immediately.

Program Coordinator Contact Information

| Name: |  |
| --- | --- |
| Title: |  |
| Email: |  |
| Phone Number: |  |

## ATTACHMENT 2: MINIMUM QUALIFICATIONS

Provide a response and support for the following minimum qualifications of the Proposer:

| B.1. | Be an established organization which has been in operation for at least two (2) years and has at least two (2) years’ experience supporting, facilitating, or partnering with youth-led or youth-serving programs; - Provide support |
| --- | --- |
|  | Provide support and reference the location in the proposal where the support is located |
| B.2. | Be a 501(c)(3) non-profit corporation, registered to do business in California. - Evidence that Proposer is registered to do business in California. The support can be provided with a copy or screen shot of your California Secretary of State certification showing an “Active Status”. This can be found at https://bizfileonline.sos.ca.gov/search/business. |
|  | Reference the location in the proposal where the support is located |

## ATTACHMENT 3: PROPOSER BACKGROUND

Provide a response to the following:

| C.1. | Describe how long your organization has been in existence, including your mission, core activities, and organizational structure. |
| --- | --- |
|  | - Provide support. |
| C.2. | Describe your experience engaging, mentoring, or supporting TAY, particularly from BHSA priority populations. |
|  | - Include examples of programs or initiatives that demonstrate your ability to reach, teach, and support TAY, build leadership, and develop advocacy skills. |
|  | - Describe your ability to teach TAY how to understand, navigate, and engage with local and state behavioral health systems. |
| C.3. | How many staff are employed by your organization? This does not include volunteers or contractors? |
|  | - Provide support. |
| C.4. | Describe your organization’s operational capacity, systems, and partnerships that demonstrate your ability to: - Recruit and engage diverse TAY participants particularly from BHSA priority populations in high-needs settings (e.g., juvenile justice facilities, homeless shelters, foster care, alternative schools) - Facilitate multi-cohort programs - Deliver curriculum and workshops effectively - Provide supportive services to TAY participants - Support TAY in engaging with behavioral health systems and practicing advocacy skills. |
| C.5. | Describe your experience designing, developing, or delivering curriculum, workshops, or structured learning experiences for TAY populations. |
|  | - Highlight how your experience demonstrates your ability to develop and implement the Leadership Academy curriculum, including co-design and co-facilitation with TAY participants, and including teaching TAY to apply leadership and advocacy skills in real-world contexts. |
|  | - Describe your approach to ensuring curriculum is culturally responsive and accessible. |
| C.6. | Describe your approaches and methods for connecting TAY, particularly BHSA priority populations, to programs, services, or supportive networks. |
|  | - Provide examples that demonstrate your capacity to recruit participants, foster peer connections, and maintain engagement over time. |
| C.7. | Provide evidence of outcomes achieved through your TAY programs (e.g., leadership growth, skill development, confidence, engagement). |
|  | - Include supporting documentation (e.g., evaluations, testimonials, reports, or examples of participant work). |
|  | - Explain how these outcomes demonstrate your organization’s ability to achieve the goals and objectives of this RFP, including youth engagement in advocacy and system navigation. |

## ATTACHMENT 4: PROPOSED WORKPLAN

Provide a response to the following:

| D. | Describe your approach and timeline for completing the indicated Scope of Work responsibilities and deliverables. Indicate project milestones and completion dates for each item, and specify all date(s) as days, weeks, months, quarters, and/or years. |
| --- | --- |
| D.1. | Planning Phase - Co-designing the Leadership Academy curriculum with TAY members. - Recruiting diverse TAY participants, prioritizing BHSA priority populations in high-needs settings. |
|  | Use APPENDIX 2 – WORKPLAN to respond to this requirement. |
| D.2 | Operations Phase |
| D.2.a | Implementation - Establish and facilitate three (3) nine (9)-month cohorts of recruited TAY members who will receive, engage with, and apply the co-designed Leadership Academy curriculum and practice learned skills. - Support cohort members in identifying and developing TAY advocacy projects that reflect the needs of their communities, with an emphasis on BHSA priority populations. - Provide opportunities for cohort members to perform outreach and engagement to TAY communities to ensure their voices and priorities are reflected in their TAY advocacy projects. - Facilitate opportunities for cohort members to practice advocating for their TAY advocacy projects in state and local settings, such as the BHSA Community Planning Process. - Foster peer-to-peer connections and community-building within cohorts and the broader TAY network including, but not limited to, TAY individuals and TAY-focused organizations to promote trust, belonging, and sustained engagement. - Encourage cohort members to co-lead and co-facilitate learning sessions on topics identified by each cohort to inform their final projects, whenever possible, ensuring ongoing input and adaptation based on cohort feedback. |
|  | Use APPENDIX 2 – WORKPLAN to respond to this requirement. |
| D.2.b | Additional Supportive Services - Behavioral Health Career Pathways - Educational and Financial Resources |
|  | Use APPENDIX 2 – WORKPLAN to respond to this requirement. |
| D.2.c | Supportive Funding - Recruitment and Retention Funds - Equity Access Funds |
|  | Use APPENDIX 2 – WORKPLAN to respond to this requirement. |
| D.3. | Evaluation Phase - Training and Curriculum Quality - Organizational Capacity and Execution - Outreach and Engagement Reach - Adaptability and Learning - TAY Participant Growth and Empowerment - Advocacy Skill-Building and Systems Exposure - Field-Level Learning and Influence |
|  | Use APPENDIX 2 – WORKPLAN to respond to this requirement. |
| D.4. | Deliverables - Final Workplan: During the six (6) month Planning Phase, the Contractor shall submit a Final Workplan during the Planning Phase that outlines how all Scope of Work activities and deliverables will be achieved. - Quarterly Progress Reports: The Contractor shall submit Quarterly Progress Reports within thirty (30) days of the end of each quarter. - Leadership Academy Curriculum: The Contractor shall develop and deliver the initial Leadership Academy Curriculum during the six (6) month Planning Phase. - TAY Impact Showcase and Story Collection: The Contractor shall develop a TAY Impact Showcase and Story Collection, due at the end of each cohort period. - Advocacy Toolkit: The Contractor shall develop and deliver an Advocacy Toolkit during the six (6) month Planning Phase. - Final Report & Evaluation: In the final quarter of the contract, the Contractor shall submit a Final Report and Evaluation in lieu of a quarterly report. |
|  | Use APPENDIX 2 – WORKPLAN to respond to this requirement. |

## ATTACHMENT 5: COST SHEET

| Phase | No. | Deliverable | Year 1 | Year 2 | Year 3 |
| --- | --- | --- | --- | --- | --- |
| Development | 1 | Final Workplan |  |  |  |
|  | 2 | Leadership Academy Curriculum |  |  |  |
|  | 3 | Advocacy Toolkit |  |  |  |
|  | 4 | Quarterly Report Y1Q1 |  |  |  |
|  | 5 | Quarterly Report Y1Q2 |  |  |  |
| Operations | 6 | Quarterly Report Y1Q3 |  |  |  |
|  | 7 | Quarterly Report Y1Q4 |  |  |  |
|  | 8 | Quarterly Report Y2Q1 (End of Cohort 1– includes TAY Impact Showcase and Story Collection) |  |  |  |
|  | 9 | Quarterly Report Y2Q2 |  |  |  |
|  | 10 | Quarterly Report Y2Q3 |  |  |  |
|  | 11 | Quarterly Report Y2Q4 (End of Cohort 2– includes TAY Impact Showcase and Story Collection) |  |  |  |
|  | 12 | Quarterly Report Y3Q1 |  |  |  |
|  | 13 | Quarterly Report Y3Q2 |  |  |  |
|  | 14 | Quarterly Report Y3Q3 (End of Cohort 3 – includes TAY Impact Showcase and Story Collection) |  |  |  |
| Evaluation | 15 | Final Report |  |  |  |
|  | 16 | Recruitment and Retention Funds |  |  |  |
|  | 17 | Equity Access (10% of the contract) | $67,000 | $67,000 | $67,000 |
|  | 18 | Yearly Total Cost |  |  |  |
|  | 19 | Total Cost for All Years (Cannot exceed $2,010,000) |  |  | $2,010,000 |

Instructions:

- This section requires the completion of the Cost Sheet (Attachment 5) and the Budget and Narrative (Exhibit D).

- This is a deliverables-based contract. Contractor will only be paid for the successful completion of the deliverables and activities listed on the Cost Sheet. Payments will be made no more frequent than on a quarterly basis.

- The Cost sheet is pre-filled with the deliverables listed in Section 6.D. Proposer must propose a cost for each deliverable.

- In addition, the Proposer will complete Exhibit D – Budget and Narrative (See separate Excel workbook) to identify and explain all costs that will be incurred by the Proposer in completing the SOW and deliverables. The total of the annual costs by Budget Year shall agree to the total annual costs on the Cost Sheet (Attachment 5).

- The Commission reserves the right to negotiate to execute a contract, including but not limited to the approval and acceptance of all Cost Sheet line items (deliverables, activities, and cost).

## ATTACHMENT 6: REFERENCES

| Reference for: |  |
| --- | --- |
| Organization Name: |  |
| Time Period the Reference Covers (Must have been within the last 2 years of the release date of this RFP) |  |
| Program or Service Provided: (Must be related to leadership development, advocacy, behavioral health, or youth engagement. |  |
| Reference Contact Name and Title: |  |
| Reference Contact Phone Number: |  |
| Reference Contact E Mail Address: |  |

| Ratings: Summarize Proposer’s performance and circle in the column on the right the number which best corresponds to the performance rating for each question. Provide comments related to the rating. Please follow the rating guidelines below for description of rating scale: Rating Guidelines and Description of Rating Scale:. Exceptional (5); Performance/service provided was significantly above expectations. Very Good (4); Performance/service was slightly above expectations. Satisfactory (3); Performance met expectations. Marginal (2); Performance/service was slightly below expectations. Unsatisfactory (1); Performance/service provided was significantly below expectations. Category; Comments Provide a comment for the rating; Rating (Circle One). - Understood my needs and respected my background and experiences.; 1 2 3 4 5. - Made me feel safe, supported, and respected while participating.; 1 2 3 4 5. - Helped me learn new skills that I can use.; 1 2 3 4 5. - Helped me feel more connected to other youth and community supports.; 1 2 3 4 5. - I was given real responsibility and my decisions mattered.; 1 2 3 4 5. Reference Signature; Date. |  |  |
| --- | --- | --- |

## ATTACHMENT 7: BIDDER DECLARATION (GSPD-05-105)

The Bidder Declaration form (GSPD-05-105) is a required submittal. It is available at the following website: https://www.documents.dgs.ca.gov/dgs/fmc/gs/pd/gspd05-105.pdf.

## ATTACHMENT 8: CONTRACTOR CERTIFICATION CLAUSES

CCC-307

CERTIFICATION

I, the official named below, CERTIFY UNDER PENALTY OF PERJURY that I am duly authorized to legally bind the prospective Contractor to the clause(s) listed below. This certification is made under the laws of the State of California.

| Contractor/Bidder Firm Name (Printed) |  | Federal ID Number |
| --- | --- | --- |
| By (Authorized Signature) |  |  |
| Printed Name and Title of Person Signing |  |  |
| Date Executed | Executed in the County of |  |

1. 	STATEMENT OF COMPLIANCE: Contractor has, unless exempted, complied with the nondiscrimination program requirements. (Gov. Code §12990 (a-f) and CCR, Title 2, Section 8103) (Not applicable to public entities.)

2. 	DRUG-FREE WORKPLACE REQUIREMENTS: Contractor will comply with the requirements of the Drug-Free Workplace Act of 1990 and will provide a drug-free workplace by taking the following actions:

a. 	Publish a statement notifying employees that unlawful manufacture, distribution, dispensation, possession or use of a controlled substance is prohibited and specifying actions to be taken against employees for violations.

b. 	Establish a Drug-Free Awareness Program to inform employees about:

1) The dangers of drug abuse in the workplace;

2) The person's or organization's policy of maintaining a drug-free workplace;

3) Any available counseling, rehabilitation and employee assistance programs; and,

4) Penalties that may be imposed upon employees for drug abuse violations.

c. 	Every employee who works on the proposed Agreement will:

1) Receive a copy of the company's drug-free workplace policy statement; and,

2) Agree to abide by the terms of the company's statement as a condition of employment on the Agreement.

Failure to comply with these requirements may result in suspension of payments under the Agreement or termination of the Agreement or both and Contractor may be ineligible for award of any future State agreements if the department determines that any of the following has occurred: the Contractor has made false certification, or violated the certification by failing to carry out the requirements as noted above. (Gov. Code §8350 et seq.)

3.	NATIONAL LABOR RELATIONS BOARD CERTIFICATION: Contractor certifies that no more than one (1) final unappealable finding of contempt of court by a Federal court has been issued against Contractor within the immediately preceding two-year period because of Contractor's failure to comply with an order of a Federal court, which orders Contractor to comply with an order of the National Labor Relations Board. (Pub. Contract Code §10296) (Not applicable to public entities.)

4. 	CONTRACTS FOR LEGAL SERVICES $50,000 OR MORE- PRO BONO REQUIREMENT: Contractor hereby certifies that contractor will comply with the requirements of Section 6072 of the Business and Professions Code, effective January 1, 2003.

Contractor agrees to make a good faith effort to provide a minimum number of hours of pro bono legal services during each year of the contract equal to the lessor of 30 multiplied by the number of full time attorneys in the firm’s offices in the State, with the number of hours prorated on an actual day basis for any contract period of less than a full year or 10% of its contract with the State.

Failure to make a good faith effort may be cause for non-renewal of a state contract for legal services, and may be taken into account when determining the award of future contracts with the State for legal services.

5. 	EXPATRIATE CORPORATIONS: Contractor hereby declares that it is not an expatriate corporation or subsidiary of an expatriate corporation within the meaning of Public Contract Code Section 10286 and 10286.1, and is eligible to contract with the State of California.

6. 	SWEATFREE CODE OF CONDUCT:

a. 	All Contractors contracting for the procurement or laundering of apparel, garments or corresponding accessories, or the procurement of equipment, materials, or supplies, other than procurement related to a public works contract, declare under penalty of perjury that no apparel, garments or corresponding accessories, equipment, materials, or supplies furnished to the state pursuant to the contract have been laundered or produced in whole or in part by sweatshop labor, forced labor, convict labor, indentured labor under penal sanction, abusive forms of child labor or exploitation of children in sweatshop labor, or with the benefit of sweatshop labor, forced labor, convict labor, indentured labor under penal sanction, abusive forms of child labor or exploitation of children in sweatshop labor. The contractor further declares under penalty of perjury that they adhere to the Sweatfree Code of Conduct as set forth on the California Department of Industrial Relations website located at www.dir.ca.gov, and Public Contract Code Section 6108.

b. 	The contractor agrees to cooperate fully in providing reasonable access to the contractor’s records, documents, agents or employees, or premises if reasonably required by authorized officials of the contracting agency, the Department of Industrial Relations, or the Department of Justice to determine the contractor’s compliance with the requirements under paragraph (a).

7. 	DOMESTIC PARTNERS: For contracts over $100,000 executed or amended after January 1, 2007, the contractor certifies that contractor is in compliance with Public Contract Code section 10295.3.

DOING BUSINESS WITH THE STATE OF CALIFORNIA

The following laws apply to persons or entities doing business with the State of California.

1. 	CONFLICT OF INTEREST: Contractor needs to be aware of the following provisions regarding current or former state employees. If Contractor has any questions on the status of any person rendering services or involved with the Agreement, the awarding agency must be contacted immediately for clarification.

Current State Employees (Pub. Contract Code §10410):

1)	No officer or employee shall engage in any employment, activity or enterprise from which the officer or employee receives compensation or has a financial interest and which is sponsored or funded by any state agency, unless the employment, activity or enterprise is required as a condition of regular state employment.

2)	No officer or employee shall contract on his or her own behalf as an independent contractor with any state agency to provide goods or services.

Former State Employees (Pub. Contract Code §10411):

1) 	For the two-year period from the date he or she left state employment, no former state officer or employee may enter into a contract in which he or she engaged in any of the negotiations, transactions, planning, arrangements or any part of the decision-making process relevant to the contract while employed in any capacity by any state agency.

2)	For the twelve-month period from the date he or she left state employment, no former state officer or employee may enter into a contract with any state agency if he or she was employed by that state agency in a policy-making position in the same general subject area as the proposed contract within the 12-month period prior to his or her leaving state service.

If Contractor violates any provisions of above paragraphs, such action by Contractor shall render this Agreement void. (Pub. Contract Code §10420)

Members of boards and commissions are exempt from this section if they do not receive payment other than payment of each meeting of the board or commission, payment for preparatory time and payment for per diem. (Pub. Contract Code §10430 (e))

2.	LABOR CODE/WORKERS' COMPENSATION: Contractor needs to be aware of the provisions which require every employer to be insured against liability for Worker's Compensation or to undertake self-insurance in accordance with the provisions, and Contractor affirms to comply with such provisions before commencing the performance of the work of this Agreement. (Labor Code Section 3700)

3. 	AMERICANS WITH DISABILITIES ACT: Contractor assures the State that it complies with the Americans with Disabilities Act (ADA) of 1990, which prohibits discrimination on the basis of disability, as well as all applicable regulations and guidelines issued pursuant to the ADA. (42 U.S.C. 12101 et seq.)

4. 	CONTRACTOR NAME CHANGE: An amendment is required to change the Contractor's name as listed on this Agreement. Upon receipt of legal documentation of the name change the State will process the amendment. Payment of invoices presented with a new name cannot be paid prior to approval of said amendment.

5. 	CORPORATE QUALIFICATIONS TO DO BUSINESS IN CALIFORNIA:

a. 	When agreements are to be performed in the state by corporations, the contracting agencies will be verifying that the contractor is currently qualified to do business in California in order to ensure that all obligations due to the state are fulfilled.

b. 	"Doing business" is defined in R&TC Section 23101 as actively engaging in any transaction for the purpose of financial or pecuniary gain or profit. Although there are some statutory exceptions to taxation, rarely will a corporate contractor performing within the state not be subject to the franchise tax.

c. 	Both domestic and foreign corporations (those incorporated outside of California) must be in good standing in order to be qualified to do business in California. Agencies will determine whether a corporation is in good standing by calling the Office of the Secretary of State.

6. 	RESOLUTION: A county, city, district, or other local public body must provide the State with a copy of a resolution, order, motion, or ordinance of the local governing body which by law has authority to enter into an agreement, authorizing execution of the agreement.

7. 	AIR OR WATER POLLUTION VIOLATION: Under the State laws, the Contractor shall not be: (1) in violation of any order or resolution not subject to review promulgated by the State Air Resources Board or an air pollution control district; (2) subject to cease and desist order not subject to review issued pursuant to Section 13301 of the Water Code for violation of waste discharge requirements or discharge prohibitions; or (3) finally determined to be in violation of provisions of federal law relating to air or water pollution.

8. 	PAYEE DATA RECORD FORM STD. 204: This form must be completed by all contractors that are not another state agency or other governmental entity.

http://www.documents.dgs.ca.gov/dgs/fmc/pdf/std204.pdf

## ATTACHMENT 9: DARFUR CONTRACTING ACT CERTIFICATION

Public Contract Code Sections 10475 -10481 applies to any company that currently or within the previous three years has had business activities or other operations outside of the United States. For such a company to bid on or submit a Proposal for a State of California contract, the company must certify that it is either a) not a scrutinized company; or b) a scrutinized company that has been granted permission by the Department of General Services to submit a Proposal.

If your company has not, within the previous three years, had any business activities or other operations outside of the United States, you do not need to complete this form.

OPTION #1 - CERTIFICATION

If your company, within the previous three years, has had business activities or other operations outside of the United States, in order to be eligible to submit a bid or Proposal, please insert your company name and Federal ID Number and complete the certification below.

I, the official named below, CERTIFY UNDER PENALTY OF PERJURY that a) the prospective proposer/bidder named below is not a scrutinized company per Public Contract Code 10476; and b) I am duly authorized to legally bind the prospective proposer/bidder named below. This certification is made under the laws of the State of California.

| Company/Vendor Name (Printed) |  | Federal ID Number |
| --- | --- | --- |
| By (Authorized Signature) |  |  |
| Printed Name and Title of Person Signing |  |  |
| Date Executed | Executed in the County and State of |  |

OPTION #2 – WRITTEN PERMISSION FROM DGS

Pursuant to Public Contract Code section 10477(b), the Director of the Department of General Services may permit a scrutinized company, on a case-by-case basis, to bid on or submit a Proposal for a contract with a state agency for goods or services, if it is in the best interests of the state. If you are a scrutinized company that has obtained written permission from the DGS to submit a bid or Proposal, complete the information below.

We are a scrutinized company as defined in Public Contract Code section 10476, but we have received written permission from the Department of General Services to submit a bid or Proposal pursuant to Public Contract Code section 10477(b). A copy of the written permission from DGS is included with our bid or Proposal.

| Company/Vendor Name (Printed) | Federal ID Number |
| --- | --- |
| Initials of Submitter |  |
| Printed Name and Title of Person Initialing |  |

## ATTACHMENT 10: PAYEE DATA RECORD (STD 204)

The Proposer must complete and submit the Payee Data Record (STD. 204) with their Proposal.

This form is available at: http://www.documents.dgs.ca.gov/dgs/fmc/pdf/std204.pdf

## ATTACHMENT 11: FINAL SUBMISSION CHECKLIST

A responsive Proposal shall consist of all the required items identified below. Complete this checklist by marking the box with an “X” for each item you are submitting to the Commission

| Check | DESCRIPTION |
| --- | --- |
|  | Attachment 1: Proposal Cover Sheet |
|  | Attachment 2: Minimum Qualifications |
|  | Attachment 3: Proposer Background |
|  | Attachment 4: Proposed Workplan |
|  | Attachment 5: Cost Sheet |
|  | Attachment 6: References |
|  | Attachment 7: Bidder Declaration (GSPD-05-105) |
|  | Attachment 8: Contractor Certification Clauses (CCC-307) |
|  | Attachment 9: Darfur Contracting Act Certification (if applicable) |
|  | Attachment 10: Payee Data Record (STD 204) |
|  | Attachment 11: Final Submission Checklist |
|  | Exhibit D: Budget and Narrative |

## ATTACHMENT 12: QUESTIONS TEMPLATE

Use this template for submitting questions in relation to this solicitation. Add rows as needed. Follow the Key Action Dates in Table 4-1 and submit it to procurements@mhsoac.ca.gov.

| RFP TAY-005 |  |  |
| --- | --- | --- |
|  | RFP Section Reference | Question |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| 4 |  |  |
| 5 |  |  |
| 6 |  |  |
| 7 |  |  |
| 8 |  |  |

## APPENDIX 1: CONTRACT EXHIBITS B and C

EXHIBIT B SAMPLE

Budget Detail and Payment Provisions

- Invoicing and Payment

- For services satisfactorily rendered (i.e., upon receipt and approval of agreed upon deliverables), and upon receipt and approval of the invoices, the Commission agrees to compensate the Contractor in accordance with Section 5 of this Exhibit B. Payments will be made no more frequent than on a quarterly basis.

- Invoices shall include the Agreement Number and shall be submitted in arrears to the address shown below. Electronic submission is preferred:

Behavioral Health Services Oversight and Accountability Commission
Attention: Accounting Office
1812 9th Street
Sacramento, CA 95831
Accounting@bhsoac.ca.gov

- Budget Contingency Clause

  - It is mutually agreed that if the Budget Act of the current year and/or any subsequent years covered under this Agreement does not appropriate sufficient funds for the program, this Agreement shall no longer be in full force and effect. In this event, the State shall have no liability to pay any funds whatsoever to Contractor or to furnish any other considerations under this Agreement and Contractor shall not be obligated to perform any provisions of this Agreement.

  - If funding for any fiscal year is reduced or deleted by the Budget Act for purposes of this program, the State shall have the option to either cancel this Agreement with no liability occurring to the State, or offer an agreement amendment to Contractor to reflect the reduced amount.

  - If this Agreement overlaps State fiscal years, should funds not be appropriated and approved by the Legislature for the fiscal year(s) following that during which this Agreement was executed, the State may exercise its option to cancel this Agreement.

  - This Agreement is subject to any additional restrictions, limitations, or conditions enacted by the Legislature which may affect the provisions or terms of funding of this contract in any manner.

- Prompt Payment Clause

Payment will be made in accordance with, and within the time specified in, Government Code Chapter 4.5, commencing with Section 927. Payment for deliverables is meant to be inclusive of all of the preparatory work, planning, and material cost involved in the completion of the intent of the deliverable not just the report itself.

- Cost Detail

- The total amount of this Agreement shall not exceed five hundred two thousand five hundred dollars and no cents ($502,500.00). Payment shall be made in accordance with the Payment Table below.

- Payment Table

This is a fixed price deliverables-based contract. Contractor will be paid based on the cost of each deliverable as identified in the Contractor’s proposal (Cost Sheet) with cost allocations and due dates set forth in the table below.

ADD TABLE

EXHIBIT C SAMPLE GENERAL TERMS AND CONDITIONS

- Amendment. This Agreement may be amended upon mutual consent of the parties. No amendment or variation of the terms of this Agreement shall be valid unless made in writing and signed by the parties. No oral understanding or agreement not incorporated in this Agreement is binding on any of the parties.

- Antitrust Claims. By signing this agreement Contractor hereby certifies that if these services or goods are obtained by means of a competitive bid, the Contractor shall comply with the requirements of the Government Code Sections set out below:

  - The Government Code Chapter on Antitrust claims contains the following definitions:

    - "Public Purchase" means a purchase by means of competitive bids of goods, services, or materials by the Commission or any of its political subdivisions or public agencies on whose behalf the Attorney General may bring an action pursuant to subdivision (c) of Section 16750 of the Business and Professions Code.

    - "Public purchasing body" means the Commission or the subdivision or agency making a public purchase. Government Code Section 4550.

  - In submitting a bid to a public purchasing body, the bidder offers and agrees that if the bid is accepted, it will assign to the purchasing body all rights, title, and interest in and to all causes of action it may have under Section 4 of the Clayton Act (15 U.S.C. Sec. 15) or under the Cartwright Act (Chapter 2 (commencing with Section 16700) of Part 2 of Division 7 of the Business and Professions Code), arising from purchases of goods, materials, or services by the bidder for sale to the purchasing body pursuant to the bid. Such assignment shall be made and become effective at the time the purchasing body tenders final payment to the bidder. Government Code Section 4552.

  - If an awarding body or public purchasing body receives, either through judgment or settlement, a monetary recovery for a cause of action assigned under this chapter, the assignor shall be entitled to receive reimbursement for actual legal costs incurred and may, upon demand, recover from the public body any portion of the recovery, including treble damages, attributable to overcharges that were paid by the assignor but were not paid by the public body as part of the bid price, less the expenses incurred in obtaining that portion of the recovery. Government Code Section 4553.

  - Upon demand in writing by the assignor, the assignee shall, within one year of such demand, reassign the cause of action assigned under this part if the assignor has been or may have been injured by the violation of law for which the cause of action arose and (a) the assignee has not been injured thereby, or (b) the assignee declines to file a court action for the cause of action. See Government Code Section 4554.

- Approval. This Agreement is of no force or effect until signed by both parties. Grantee may not commence performance until such approval has been obtained by the Commission. Unless otherwise specified in Exhibit A, each Report/Deliverable to be approved under this Agreement shall be approved by the Contract Manager. The Commission’s determination as to satisfactory work shall be final absent fraud or mistake.

- Assignment. This Agreement or any interest herein shall not be assigned without the prior written consent of the Commission.

- Audit. The Commission or California State Auditor or any State of California fiscal oversight agency has the right to audit performance under this Agreement. The auditor(s) shall be entitled to review and copy Contractor’s records and supporting documentation pertinent to its performance. Contractor agrees to maintain such records and documents for a minimum of three (3) years after final payment, for this purpose. Contractor agrees to allow the auditor(s) access to such records and documents as are relevant and pertinent, at its facilities during normal business hours; and to allow its employees to be interviewed as deemed necessary, in the professional opinion of the auditor(s). The Commission agrees to give Contractor advance written notice of any onsite audit. (Gov Code § 8546.7)

- Captions. The headings contained in this Agreement are for reference purposes only and shall not affect in any way the meaning or interpretation of this Agreement.

- Certification Clauses. The CONTRACTOR CERTIFICATION CLAUSES contained in the document DGS CCC 04/2017 are hereby incorporated by reference and made a part of this Agreement by this reference as if attached hereto.

- Child Support Compliance Act. For any Agreement in excess of $100,000, the contractor acknowledges in accordance with Public Contract Code 7110, that:

  - The Contractor recognizes the importance of child and family support obligations and shall fully comply with all applicable state and federal laws relating to child and family support enforcement, including, but not limited to, disclosure of information and compliance with earnings assignment orders, as provided in Chapter 8 (commencing with section 5200) of Part 5 of Division 9 of the Family Code; and

  - The Contractor, to the best of its knowledge is fully complying with the earnings assignment orders of all employees and is providing the names of all new employees to the New Hire Registry maintained by the California Employment Development Department.

- Change of Control. In the event Contractor undergoes a sale, merger or any other legal transaction resulting in a change of control, all of the rights and obligations of this Agreement shall inure to and be binding upon the legal representatives, successors and permitted assigns of the successor entity.

- Compensation. The consideration to be paid Contractor, as provided herein, shall be in compensation for all of Contractor's expenses incurred in the performance hereof, including travel, per diem, and taxes, unless otherwise expressly so provided.

- Confidentiality. Contractor shall not disclose data or documents or disseminate the contents of any preliminary data report or work product created under this Agreement without written permission of the Commission, and subject to the terms and conditions of Section 30 of this Exhibit C of the Agreement. Permission to disclose information or documents on one occasion shall not authorize Contractor to further disclose such information or documents on any other occasions except as otherwise provided in the Contract or required by law.

  - Contractor shall not comment publicly to the press or any other media regarding the data or documents generated, collected, or produced in connection with this contract, or the State’s actions on the same, except to the Commission staff, Contractor’s own personnel involved in the performance of this Agreement, or as required by law.

- Contract/Agreement is Complete. Other than as specified herein, no document or communication passing between the parties hereto shall be deemed a part of this Agreement.

- Copyright. Unless otherwise provided, all materials produced under this Agreement shall be considered "works for hire" as defined by the U.S. Copyright Act and shall be owned by the Commission. The Commission shall be considered the author of such materials. In the event the materials are not considered “works for hire” under the U.S. Copyright laws, Contractor hereby irrevocably assigns all right, title, and interest in materials, including all intellectual property rights, to the Commission effective from the moment of creation of such materials. Materials means all items in any format and includes, but is not limited to, data, reports, documents, pamphlets, advertisements, books, magazines, surveys, studies, computer programs, films, tapes, and/or sound reproductions. Ownership includes the right to copyright, patent, register and the ability to transfer these rights. For materials that are delivered under the contract, but that incorporate pre-existing materials not produced under the contract, Contractor hereby grants to the Commission a nonexclusive, royalty-free, irrevocable license (with rights to sublicense others) in such materials to translate, reproduce, distribute, prepare derivative works, publicly perform, and publicly display. The Contractor warrants and represents that Contractor has all rights and permissions, including intellectual property rights, moral rights and rights of publicity, necessary to grant such a license to the Commission. The Contractor shall exert all reasonable effort to advise the Commission, at the time of delivery of materials furnished under this contract, of all known or potential invasions of privacy contained therein and of any portion of such document that was not produced in the performance of this contract. The Commission shall receive prompt written notice of each notice or claim of infringement received by the Contractor with respect to any data delivered under this contract. The Commission shall have the right to modify or remove any restrictive markings placed upon the data by the Contractor.

- Contractor-Commission Collaboration. At the request of the Commission, Contractor shall permit Commission Staff to work closely with Contractor’s Staff, and Commission Staff shall be given access to Contractor’s data, working papers and other written materials as needed for this purpose.

- Counterparts. The parties may sign this Agreement in multiple counterparts, each of which constitutes an original, and all of which, collectively, constitute only one agreement.

- Dispute Resolution.

  - Contractor shall first discuss and attempt to resolve any dispute arising under its performance of this Agreement informally with the Commission Contract Manager. If the dispute cannot be disposed of at this level, it shall be decided by the Commission Executive Director for which purpose Contractor shall submit a written statement of dispute to: Executive Director, BHSOAC, 1812 9th Street, Sacramento, California 95811. The submission may be transmitted by email but must also be sent by overnight mail with proof of receipt (see provisions for Notice above).

  - Within ten (10) days of receipt of the statement described above, the Executive Director or designee shall meet Contractor’s manager(s) for the purpose of resolving the dispute. The Executive Director shall issue a decision to be served in the same manner as the written statement, which shall be final at the informal level.

  - After recourse to the informal level of dispute set forth above, any controversy or claim arising out of or relating to this Agreement or breach thereof shall be settled by arbitration at the election of either party in accordance with California Public Contract Code Section 10240 et. seq. and judgment upon the award rendered by the arbitration may be entered in any court having jurisdiction thereof.

  - While the informal dispute or arbitration process is pending, Contractor shall proceed diligently with its performance under the Agreement.

- Electronic Signature. Unless otherwise prohibited by law, the parties agree that an electronic signature has the same legal force and effect as a hard-copy with ink signature. The parties agree that a signed copy of this Agreement may be transmitted by electronic means including facsimile and email.

- Force Majeure. Neither the Commission nor the Contractor shall be deemed to be in default in the performance of the terms of this Agreement if either party is prevented from performing the terms of this Agreement by causes beyond its control, including without being limited to: acts of God; interference, rulings or decision by municipal, Federal, State or other governmental agencies, boards or commissions; any laws and/or regulations of such municipal, State, Federal, or other governmental bodies; or any catastrophe resulting from flood, fire, explosion, or other causes beyond the control of the defaulting party. If any of the stated contingencies occur, the party delayed by force majeure shall immediately give the other party written notice of the cause of delay. The party delayed by force majeure shall use reasonable diligence to correct the cause of the delay, if correctable.

- Forum Selection. The County of Sacramento in the State of California shall be the proper forum for any dispute between the parties regarding this Agreement.

- GenAI Technology Use & Reporting. During the term of the contract, Contractor must notify the State in writing if their services or any work under this contract includes, or makes available, any previously unreported GenAI technology, including GenAI from third parties or subcontractors. The Contractor shall immediately complete the GenAI Reporting and Factsheet (STD 1000) to notify the State of any new or previously unreported GenAI technology. At the direction of the State, Contractor shall discontinue the use of any new or previously undisclosed GenAI technology that materially impacts functionality, risk or contract performance, until use of such GenAI technology has been approved by the State. Failure to disclose GenAI use to the State and submit the GenAI Reporting and Factsheet (STD 1000) may be considered a breach of the contract by the State at its sole discretion and the State may consider such failure to disclose GenAI and/or failure to submit the GenAI Reporting and Factsheet (STD 1000) as grounds for the immediate termination of the contract.  The State is entitled to seek any and all relief it may be entitled to as a result of such non-disclosure.

- Governing Law. This Agreement is governed by and shall be interpreted in accordance with the laws of the State of California.

- Government Purpose Rights. Contractor hereby grants “Government Purpose Rights” to the Work Product produced pursuant to this Agreement, defined as: the unlimited, irrevocable, worldwide, perpetual, royalty-free, non-exclusive rights, and licenses to use, modify, reproduce, perform, release, display, create derivative works from, and disclose the Work Product. These Rights also include the right to release or disclose the Work Product outside the Commission for any State government purpose and to authorize recipients to use, modify, reproduce, perform, release, display, create derivative works from, and disclose the Work Product for any public purpose. These rights do not include any rights to use, modify, reproduce, perform, release, display, create derivative works from, or disclose the Work Product for any commercial purpose.

- Gratuities and Contingency Fees. The Commission, by written notice to the Contractor, may terminate the right of Contractor to proceed under this Agreement if it is found, after notice and hearing by the State, that gratuities were offered or given by the Contractor or any agent or representative of the Contractor to any officer or employee of the State with a view toward securing a contract or securing favorable treatment with respect to the awarding, amending, or performing of such contract.

  - In the event this Agreement is terminated as provided in the paragraph above, the State shall be entitled (a) to pursue the same remedies against Contractor as it could pursue in the event of the breach of the Agreement by the Contractor, and (b) as a predetermined amount of liquidated damages, to exemplary damages in an amount which shall not be less than three times the cost incurred by the Contractor in providing any such gratuities to any such officer or employee.

  - The rights and remedies of the State provided in this clause shall not be exclusive and are in addition to any other rights and remedies provided by law or under this Agreement.

  - The Contractor warrants by execution of this Agreement that no person or selling agency has been employed or retained to solicit or secure this Agreement for a commission, percentage, brokerage or contingent fee, excepting bona fide employees of Contractor, for the purpose of securing business. For breach or violation of this warranty, the Commission shall have the right to annul this Agreement without liability, paying only for the values of the work actually returned, or in its discretion to deduct from the contract price or consideration, or otherwise recover, the full amount of such commission, percentage, brokerage, or contingent fee.

- Indemnification. Contractor agrees to indemnify, defend and save harmless the State, its officers, agents and employees from any and all claims and losses accruing or resulting to any and all contractors, subcontractors, suppliers, laborers, and any other person, firm or corporation furnishing or supplying work services, materials, or supplies in connection with the performance of this Agreement, and from any and all claims and losses accruing or resulting to any person, firm or corporation who may be injured or damaged by Contractor in the performance of this Agreement.

- Independent Contractor. Contractor, and the agents and employees of Contractor, in the performance of this Agreement, shall act in an independent capacity and not as officers or employees or agents of the State.

- Information Security. Contractor shall comply with applicable laws and regulations, including but not limited to Sections 14100.2 and 5328 et seq. of the Welfare and Institutions Code, Section 431.300 et seq. of Title 42, Code of Federal Regulations, and the Health Insurance Portability and Accountability Act (HIPAA), and it’s implementing regulations (including but not limited to Title 45, CFR, Parts 160, 162 and 164) regarding the confidentiality and security of individually identifiable health information (IIHI).

- Key Personnel. Contractor’s key personnel, as may be identified in this Agreement, cannot be substituted without the Commission’s prior written approval.

- Litigation. The Commission, promptly after receiving notice thereof, shall notify the Contractor in writing of the commencement of any claim, suit, or action against the State or its officers or employees for which the Contractor must provide indemnification under this Agreement.

  - The failure of the Commission to give such notice, information, authorization or assistance shall not relieve the Contractor of its indemnification obligations. The Contractor shall immediately notify the Commission of any claim or action against it which affects, or may affect, this Agreement, the terms and conditions hereunder, or the State, and shall take such action with respect to said claim or action which is consistent with the terms of this Agreement and the interest of the State.

- Limited License and Fair Use. Upon request, the Commission may assign Contractor a limited, non-exclusive, royalty-free License to use materials produced under this Agreement for which the Commission holds the copyright. This License shall be limited to the following purposes: research, professional publication or educational outreach. Furthermore, the Commission recognizes the Fair Use Doctrine in U.S. copyright law, by which it is permissible to use limited portions of a work including quotes for purposes such as commentary, criticism, scholarly reports and more as identified at Copyright.gov.

- Loss Leader. If this Agreement involves the furnishing of equipment, materials, or supplies then the following statement is incorporated: It is unlawful for any person engaged in business within this state to sell or use any article or product as a "loss leader" as defined in Section 17030 of the Business and Professions Code. (Pub. Contract Code §10344(e)).

- Commission Logo. The Commission may, in its sole discretion, grant Contractor a limited, non-exclusive, non-transferable, revocable license to use the Commission's logo bearing the name "Commission for Behavioral Health (CBH)" solely in connection with Contractor's performance of its obligations under this Agreement. All uses of the logo by the Contractor must receive prior written approval from the Commission Executive Director. Contractor understands and agrees that it must adhere to the CBH Branding Guidelines posted on the Commission’s website, as a condition of usage. The Commission may revoke the license granted herein at any time, with or without cause, upon written notice to Contractor.

- Contractor understands and agrees that it must adhere to the CBH Branding Guidelines as a condition of usage. Contractor shall request a copy of the CBH Branding Guidelines from the Commission, if applicable to Contractor’s work.

- Nondisclosure. Contractor shall not use or disclose confidential, individually identifiable, or sensitive information other than as permitted or required by the Agreement and as permitted or required by law.

- Non-Discrimination. During the performance of this Agreement, Contractor and its subcontractors shall not deny the contract’s benefits to any person on the basis of race, religious creed, color, national origin, ancestry, physical disability, mental disability, medical condition, genetic information, marital status, sex, gender, gender identity, gender expression, age, sexual orientation, or military and veteran status, nor shall they discriminate unlawfully against any employee or applicant for employment because of race, religious creed, color, national origin, ancestry, physical disability, mental disability, medical condition, genetic information, marital status, sex, gender, gender identity, gender expression, age, sexual orientation, or military and veteran status. Contractor shall ensure that the evaluation and treatment of employees and applicants for employment are free of such discrimination. Contractor and subcontractors shall comply with the provisions of the Fair Employment and Housing Act (Gov. Code §12900 et seq.), the regulations promulgated thereunder (Cal. Code Regs., tit. 2, §11000 et seq.), the provisions of Article 9.5, Chapter 1, Part 1, Division 3, Title 2 of the Government Code (Gov. Code §§11135-11139.5), and the regulations or standards adopted by the awarding state agency to implement such article. Contractor shall permit access by representatives of the Department of Fair Employment and Housing and the awarding state agency upon reasonable notice at any time during the normal business hours, but in no case less than 24 hours’ notice, to such of its books, records, accounts, and all other sources of information and its facilities as said Department or Agency shall require ascertaining compliance with this clause. Contractor and its subcontractors shall give written notice of their obligations under this clause to labor organizations with which they have a collective bargaining or other agreement. (See Cal. Code Regs., tit. 2, §11105.).

  - Contractor shall include the nondiscrimination and compliance provisions of this clause in all subcontracts to perform work under the Agreement.

- Notice. The parties agree that any document or notice required under this Agreement, including reports and other communications, shall be made in writing to the other party’s Contract Manager as identified in Exhibit A. Except for Notices of Termination, which must be sent by overnight mail with proof of receipt to the appropriate Contract Manager, the parties agree that email will be considered sufficient for any and all notices, reports and other documents required under this Agreement.

- Notice of Litigation. Contractor shall promptly notify the Commission of any claim or action that may affect performance under this Agreement.

- Permits and Licenses. Contractor shall procure and keep in full force and effect during the term of this Contract all permits, registrations and licenses necessary to accomplish the work specified in this Agreement, and give all notices necessary and incident to the lawful prosecution of the work.

  - Contractor shall keep informed of, observe, comply with, and cause all its agents and employees to observe and to comply with all prevailing Federal, State, and local laws, and rules and regulations made pursuant to said Federal, State, and local laws, which in any way affect the conduct of the work of this Agreement. If any conflict arises between provisions of the plans and specifications of this Agreement and any such law above referred to, then the Contractor shall immediately notify the Commission in writing.

- Priority Hiring Considerations. If this Agreement includes services in excess of $200,000, the Contractor shall give priority consideration in filling vacancies in positions funded by the Agreement to qualified recipients of aid under Welfare and Institutions Code Section 11200 in accordance with Pub. Contract Code §10353.

- Public Hearings. If public hearings on the subject matter dealt with in this Agreement are held within one year from the contract expiration date, Contractor shall make available to testify the personnel assigned to this Contract at the hourly rates specified in the Contractor’s proposed budget. The Commission shall reimburse Contractor for travel of said personnel at the contract rates for such testimony as may be requested by the Commission.

- Public Records Act. This Agreement is subject to the California Public Records Act (PRA) in Government Code Section 7920.000 et seq. Under a Public Records Act Request, Contractor may be required to provide information regarding any aspect of this Agreement to the Commission. Under the PRA, medical records, data and any other information in the custody of the Commission are exempt from disclosure to the extent they contain personally identifiable information and shall be withheld from disclosure to that extent. The Commission will coordinate with federal entities on disclosure of public records should there be a joint request under the PRA and the federal Freedom of Information Act.

- Publications and Reports. The Commission reserves the right to use and reproduce all reports and data produced and delivered under this Agreement. The Commission further reserves the right to authorize others to use or reproduce such materials.

  - If the publication and/or report are prepared by non-employees of the State, and the total cost for such preparation exceeds $5,000, the publication and/or report shall contain the numbers and dollar amounts of all contracts and subcontracts relating to the preparation of the publication and report in a separate section of the report (Government Code Section 7550).

- Recycling Certification. Contractor shall certify in writing under penalty of perjury, the minimum, if not exact, percentage of post-consumer material as defined in the Public Contract Code Section 12200, in products, materials, goods, or supplies offered or sold to the Commission regardless of whether the product meets the requirements of Public Contract Code Section 12209. With respect to printer or duplication cartridges that comply with the requirements of Section 12156(e), the certification required by this subdivision shall specify that the cartridges so comply. (Pub. Contract Code §12205).

- Severability. In the event any provision of this Agreement is unenforceable or held to be unenforceable, then the parties agree that all other provisions of this Agreement have force and effect and shall not be affected thereby.

- Small Business Participation and DVBE Participation Reporting Requirements.

  - If for this Agreement, Contractor made a commitment to achieve a small business participation, then Contractor must within 60 days of receiving final payment under this Agreement (or within such other time period as may be specified elsewhere in this Agreement) report to the awarding department the actual percentage of small business participation that was achieved. (Govt. Code §14841.).

  - If for this Agreement, Contractor made a commitment to achieve a disabled veteran business enterprise (DVBE) participation, then Contractor must within 60 days of receiving final payment under this Agreement (or within such other time period as may be specified elsewhere in this Agreement) certify in a report to the awarding department: (1) the total amount of the prime Contractor received under the Agreement; (2) the name and address of the DVBE(s) that participated in the performance of the Agreement; (3) the amount each DVBE received from the prime Contractor; (4) that all payments under the Agreement have been made to the DVBE; and (5) the actual percentage of the DVBE participation that was achieved. A person or entity that knowingly provides false information shall be subject to a civil penalty for each violation. (Mil. & Vets. Code §999.5(d); Govt. Code §14841).

- State Funds. Contractor, including its officers and members, shall not use funds received from the Commission pursuant to this Agreement to support or pay for costs or expenses related to the following:

  - Campaigning or other partisan activities to advocate for either the election or defeat of any candidate for elective office, or for or against the passage of any proposition or ballot measure; or,

  - Lobbying for either the passage or defeat of any legislation.

This provision is not intended and shall not be construed to limit any activities specified in this Agreement that are intended to inform, educate, and support advocacy before local and state administrative and legislative bodies regarding policies and issue-based legislation consistent with the BHSA.

This provision is not intended and shall not be construed to limit any expression of a view, opinion, or position of any member of Contractor as an individual or private citizen, as long as state funds are not used; nor does this provision limit Contractor from merely reporting the results of a poll or survey of its membership.

- Subcontracts. Prior to entering any subcontract, Contractor shall obtain the Commission’s prior approval. Contractor shall provide a list of all subcontractors in initial, progress and final reports to the Commission, or upon request. If the Commission determines that a subcontract was executed without prior approval, a ten percent (10%) penalty may be applied against total funding at or before fiscal close-out. Contractor shall notify the Commission upon the termination of any subcontract , at least two weeks in advance of the termination. All subcontracts shall incorporate the following terms and conditions from this Exhibit C: Audit, Assignment, Confidentiality, Copyright, Forum Selection, Governing Law, Indemnification, Independent Contractor, Non-Discrimination, Public Records Act, Publication and Reports and Subcontracts.

- Substitutions. Contractor’s key personnel as indicated in its Proposal may not be substituted without Contract Manager’s prior written approval.

- Survival. The following terms and conditions in this Exhibit C shall survive termination of this Agreement: Audit, Assignment, Confidentiality, Copyright, Dispute Resolution, Forum Selection, Governing Law, Indemnification, Public Records Act, and Publication and Reports.

- Termination For Cause. The Commission may terminate this Agreement and be relieved of any payments should the Contractor fail to perform the requirements of this Agreement at the time and in the manner herein provided. In the event of such termination the Commission may proceed with the work in any manner deemed proper by the Commission. All costs to the Commission shall be deducted from any sum due the Contractor under this Agreement and the balance, if any, shall be paid to the Contractor, pursuant to Exhibit B of this Agreement, upon demand.

- Termination Without Cause. Either party is entitled to terminate this Agreement without cause upon serving written Notice on the named representative of the other party at least thirty (30) days in advance. The Commission shall be relieved from any obligation to pay Contractor for performance that is interrupted or not delivered as a result of termination. The Commission shall pay the Contractor for any balance remaining, pursuant to Exhibit B of this Agreement, for work satisfactorily performed. The Commission shall also be entitled to an accounting of the use of the funds and is entitled to a refund of any unused and uncommitted funds attributable to actions that have not occurred as of the date of the Notice of termination.

- Timeliness. Time is of the essence in this Agreement.

- Unenforceable Provision. In the event that any provision of this Agreement is unenforceable or held to be unenforceable, then the parties agree that all other provisions of this Agreement have force and effect and shall not be affected thereby.

- Waiver. Waiver of breach under this Agreement shall not be held to be a waiver of any other or subsequent breach. All remedies afforded in this Agreement shall be cumulative in addition to any other remedy provided by law. Any failure by the Commission to enforce a provision(s) of this Agreement shall not be construed as a waiver nor shall it affect the validity of the entire Agreement.

- Worker’s Compensation. Contractor hereby warrants that it carries and shall maintain in full force and effect during the full term of this contract and any extensions to said term, sufficient and adequate Worker’s Compensation Insurance for all its employees who shall be engaged in the performance of this Agreement and agrees to furnish to Commission satisfactory evidence thereof at any time the Commission may request the same.

- Work For Hire. Contractor understands and agrees that all original works created and delivered under this Agreement is “work for hire” and owned by the Commission as of the time created, including the website development (programming), content and design. Contractor also grants the Commission the right to use and reproduce all Reports and data generated and delivered under this Agreement, and the Commission reserves the right to authorize another government entity to use or reproduce such materials.

- Generative AI Disclosure Obligations.

  - The following terms are in addition to the defined terms and shall apply to the Contract:

    - “Generative AI (GenAI)” means an artificial intelligence system that can generate derived synthetic content, including text, images, video, and audio that emulates the structure and characteristics of the system's training data. (Gov. Code § 11549.64 and any updates thereto)

  - Contractor shall immediately notify the State in writing if it: (1) intends to provide GenAI as a deliverable to the State; or (2), intends to utilize GenAI, including GenAI from third parties, to complete all or a portion of any deliverable that materially impacts: (i) functionality of a State system, (ii) risk to the State, or (iii) Contract performance. For avoidance of doubt, the term “materially impacts” shall have the meaning set forth in State Administrative Manual (SAM) § 4986.2 Definitions for GenAI.

  - Notification shall be provided to the State designee identified in this Contract.

  - At the direction of the State, Contractor shall discontinue the provision to the State of any previously unreported GenAI that results in a material impact to the functionality of the System, risk to the State, or Contract performance, as determined by the State.

  - If the use of previously undisclosed GenAI is approved by the State, then Contractor will update the Deliverable description, and the Parties will amend the Contract accordingly, which may include incorporating the GenAI Special Provisions into the Contract, at no additional cost to the State.

  - The State, at its sole discretion, may consider Contractor’s failure to disclose or discontinue the provision or use of GenAI as described above, to constitute a material breach of Contract when such failure results in a material impact to the functionality of the System, risk to the State, or Contract performance. The State is entitled to seek any and all remedies available to it under law as a result of such breach, including but not limited to termination of the contract.

The State reserves the right to amend the contract, without additional cost, to incorporate GenAI Special Provisions into the contract at its sole discretion and/or terminate any contract that presents an unacceptable level of risk to the State.

## EXHIBIT D: BUDGET AND NARRATIVE

See Excel workbook EXHIBIT D - Budget and Narrative.xlsx to complete this requirement.

## APPENDIX 2: WORKPLAN

| Scope of Work: Describe your approach and timeline for completing the indicated Scope of Work responsibilities and deliverables. |  | Schedule and Milestones: Indicate project milestones and completion dates for each item and specify all date(s) as days weeks, months, quarters, and/or years. |
| --- | --- | --- |
| 1. Planning Phase: |  |  |
| - Develop a Leadership Academy curriculum that is co-designed with TAY members, culturally responsive, and covers leadership skills, advocacy strategies, behavioral health policy and systems knowledge, and effective communication. |  |  |
| - Produce an Advocacy Toolkit informed by the Leadership Academy. |  |  |
| - Design and implement a recruitment strategy that attracts a diverse group of TAY to each cohort. |  |  |
| 2. Operations Phase: |  |  |
| a. Implementation: |  |  |
| - Establish and facilitate three (3) nine (9) month cohorts of recruited TAY members who will receive, engage with, and apply the co-designed Leadership Academy curriculum and practice learned skills. |  |  |
| - Support cohort members in identifying and developing TAY advocacy projects that reflect the needs of their communities, with an emphasis on BHSA priority populations. |  |  |
| - Provide opportunities for cohort members to perform outreach and engagement to TAY communities to ensure their voices and priorities are reflected in their TAY advocacy projects. |  |  |
| - Facilitate opportunities for cohort members to practice advocating for their TAY advocacy projects in state and local settings, such as the BHSA Community Planning Process. |  |  |
| - Foster peer-to-peer connections and community-building within cohorts and the broader TAY network including, but not limited to, TAY individuals and TAY-focused organizations to promote trust, belonging, and sustained engagement. |  |  |
| - Encourage cohort members to co-lead and co-facilitate learning sessions on topics identified by each cohort to inform their final projects, whenever possible, ensuring ongoing input and adaptation based on cohort feedback. |  |  |
| b. Additional Supportive Services: |  |  |
| - Behavioral Health Career Pathways |  |  |
| - Educational and Financial Resources |  |  |
| c. Supportive Funding: |  |  |
| - Recruitment and Retention Funds |  |  |
| - Equity Access Funds |  |  |
| 3. Evaluation Phase: |  |  |
| - Training and Curriculum Quality |  |  |
| - Organizational Capacity and Execution |  |  |
| - Outreach and Engagement Reach |  |  |
| - Adaptability and Learning |  |  |
| - TAY Participant Growth and Empowerment |  |  |
| - Advocacy Skill-Building and Systems Exposure |  |  |
| - Field-Level Learning and Influence |  |  |
| 4. Deliverables: |  |  |
| - Final Workplan |  |  |
| - Quarterly Progress Reports |  |  |
| - Leadership Academy Curriculum |  |  |
| - TAY Impact Showcase and Story Collection |  |  |
| - Advocacy Toolkit |  |  |
| - Final Report & Evaluation |  |  |

Welfare and Institutions Code (WIC) §5845

WIC §5892(d) and (k)(7)(A), as operative July 1, 2026.

WIC §§ 5963 - 5963.03

WIC § 5892(f)(1)(B), as operative July 1, 2026

California Department of Health Care Services, Integrated Plans.

California Department of Health Care Services, Behavioral Health Services Act County Policy Manual.

California Department of Public Health Behavioral Health Services Act Population-Based Prevention Program Guide.

WIC § 5892 (a) - (f), as operative July 1, 2026

Commission for Behavioral Health’s Community Advocacy.